## Slide 1
Tata McGraw

## Slide 2
Chapter 3
Project Management

## Slide 3
Definition of Project Management
Work Breakdown Structure
Project Control Charts
Structuring Projects
Critical Path Scheduling
OBJECTIVES
3-<number>
Notes: 2

## Slide 4
A Project is a series of related jobs usually directed toward some major output and requiring a significant period of time to perform
Project Management are the management activities of planning, directing, and controlling resources (people, equipment, material) to meet the technical, cost, and time constraints of a project
Project Management Defined
3-<number>
Notes: 3

## Slide 5: Gantt Chart
Activity 1
Activity 2
Activity 3
Activity 4
Activity 5
Activity 6
Time
Vertical Axis: Always Activities or Jobs
Horizontal Axis: Always Time
Horizontal bars used to denote length of time for each activity or job.
3-<number>
Notes: 6

## Slide 6: Structuring Projects Pure Project: Advantages
Pure Project
Defined
A pure project is where a self-contained team works full-time on the project
The project manager has full authority over the project
Team members report to one boss
Shortened communication lines
Team pride, motivation, and commitment are high
3-<number>
Notes: 8

## Slide 7: Structuring Projects Pure Project: Disadvantages
Duplication of resources
Organizational goals and policies are ignored
Lack of technology transfer
Team members have no functional area "home"
3-<number>
Notes: 8

## Slide 8: Functional Project
President
Research and
Development
Engineering
Manufacturing
Project
A
Project
B
Project
C
Project
D
Project
E
Project
F
Project
G
Project
H
Project
I
A functional project is housed within a functional division
Example, Project “B” is in the functional area of Research and Development.
3-<number>
Notes: 9

## Slide 9: Structuring Projects Functional Project: Advantages
A team member can work on several projects
Technical expertise is maintained within the functional area
The functional area is a “home” after the project is completed
Critical mass of specialized knowledge
3-<number>
Notes: 10

## Slide 10: Structuring Projects Functional Project: Disadvantages
Aspects of the project that are not directly related to the functional area get short-changed
Motivation of team members is often weak
Needs of the client are secondary and are responded to slowly
3-<number>
Notes: 11

## Slide 11: Matrix Project Organization Structure
President
Research and
Development
Engineering
Manufacturing
Marketing
Manager
Project A
Manager
Project B
Manager
Project C
3-<number>
Notes: 12

## Slide 12: Structuring Projects Matrix: Advantages
Enhanced communications between functional areas
Pinpointed responsibility
Duplication of resources is minimized
Functional “home” for team members
Policies of the parent organization are followed
3-<number>
Notes: 13

## Slide 13: Structuring Projects Matrix: Disadvantages
Too many bosses
Depends on project manager’s negotiating skills
Potential for sub-optimization
3-<number>
Notes: 14

## Slide 14
Statement of Work
  A written description of the objectives to be achieved
Task
  A further subdivision of a project – usually shorter than several months and performed by a single group or organization
Work Package
  A group of activities combined to be assignable to a single organizational unit

## Slide 15
Project Milestone
  Specific events in the life of the project
Work Breakdown Structure
  Defines the hierarchy of project tasks, subtasks, and work packages
Activities
  Pieces of work that consume time

## Slide 16: Work Breakdown Structure
Program
Project 1
Project 2
Task 1.1
Subtask 1.1.1
Work Package 1.1.1.1
Level
1
2
3
4
Task 1.2
Subtask 1.1.2
Work Package 1.1.1.2
A work breakdown structure defines the hierarchy of project tasks, subtasks, and work packages
3-<number>
Notes: 4

## Slide 18: Prerequisites for Critical Path Methodology
A project must have:
well-defined jobs or tasks whose completion marks the end of the project;
independent jobs or tasks;
and tasks that follow a given sequence.
3-<number>
Notes: 16

## Slide 19: Types of Critical Path Methods
CPM with a Single Time Estimate
  Used when activity times are known with certainty
  Used to determine timing estimates for the project, each activity in the project, and slack time for activities
CPM with Three Activity Time Estimates
  Used when activity times are uncertain
  Used to obtain the same information as the Single Time Estimate model and probability information
Time-Cost Models
  Used when cost trade-off information is a major consideration in planning
  Used to determine the least cost in reducing total project time
3-<number>
Notes: 15

## Slide 21: Steps in the CPM with Single Time Estimate
Activity Identification
Activity Sequencing and Network Construction
Determine the critical path
  From the critical path all of the project and activity timing information can be obtained
3-<number>
Notes: 15

## Slide 22: CPM with Single Time Estimate
Consider the following consulting project:
Activity
Designation
Immed. Pred.
Time (Weeks)
Assess customer's needs
A
None
2
Write and submit proposal
B
A
1
Obtain approval
C
B
1
Develop service vision and goals
D
C
2
Train employees
E
C
5
Quality improvement pilot groups
F
D, E
5
Write assessment report
G
F
1
Develop a critical path diagram and determine the duration of the critical path and slack times for all activities.
3-<number>

## Slide 23: First draw the network
A(2)
B(1)
C(1)
D(2)
E(5)
F(5)
G(1)
A None 2
B A 1
C B 1
D C 2
E C 5
F D,E 5
G F 1
Act. Imed. Pred. Time
3-<number>
Notes: 18

## Slide 24: Determine early starts and early finish times
ES=9
EF=14
ES=14
EF=15
ES=0
EF=2
ES=2
EF=3
ES=3
EF=4
ES=4
EF=9
ES=4
EF=6
A(2)
B(1)
C(1)
D(2)
E(5)
F(5)
G(1)
Hint: Start with ES=0 and go forward in the network from A to G.
3-<number>
Notes: 21

## Slide 25: Determine late starts and late finish times
ES=9
EF=14
ES=14
EF=15
ES=0
EF=2
ES=2
EF=3
ES=3
EF=4
ES=4
EF=9
ES=4
EF=6
A(2)
B(1)
C(1)
D(2)
E(5)
F(5)
G(1)
LS=14
LF=15
LS=9
LF=14
LS=4
LF=9
LS=7
LF=9
LS=3
LF=4
LS=2
LF=3
LS=0
LF=2
Hint: Start with LF=15 or the total time of the project and go backward in the network from G to A.
3-<number>
Notes: 22

## Slide 26: Critical Path & Slack
ES=9
EF=14
ES=14
EF=15
ES=0
EF=2
ES=2
EF=3
ES=3
EF=4
ES=4
EF=9
ES=4
EF=6
A(2)
B(1)
C(1)
D(2)
E(5)
F(5)
G(1)
LS=14
LF=15
LS=9
LF=14
LS=4
LF=9
LS=7
LF=9
LS=3
LF=4
LS=2
LF=3
LS=0
LF=2
Duration=15 weeks
Slack=(7-4)=(9-6)= 3 Wks
3-<number>
Notes: 23

## Slide 27: Example 2. CPM with Three Activity Time Estimates
3-<number>

## Slide 28
End of Chapter 3
3-<number>