| King Saud University | CE 417 Ch. 17 |  |
| --- | --- | --- |
| Collage of Engineering |  | Eng. Saad Al-Jadhai |
| Civil Engineering Department | Tutorial No.9 | 1st semester 1431-1432 |

Question

Financial data for a project are shown below. Plot the accumulated project expenditures, value of work, progress payments received versus time. What is the contractor's maximum negative cash flow and when does it occur? Progress payments are calculated at the end of each month and received the middle of the following month. Retainage is 10% until project completion. Assume that final project payment, including released retainage, is received the middle of the month following project completion.

| Month | End of month cumulative |  | Actual Receipt | Before Payment | After Payment |
| --- | --- | --- | --- | --- | --- |
|  | Expenditure | Value of work |  |  |  |
| 1 | 14000 | 10500 |  |  |  |
| 1.5 | 24000 |  | 9450 & | 24000* | 14550** |
| 2 | 34000 | 28000 |  |  |  |
| 2.5 | 46000 |  | 25200 | 36550 # | 20800 ## |
| 3 | 58000 | 56000 |  |  |  |
| 3.5 | 72000 |  | 50400 | 46800 | 21600 |
| 4 | 86000 | 92000 |  |  |  |
| 4.5 | 106000 |  | 82800 | 55600 | 23200 |
| 5 | 126000 | 134000 |  |  |  |
| 5.5 | 129000 |  | 120600 | 46200 | 8400 |
| 6 | 132000 | 145000 |  |  |  |
| 6.5 | 136000 |  | 130500 | 15400 | 5500 |
| 7 | 140000 | 160000 |  | 9500 $ |  |
| 7.5 |  |  | 160000 |  |  |

& 10500 * 0.9 = 9450				## 46000-25200 = 20800

* 24000-0=24000					# 46000-9450 = 36550

** 24000-9450= 14550				$ 140000-130500 = 9500

Maximum negative cash flow= SR 55600		at month 4.5

9500

- 20000