## Slide 1: Maintenance Scheduling
Industrial Engineering Department
King Saud University
Industrial Engineering Department

## Slide 2: MAINTENANCE PLANNING AND SCHEDULING
Effective planning and scheduling contribute significantly to the following:
Reduced maintenance cost.
Improved utilization of the maintenance workforce by reducing delays and interruptions.
Improved quality of maintenance work by adopting the best methods and procedures and assigning the most qualified workers for the job.

## Slide 3: Planning and Scheduling Objectives
Minimizing the idle time of maintenance workers.
Maximizing the efficient use of work time, material, and equipment.
Maintaining the operating equipment at a responsive level to the need of production in terms of delivery schedule and quality.

## Slide 4: Classification of Maintenance Work According to Planning and Scheduling Purposes
Routine maintenance: are maintenance operations of a periodic nature. They are planned and scheduled and in advance. They are covered by blanket orders.
Emergency or breakdown maintenance: interrupt maintenance schedules in order to be performed. They are planned and scheduled as they happened.

## Slide 5
Design modifications: are planned and scheduled and they depend on eliminating the cause of repeated breakdowns.
Scheduled overhaul and shutdowns of the plant: planned and scheduled in advanced.
Overhaul, general repairs, and replacement: planned and scheduled in advanced.
Preventive maintenance: planned and scheduled in advanced.

## Slide 6
An essential part of planning and scheduling is to forecast future work and to balance the workload between these categories.
The maintenance management system should aim to have over 90% of the maintenance work planned and scheduled.

## Slide 7: Planning
Planning is the process by which the elements required to perform a task are determined in advance of the job start.

## Slide 8: Planning
It comprises all the functions related to the preparation of:
  The work order
  Bill of material
  Purchase requisition
  Necessary drawings
  Labor planning sheet including standard times
  All data needed prior to scheduling and releasing the work order.
Good planning is a prerequisite for sound scheduling.

## Slide 9: Planning Procedures
Determine the job content.
Develop work plan. This entails the sequence of the activities in the job and establishing the best methods and procedures to accomplish the job.
Establish crew size for the job.
Plan and order parts and material.
Check if special tools and equipment are needed and obtain them.
Assign workers with appropriate skills.

## Slide 10: Planning Procedures
Review safety procedures.
Set priorities for all maintenance work.
Assign cost accounts.
Complete the work order.
Review the backlog and develop plans for controlling it.
Predict the maintenance load using effective forecasting technique.

## Slide 11: Basic Levels of Planning Process (Depend on The Planning Horizon)
Long-rang planning: it covers a period of 3 to 5 years and sets plans for future activities and long-range improvement.
Medium-range planning: it covers a period of 1 month to 1 year.
Short-rang planning: it covers a period of 1 day to 1 week. It focuses on the determination of all the elements required to perform maintenance tasks in advance.

## Slide 12: Long and Medium-Range Planning
Needs to utilize the following:
Sound forecasting techniques to estimate the maintenance load.
Reliable job standards times to estimate staffing requirements.
Aggregate planning tools such as linear programming to determine resource requirements.

## Slide 13: Long-Range Planning
sets plans for future activities and long-range improvement.

## Slide 14: Medium-Range Planning
Specify how the maintenance workers will operate.
Provide details of major overhauls, construction jobs, preventive maintenance plans, and plant shutdowns.
Balances the need for staffing over the period covered.
Estimates required spare parts and material acquisition.

## Slide 15: Short-Range Planning
It focuses on the determination of all the elements required to perform maintenance tasks in advance.

## Slide 16: Scheduling
Is the process by which jobs are matched with resources and sequenced to be executed at a certain points in time.

## Slide 17: Scheduling
Scheduling deals with the specific time and phasing of planned jobs together with the orders to perform the work, monitoring the work, controlling it, and reporting on job progress.
Successful planning needs a feedback from scheduling.

## Slide 18: Reliable Schedule Must Take Into Consideration
A job priority ranking reflecting the criticality of the job.
The availability of all materials needed for the work order in the plant.
The production master schedule.
Realistic estimates and what is likely to happen.
Flexibility in the schedule.

## Slide 19: Elements of Sound Scheduling
Requirements for effective scheduling:
Written work orders that are derived from a well-conceived planning process. (Work to be done, methods to be followed, crafts needed, spare parts needed, and priority).
Time standards.
Information about craft availability for each shift.
Stocks of spare parts and information on restocking.

## Slide 20: Elements of Sound Scheduling
Requirements for effective scheduling:
Information on the availability of special equipment and tools necessary for maintenance work.
Access to the plant production schedule and knowledge about when the facilities will be available for service without interrupting production schedule.
Well-define priorities for maintenance work.
Information about jobs already scheduled that are behind the schedule (backlog).

## Slide 21: Maintenance Schedule Can be Prepared at Three Levels (Depend on The Time Horizon)
Long-range (master) schedule
Weekly schedule
Daily schedule

## Slide 22: Long-Range (master) Schedule
Covering a period of 3 months to 1 year.
Based on existing maintenance work orders (blanket work order, backlog, PM, anticipated EM).
Balancing long-term demand for maintenance work with available resources.
Spare parts and material could be identified and ordered in advance.
Subject to revision and updating to reflect changes in the plans and maintenance work.

## Slide 23: Weekly Schedule
Covering 1 week.
Generated from the master schedule.
Takes into account current operations schedules and economic considerations.
Allow 10% to 15% of the workforce to be available for emergency work.
The schedule prepared for the current week and the following one in order to consider the available backlog.
The work orders scheduled in this week are sequenced based in priority.
CPM and integer programming techniques can be used to generate a schedule.

## Slide 24: Daily Schedule
Covering 1 day.
Generated from weekly schedule.
Prepared the day before.
Interrupted to perform EM.
Priorities are used to schedule the jobs.

## Slide 25: Scheduling Procedures (Steps)
Sort backlog work orders by crafts.
Arrange orders by priority.
Compile a list of completed and carry over jobs.
Consider job duration, location, travel distance, and the possibility of combining jobs in the same area.
Schedule multi-craft jobs to start at the beginning of every shift.
Issue a daily schedule (not for shutdown maintenance).
Authorize a supervisor to make work assignments (dispatching).

## Slide 26: Maintenance Job Priority System
Priorities are established to ensure that the most critical work is scheduled first.
It is developed under coordination with operations staff.
It should be dynamic.
It must be updated periodically to reflect changes in operation and maintenance strategies.
It typically includes three to ten levels of priority.

## Slide 27: Priorities of Maintenance Work

## Slide 28: Scheduling Techniques
The objective of the scheduling techniques is to construct a time chart showing:
The start and finish for each job.
The interdependencies among jobs.
The critical jobs that require special attention and effective monitoring.

## Slide 29: Scheduling Techniques
Such techniques are:
Modified Gantt chart
CPM
PERT
Integer and stochastic programming.

## Slide 30
<number>
Example
Maintenance Scheduling
Scheduling Techniques
Example
Industrial Engineering
  Gantt Chart
Notes: <number>