King Saud University

College of Engineering

Department of Civil Engineering

GE 402:  MANAGEMENT OF ENGINEERING PROJECTS

| No | Topic | Reading Assignment | Duration “Weeks” |
| --- | --- | --- | --- |
| 1 | Introduction | Ch. 1 | 1 |
| PROJECT PLANNING |  |  |  |
| 2 | Gantt Bar Chart | Ch. 1 | 1 |
| 3 | Network-based Critical Path Methods (CPM) Arrow Diagramming: Activity-On-Arrow (AOA) | Ch. 2 (pp. 21-34) Ch. 3 (pp. 47-53) Ch. 4 (pp. 72-82) | 2½ |
| 4 | Node Diagramming: Activity-On-Node (AON) Precedence Diagramming | Ch. 2 (pp. 37-43) Ch. 4 (pp. 93-107) | 1 |
| 5 | Program Evaluation & Review Technique (PERT) | Ch. 9 (pp. 269-293) | 1 |
| 6 | Resource Leveling and Allocation | Ch. 7 (pp. 191-210) | 1 |
| 7 | Time-Cost Trade-Offs | Ch. 8 (pp. 237-249) | 1 |
| PROJECT ORGANIZING |  |  |  |
| 8 | Contractual and Organizational Approaches | Class Notes | 1 |
| PROJECT CONTROL |  |  |  |
| 9 | Time & Cost Control | Ch. 5 (pp. 133-163) Class Notes | 1 |
| 10 | Engineering Contracts | Class Notes | 1 |
| 11 | Financial Management | Class Notes | 1 |
| 12 | # Engineering Administration | Class Notes | 1½ |

Textbook:	Project Management with CPM, PERT, and Precedence Diagramming,

3rd Edition, by Moder J., Phillips, C., and Davis, E.