## Slide 1
Notes: <number>

## Slide 2: Event on A Mission?
Why Are We Doing This?

## Slide 3: Special Event Management BMO5401
LECTURE 2
More History
Conceptualising the Event
<number>
Notes: <number>

## Slide 4: From Last Week
Events as Connection
  To Others
  To Story, Myth, Religion
  To Place
Events as Celebration
  Identity
  Difference
  Life Itself
<number>

## Slide 5
<number>
Events as Strategy for
  Commercial Interests
  Community Interests
  State / National Interests
Events as a Means of
  Envisioning the Future
  Shaping the Future

## Slide 6: Events as Vehicles for Expression
Performers & Community
  Develop Performance Skills
  Build Social Capital
Place
  ‘This is Who We Are ‘
  ‘This is What We Want to be Known For’
<number>

## Slide 7: This Week’s Festival Moama Echuca Celtic Festival
<number>

## Slide 8: The Place – Echuca
Setting is a great place
  Historical Riverboat Town
  Tourist Facilities in close proximity
  Not too far from Melbourne
  Plenty of Accomodation
  Good Weather
<number>

## Slide 9: History of the Event
http://www.celticfestival.com.au/about-celtic-festival.html
Echuca Rotary –
  Tie into Echuca Steam Festival
  Lacked the Skills to draw the resources together
Riverboat owners came in
  Aggressive marketing of the region as a tourist destination
  Have the management skills to make it work
  Hunted down players / performers
  Made it happen in 2009 (2011 is year 3)
<number>

## Slide 10: Two Other Events
Gay Mardi Gras
  http://www.mardigras.org.au/partners/index.cfm
Melbourne Naked Bike Ride

## Slide 11
The first Naked Bike Ride was held in Zaragoza, Spain, in 2001.[3]
In 2003 Conrad Schmidt conceived the World Naked Bike Ride
Artists for Peace/Artists Against War (AFP/AAW)[4]
Collaborations with activist groups and individuals around the world. The first WNBR event in 2004 was a collaboration between the WNBR & Manifestación Ciclonudista in Spain
  Other organisations had similar events protesting oil dependency

## Slide 12
INITIAL MESSAGE
  Protesting against oil dependency and celebrating the power and individuality of the human body.
  2006, the message focused on cycling advocacy.
The 2004 WNBR saw events in 28 cities, in ten countries on four continents.[1]
By 2010, the WNBR had expanded to stage rides in 74 cities, in 17 countries, from the United States to United Kingdom and Hungary to Paraguay
Current Mission
  To deliver a vision of a cleaner, safer, body-positive world
  Dress Code: Bare as you Dare

## Slide 13: Sydney Gay Mardi Gras
24 June, 1978, 10pm – 1st GMG Parade
  Part of a Range of Events
    Contribution to International Gay Solidarity Celebrations (from Stonewall Riots)
    Protesting Attempts to stop gay rights supporters teaching in the US
  Several Hundred G&L’s and Supporters marched (small pa on a truck)
    Police Harrassment – confiscated the truck – arrested the driver

## Slide 14
This stirred up a crowd (1500) who joined the protest
  Police violently arrested 53 men and women
    Many beaten in the cells
    Followed by more arrests over the next months
Laws were changed
  Free to protest without a permit (civil rights)
1979 – 3000 people – no incidents
1980 – post parade party
1981 – change to March for weather

## Slide 15
1984 – 50 000 people
  6 000 at the after party
  Generating Profits
1986 - Positive media coverage
1989 – 200 000
1993 – 500 000
  Interstate and O/S visitors
  $38 M for the economy
1994 – Mainstream event (ABC TV)
2002 – Financial Problems (receivership)

## Slide 16
The Current Model
  New Mardi Gras (post 2002)
  100 DIFFERENT ARTS EVENTS
  70 000 person daytime picnic
  Post Parade Party
    Developed reputation for running great events
      These skills being one outcome of the event
The Critics?
  The best gay event in the world (Planetout)
  Top 10 costume parades itw (Conde Nast)
Mission
  ?????
  Celebrating Gay Pride

## Slide 17: This Lecture ...
Creating The Vision
<number>

## Slide 18: The Event Vision
Starting Point
  May change in laying the groundwork phase
  Once firmed up, plays part in moving towards aims
  Needs to be expressed simply and widely known
    Best form of control – shared goals
  Policies and procedures – support, but don’t replace vision
  Ask questions to test feasibility of vision
Notes: merrier and less stern than the Olympic Games – commonwealth games
to touch the soul of the nation and inspire the world by creating and delivering an extraordinary Olympic and Paralympic experience with lasting legacies. – Vancouver Olympics 2010

## Slide 19: Needs Assessment (The 5 W’s)
WHY?
What is the reason for this event
Why must the event be held?
WHO?
Who will benefit from this event?
Who do you want to attend?
WHEN?
When will the event be held?
Is the date and time changeable?
WHERE?
What is the best location / venue?
WHAT?
What resources are required to satisfy the needs identified
above?

## Slide 20: Relating The 5 “W’s”
WHY is the event being organised?:
  To provide an opportunity for the community to discover, develop and display their ideas, talents and culture
  To raise funds for charity etc.
  To provide profits for the organisers
  To educate the community or an industry group
  To develop the community’s identity
  As a celebration – e.g. Australia Day, ANZAC Day

## Slide 21: Relating The 5 “W’s”
WHO is the event being organised for:
It is critical to identify the community (Consumers and Other stakeholders) that you are developing the event for and dealing with, therefore you must identify such things as:
  Community of interest – business, sporting or cultural
  Community of belief – political, religious
  Specific ethnic community
  Specific gender or age group
  Geographic community – urban, rural, industrial or a combination
    Who will be involved?

## Slide 22: Relating The 5 “W’s”
WHEN will the event be held:
  Research weather patterns (especially for outside events)
  Establish “seasonality” of the event
    Note SMG and NBR are at the end of summer
  Research the timing of other events and activities in the area, will they clash, coincide or provide a “piggyback”
  Determine the duration of the event and the hours of operation

## Slide 23: Relating The 5 “W’s”
WHERE will the event be held:
  Multiple or Single venues
  Indoors or Outdoors
  If outdoors, is there a need to provide shelter from the elements, will you need to provide power, light and water?
  If streets and public spaces are to be used can permission be obtained and what is your role in developing alternative routes and controlling access etc.?
  What amenities are available at each potential venue, how do they help or hinder your event?
  Disability access?

## Slide 24: Relating The 5 “W’s”
WHAT will be included in the event:
  Music
  Stalls
  Personalities
  Activities
  Performances
  Sporting fixtures
  Amateur groups and organisations
  Contributions from local clubs, schools, hospitals, etc.

## Slide 25: Relating The 5 “W’s”
HOW will the Event be Funded:
  Donations
  Local, State or Federal funding
  Grants
  Business Sponsorship
  Mixture
    http://www.mardigras.org.au/partners/index.cfm

## Slide 26: Relating The 5 “W’s”
HOW will the event be Coordinated:
  Professional Event Manager / Management Team
  Community Volunteers
  Combination of both

## Slide 27: Strategic Event Planning
Depends on the type of event
  Its purpose, size, intended impact, for example
    Is it a Hallmark Event?
    For Profit / Not For Profit
    Community / Trade / Tourism / Cultural / Sport / Interest Group /
    Celebration
    One Off / Annual / Other
Research is paramount
Understand the Infrastructure

## Slide 28: Key Features of Thorough Event Planning
Has potential to:
  Minimise negative impacts
  Maximise economic and social returns to the community
It also is the vehicle for Generating Enthusiasm about the Event
  And Channeling that Enthusiasm into Concrete Plans and Action

## Slide 29: Events as Problems
Initiating an Event is a process of
  Creating a long list of problems and then ..
  Going about the business of Solving these
Strategic Planning Recognises the inevitiability of these problems
  And sets about identifying them
  Thinking about them
  And creating frameworks to solve them

## Slide 30: Key Features of Thorough Event Planning
Must be Holistic:
  Include any tourism requirements and initiatives
  Involve representation-all stakeholder groups
  Needs to carefully consider committee structures
  Large planning committees are unwieldy
  Small planning committees may be unrepresentative
  Every function must be clearly vested in some specific role
  Address the macro environment issues as well as the micro environment

## Slide 31: Goldblatt’s 5 Critical Stages in Managing Events
Research
Design
Planning
Coordination
Evaluation
  Goldblatt, J.J., (1997) Special Events: Best Practices in Modern Event Management, 2nd ed. Van Nostrand Reinhold, New York.

## Slide 32: Assess the Idea Is it Feasible?
What are the number of events held annually in the region?
What are the type of events held annually in the region?
Is the proposed event duplicating an existing event?
What are the peak and low points of the region’s annual event calendar?
What human resources will be available at the time the event is planned?
IS THERE A CLEARLY DEFINED OPPORTUNITY TO STAGE THE EVENT?

## Slide 33: What are the Key Objectives?
Determine the key objectives of the event:
  Raise funds
  Provide entertainment
  Start a new annual event
  Increase local or regional tourism
  Celebrate an important community event
  Expose product or services to a new market

## Slide 34: Establish the Event Date
Check event calendars to ensure no clash
Check location/venue availability
Similar events in other regions
Availability of local market – no clash with another major event or time e.g. school holidays
Probable weather conditions
Staging a tourism event in off-peak or peak tourism season

## Slide 35: Establishing Lead Time
Identify the required time to undertake the planning process:
  Small local events – 4 to 6 months
  Medium scale events – 6 to 12 months
  Large events – 12 to 18 months
Failure to allow adequate lead time is a common trap,
Can lead to things being missed
  Insufficient time to develop and implement marketing, develop sponsorship relationships

## Slide 36: Establishing lead time cont.
Work backwards from the event
Make realistic estimates for time needed to complete tasks
Aim to have all tasks completed at least 2 weeks prior to the event starting – allows a buffer for the things that WILL go pear shaped.
Monitor constantly!

## Slide 37: Pre-event Research and Development
Identify audience
Identifying goals & objectives
Identifying Strengths & Weaknesses
Identifying Opportunities & Threats
Designing the event

## Slide 38: Identifying Audience
Are you finding an audience for an event you have in mind OR
Designing an event for a particular audience?

## Slide 39: Identifying Goals & Objectives
Who are the stakeholders?
Why is the event being held?
When will the event be held?
Where will the event be held?
What is the event to achieve?

## Slide 40: The Vision and Mission
The Vision sets out the long term goal of the event (if it is an annual, or ongoing event)
The Mission sets out the specific task that the event will complete or achieve

## Slide 41: Evaluating the Concept
Three Screens
  The Marketing Screen
  The Operations Screen
  The Financial Screen

## Slide 42: Marketing Screen asks..
How will the target audience respond to the concept?

## Slide 43: Operations Screen asks..
What are the Skills and Resources needed to stage the Event?
Do we have access to these?

## Slide 44: Financial Screen asks..
Do we have enough money to run the event?

## Slide 45: Finally ….
Why are you holding the event?
  What is your aim?
  What will be the impact of your event on
    People?
    Place?
    Time?
    Law?
    .............................
A Clear compelling aim
  Often difficult to discover (or develop)

## Slide 46: Tutorial Questions
Discuss the value of setting a mission statement
2. Consider the four mission statements in the handout and discuss how they differ

## Slide 47: Tutorial questions
Discuss the differences between a functional organisational structure, a network structure and a matrix structure. Suggest different types of events which might use each structure
Choose a well-known event and conduct a SWOT analysis considering strengths, weaknesses, opportunities and threats that you consider are appropriate to that event.