## Slide 1
Notes: <number>

## Slide 3: Festival and Special Event Management 4e
Chapter 15
Logistics

## Slide 4: Learning objectives
Define logistics management and describe its evolution
Understand the concept of logistics management and its place in event management
Construct a logistics plan for the supply of customers, event products and event facilities
Use event logistics techniques and tools

## Slide 5: What are logistics?
Logistics assist the event manager to identify the elements of special event and festival operations
Logistics is an analysis tool to manage an aspect of an event by subdividing the work into categories
The value of a company’s products or services can be improved by efficient logistics
In Australia, logistics is more important because of our special conditions

## Slide 7
Logistikos (Greek)
  Skilled in Calculating
  Used by the Romans for the administration of their armies
In Modern times
  Developed by Business post war
  Integrated Logistics Management
Logistics
  Planning, implementing and control of the flow and storage of products and related information from production to consumption – as per consumer rqt’s

## Slide 8: Event Logistics
More like Military Logistics than Business Logistics
  Event Logistics includes efficient supply of
    Customer to the product
    Facilities to and from the site
  Like getting the troops to battle, with the necessary supplies to engage in battle
  Touring Event has the same problems
    Big Day Out, Falls Festival

## Slide 9: The elements of event logistics

## Slide 10: The elements of event logistics
Supply
  Customer – Product – Facilities
Transport
  Major Cost in Australia
Linking all the parts
  Linking Marketing with Logistics (IKEA)
Flow control
  Flow of Products, Services and Customers during the event
Information networks
  Efficient flow of information on site

## Slide 11: Promotion for IKEA in Jeddah, Saudia Arabia 2004
Big pre-opening campaign
  SR500 (AU $165) for the 1st 50 customers, and SR100 to the next 200
  Opened the door at 10am
  Thousands of people stampeded to claim the cash
  3 people killed, 16 injured

## Slide 12: Supply of customer
Links with marketing and promotion
Ticketing
  Wrist bands, net purchase, phone bar codes
Queuing
  Disney
Customer transport
  Dump v Trickle
Transport

## Slide 13
Disney's Unique Queues
Probably the most disliked thing about Disneyland is the queuing for rides. Disneyland is famous for it! While queuing at Disneyland is not the reason anyone visit's Disneyland they have mastered the art and do it better than anyone.
Themed & decorated Some attractions line up areas are so well decorated that they become part of the attractions and are genuinely exciting to stand it. All designed to make your wait les tedious
'Wiggly' lines By curving the line up area around multiple corners makes it psychologically shorter. You can't see the end of the line meaning you don't know how far you really have to travel and by the time you figure it out you're there! Sound's mean, but it works!
Fast moving Lines move quickly due to their well organised dispatch method in the loading area of each attraction. This means you don't stand in the one spot without moving forward usually for any more than 20 seconds. Unlike a large grocery store line.

## Slide 14: Application for Event Approval Road Transp’t Authority NSW

## Slide 15: Supply of product (Artists) product portfolio
Transport
  Local and overseas
  Shuttle Bus v Limo
  Meet and Greet at the Airport
Accommodation
  Separate from the Audience ??
Artist’s needs on site
  Anticipating what the artists / speakers require and expect to be provided
  Crucial in getting the best from them

## Slide 16: Supply of facilities
The storage of consumables and equipment
Sourcing the facilities
  Availability
  Cost
  Lead times

## Slide 17: Checklists for Suppliers

## Slide 18: On-site logistics
Flow

## Slide 19: On-site logistics
Communication
Two-way radios
Mobile phones and text messages
Signage
Runners / news sheets
Loud hailer / sound system
Flags / visual and audio cues
CCTV and webcams
Short-range FM radios
WiFi and Bluetooth
Bulletin boards

## Slide 20: Also
Signage critical for large events
  Detailed Plan
  Signs at Key Decision Points and Danger Spots
  Types of Signs
    Sponsor – Directional – Statutory – Operational – Facility – Sponsor
  Sign Literacy of the Audience
    What signs are they use to reading?

## Slide 21: On-site logistics
Amenities and solid waste management
http://www.deniutemuster.com.au/the-site/site-map

## Slide 23
http://www.melbflowershow.com.au/Ticketing

## Slide 24: On-site Logistics
Consumables – food and beverage
Storage and distribution
Sale of alcoholic beverages
Pre-sale tickets for purchase of food and drink
Catering for sponsors and VIPs
Food Standards Code & HACCP

## Slide 25: On-site Logistics
VIP and media requirements
Media coverage of events can disrupt live performances
  Use of separate microphones and cameras
  Short timelines
However, because of the positive benefits of media coverage, media logistics can take precedence
VIPs can require special security arrangements
  Eg Royals or President to an Exhibition

## Slide 26: On-site logistics
Emergency procedures
Local councils can shut down an event that does not comply with emergency regulations
Emergency response plans
  Can effect the design of the site

## Slide 27: Shutdown
Proportional to size of event
Event project plan
  Work breakdown structure
  Task/responsibility list
  Schedule with a critical path
Crowd management
Security
Shutdown checklist
Acquitting large event capital assets

## Slide 28: Techniques of logistics management
The event logistics manager

## Slide 29
POSITION | GENERAL ROLE | INFORMATION SENT TO LOGISTICS MANAGER
Artistic Director | Selection of and negotiation with artists | Travel accommodation, staging and equipment requirements
Staging Manager | Selection of and negotiation with subcontractors | Sound, lights and backstage requirements and programming times
Finance Director | Overseeing of budgets and contracts | How and when funds will be approved and released and the payment schedule
Volunteers Coordinator | Recruitment and management of volunteers | Volunteers selected and their requirements (eg free parking)
Promotions Manager | Promotion during the event | Requirements of the media and VIPs
Traders Manager | Selection of suitable traders | Requirements of the traders (positioning, theming, water and power)

## Slide 30: Techniques of logistics management
Site or venue map
A necessary communication tool for the logistics manager
The three features of maps:
  Scale
  Projection
  The key (showing the symbols used)

## Slide 31: Negotiation and assessment
One-off events
Events as a dynamic system
  Reassessing decisions
Gap Analysis

## Slide 32: Control of events logistics
Monitoring the plan
Identification of milestones
Gantt chart
The aim of the logistics manager is to create a plan to enable the logistics to flow without the need for active control
  The use of qualified subcontractors is the only way in which to make this happen!

## Slide 33: Evaluation of logistics
Simply: Was the event a success?
May need more detailed analysis
  For stakeholders, eg sponsors, committee
Easy to complete if
  Logistic objectives are measurable
  SMART objectives / goals
Quantitative
  Comparison of performance against benchmarks
Qualitative
  Discussion with stakeholders
Logistics audit
  Including whether audience expectations were met

## Slide 34: Logistics Critical .......
Australian Dep’t of Foreign Affairs and Trade (DFAT)
  Launch a multidimensional promotion of Australia in country ......
  Why will logistics be such a critical element of the promotion / exhibition?
    What would be Some of the Specific elements of the Logistics for the Exhibition?
    What are some KPI’s that could be used to evaluate the Logistics

## Slide 35: The logistics or operations plan
For a large event, this would contain:
  A general contact list
  A site map
  Schedules, including timelines and bar charts
  The emergency plan
  Subcontractor details, including all time constraints
  On-site contacts, including security and volunteers
  Evaluation sheets (sample questionnaires)