## Slide 1
Notes: <number>

## Slide 2: Festival and Special Event Management 4e
Chapter 18
Risk Management
Notes: <number>

## Slide 3: Learning Objectives
Define risk and its relationship to the management of festivals and special events
Understand the context of risk
Use the tools of risk identification and identify the risks specific to events
Understand the latest methodologies of risk management
Understand the core concepts of occupational health and safety

## Slide 4: Risk management process
Every part of event management has potential risks
  Administration
  Marketing and public relations
  Health and safety
  Crowd management
  Security
  Transport
Notes: <number>

## Slide 5: Risk management process

## Slide 6: Risk management process
Understanding context
Type of event
Management structure
Stakeholder analysis
General risk environment

## Slide 7: Risk management process
Analysis and evaluation of the risk
The dimensions of risk
  The likelihood of them occuring
    High or Low
  The consequences if they do occur
    High or Low

## Slide 8: Risk management process
Control
After risk evaluation, the event management team needs to create mechanisms to control potential problems
The decisions include:
  Changing the likelihood that a problem will occur
  Changing the consequence if the problem does occur
  Accepting the risk
  Transferring the risk to another party

## Slide 9: Risk management process
Mitigating actions
Unattended packages
  Who will respond?
  Are dogs available who are trained to identify explosives?
  Will the area be evacuated?
Risk communication
  Understanding the terminology of risk
  Open communication channels
  Informal methods of communication

## Slide 10: Risk management process
Further risk management methodologies
Principle of safe design
  Person with control
  Product lifecycle
  Systematic risk management
  Safe design knowledge and capability
  Information transfer
Hazard analysis and critical control points

## Slide 11: Risk management process
Further risk management
methodologies

## Slide 12: Risk management process
Specific event risks
Volunteers
Crowd management
Alcohol and drugs
Communication
Environment
Emergency
Review
Evaluation the successes and failures of the risk control strategy is essential for future events

## Slide 13: Risk Management Processes
See
Minton Ellis Risk Management Booklet in Lecture Notes

## Slide 14: OHS and events
Consultation
Differs between states
The event team must consult with the event stakeholders on event health and safety
It is mandatory for the event team to understand their state’s legislation

## Slide 15: Summary
There are many Legal Aspects involved in presenting Live Performances
They have little of the Excitement associated with putting on the Event
Failure to Address these Matters can be a disaster
  Financial and Personal
It is important to
  Know About and Address the Legal Side of the Business