## Slide 1
ARCH 435 PROJECT MANAGEMENT
Lecture 7: Cash-Flow

## Slide 2
In order to make a workable project plan, the resources needed for the project and their availability must be checked.
Money is one of the most important resources.
Cash flow forecasting is required to determine whether or not the funds to execute the plan are available.
Cash flow forecasting is the forecasting of both cash in and cash out of the project.
Cash Flow Forecasting

## Slide 3
Engineering project contracts typically provide that the owner shall make progress payments of the contract amount to the prime contractor as the work progresses.
Cash in = Cash receipt = income
Principal components of cash in
Value of work actually performed in the field. The total value of work done to date is obtained in different ways, depending on the type of contract, and
Material stored on the site, but not yet incorporated into work, as well as any prefabrication or pre assembly work that the contractor may have done at some location other than the job site.
A step curve is used to represent contract cash income.
Cash in

## Slide 4
An income is the actual receipt of revenue. It takes into account the delays between incurring a commitment and making a money transaction.
Cash in (Receipt or Income) and Revenue
Contract revenue and income curves

## Slide 5
  The quantities of work done on unit-price contracts are determined by actual field measurement of the bid items put into place.
  The total quantity accomplished to date on each bid item is multiplied by its corresponding contract unit price.
  All of the bid items are totaled and the value of materials stored on the site as well as any prefabrication or pre assembly work that the contractor may have done at some location other than the job site is then added.
  The prescribed retainage is subtracted from this total.
  The resulting figure represents the entire amount due the contractor for his work to date. The sum of all prior progress payments that have already been paid is then subtracted, this yielding the net amount of money payable to the contractor for his work that month.
Payment Request for Unit Price Contract

## Slide 6
  Under lump sum contract the project is divided for payment purposes into relatively few work classifications, most of which are extensive and often extend over considerable portions of the construction period. Contracts progress is customarily measured in terms of estimated percentages of completion of work classifications (major job components).
  The contractor estimates the percentage completed and in place.
  The total value of each work classification is multiplied by its percent completion.
  To the total of completed work is added the value of all materials stored on the site. From this total is subtracted the retainage. This gives the total amount of money due the contractor up to the date of the pay request.
  Form this is subtracted the amount of progress payments already made. The resulting figure gives the net amount now payable to the contractor.
Payment Request for Lump Sum Contract

## Slide 7
Advanced payment
Progress payment
Materials stored on the site
Final Payment
Retention
…………
Contract Provision that Impact Cash in

## Slide 8
A prescribed percentage of each progress payment is usually retained by the owner in accordance with the terms of the contract.
The retainage may be held by the owner until the work receives final certification by the A/E, the owner accepts the project.
Final payment is then made to the contractor, including the accumulated retainage.
Retainage = Retention

## Slide 9
After the work has been finalized and all deficiencies remedied, the owner makes formal written acceptance of the project and the contractor presents his application for final payment.
Under a lump-sum form of contract, the final payment is the final contract price less the total of all previous payment installments made.
With a unit-price contract, the final total quantities of all payment items are measured and the exact final contract price is determined. Final payment is again equal to the contract price less the sum of all progress payments previously made.
In all cases, final payment by the owner includes all retainage that has been held by him.
Final Payment

## Slide 10
Engineering projects can make substantial demands on a contractor's cash.
Cash out = payment of costs = expense
Principal components of cash out
“Up-front" costs = initial expenses = start-up costs are costs necessary to start the project such as costs of moving in workers and equipment; erecting field offices, storage sheds, fences, job layout, installation of temporary electricity, water, telephone, sanitary, and other services, bonds, permits and project insurance.
Payment of direct job costs. These include costs associated with payrolls, materials, equipment, and subcontractor payments.
Payments for filed overhead expense and tax.
An S-curve (a smooth curve) is used to represent contract cash out.
Cash out

## Slide 11
An expense is the actual payment of costs. It takes into account the delays between incurring a commitment and making a money transaction.
Cash out (Payment of Cost = Expense) and Cost
Contract cost and expense curves

## Slide 12
The contractor's expense on a project will typically exceed his monthly progress payment income over an appreciable part of the construction period.
The cash shortage on the project must be made up from the contractor's working capital, or money must be borrowed to provide the necessary operating funds.
"Cash flow" refers to a contractor's income and outgo of cash.
Cash Flow

## Slide 13
The net cash flow is the difference between cash out and income at any point in time. A negative net flow means expense are exceeding income, a normal situation on even a highly profitable project during the greater part of its duration.
A determination of the future rates of cash outs and cash income, together with their combined effect on the project cash balance, is called a "cash flow forecast".
Net Cash Flow

## Slide 14
Having determined the contract cumulative income and expense curves, one can combine them on one graph to represent the contract cumulative cash flow curves.
Contract Cash Flow Curves

## Slide 15
The difference between contract cumulative income and expense curves can be drawn to represent the contract cumulative net cash flow.
Contract Net Cash Flow

## Slide 16
Front end rate loading: earlier items in bill of quantities carry a higher mark-up than later items. This reduces negative cash flows in contract early stages.
Reduction of delays in receiving revenue.
Adjustment of work schedule to late start timing.
Coinciding the timing of delivery of large materials orders with the submittal of the contractor's monthly pay estimate.
Delay in paying labor, plant hirers, materials suppliers, and subcontractors. This would reduce negative cash flows but undermine commercial confidence in the company.
Increasing the mark-up and reducing the retentions.
Increasing advance payment.
Achievement of maximum production in the field.
Quick settlement or claims.
Factors That Minimize Contractor's Negative Cash Flow