**Assignment #2**

The below table described a project’s schedule:

|  |  |  |
| --- | --- | --- |
| Estimated time of the activity in weeks | Immediate predecessor | Activity |
| 5 | \_\_ | A |
| 6 | A | B |
| 3 | A | C |
| 7 | B and C | D |
| 8 | D | E |

Q.1) Draw the project network.

Q.2) What is the critical path?

Q.3) What is the expected projection duration?

**Note:** The deadline for this assignment is **Wednesday, December 7, 2016**. Late submission of the assignment means getting less marks for the assignment.