## Slide 1: Software Project Sizing and Cost Estimation

## Slide 2: A Good Manager Measures
measurement
What do we
use as a
basis?
• size?
• function?
project metrics
process metrics
process
product
product metrics

## Slide 3: Why Do We Measure? SWE 22, 22.1
To characterize, in an effort to gain an understanding of process, products, resources, and environment.
To establish baselines for comparisons with future assessments
To evaluate status with respect to plan
To predict, by gaining understanding of relationships among processes and products, and building models of these relationships
To improve, by identifying roadblocks, root causes, inefficiencies, and other opportunities for improving product quality and process performance

## Slide 4: Project Metrics and Software Project Manager
Project metrics help a software project manager in
assessing the status of an ongoing project
tracking potential risks
uncovering problem areas before they go “critical,”
adjusting work flow or tasks,
evaluating the project team’s ability to control quality of software work products.

## Slide 5: Software Process Improvement
SPI
Process model
Improvement goals
Process metrics
Process improvement
recommendations

## Slide 6: Software Process Improvement
Factors that influence software quality and organizational performance
  Skills and motivation of people
  Complexity of the product
  Technology
  Development environments
  Business conditions
  Customer characteristics

## Slide 7: Process Measurement
We measure the efficacy of a software process indirectly.
  That is, we derive a set of metrics based on the outcomes that can be derived from the process.
  Outcomes include
    measures of errors uncovered before release of the software
    defects delivered to and reported by end-users
    work products delivered (productivity)
    human effort expended
    calendar time expended
    schedule conformance
    other measures.
We also derive process metrics by measuring the characteristics of specific software engineering tasks.

## Slide 8: Process Metrics
Quality-related
  focus on quality of work products and deliverables
Productivity-related
  Production of work-products related to effort expended
Statistical SQA data
  error categorization & analysis
Defect removal efficiency
  propagation of errors from process activity to activity
Reuse data
  The number of components produced and their degree of reusability

## Slide 9: Process Metrics
Private process metrics,
  Private to the software project team but public to all team members
  defects reported for major software functions
  Errors found during formal technical reviews
  Line s of code or function points per component or function
Public process metrics
  Originally was private to individuals and teams
  Project level defect rates (not attributed to an individual)
  Effort
  Calendar times, and related data.

## Slide 10: Process Metrics Guidelines
Use common sense and organizational sensitivity when interpreting metrics data.
Provide regular feedback to the individuals and teams who collect measures and metrics.
Don’t use metrics to appraise individuals.
Work with practitioners and teams to set clear goals and metrics that will be used to achieve them.
Never use metrics to threaten individuals or teams.
Metrics data that indicate a problem area should not be considered “negative.” These data are merely an indicator for process improvement.
Don’t obsess on a single metric to the exclusion of other important metrics.

## Slide 11: Project Metrics
Software project metrics are tactical, while software process metrics are strategic
They are used by a project manager and a software team to adapt project workflow and technical activities
Metrics collected from past projects are used as a basis for estimating effort and time of current software work
As a project proceeds, measures of effort and time are compared to original estimates
These data are used to monitor and control progress
Project metrics can be consolidated to create process metrics that are public to the software organization as a whole

## Slide 12: Software Measurements
Direct measures of
  Software process, e.g., cost and effort applied
  Product, e.g., lines of codes (LOC) produced, execution speed, and defects reported over some period of time
Indirect measures of the product that include functionality, quality, complexity, efficiency, reliability, maintainability, and more.

## Slide 13: Software Measurements
Size-Oriented Metrics
Function-Oriented Metrics

## Slide 14: Software Measurements
Size-Oriented Metrics
 | Project 1 | Project 2
Lines of Code (LOC) | 12,100 | 27,200
Person-Months | 24 | 62
Cost | $168,000 | $440,000
Pages of Documentation | 365 | 1224
Errors (before release) | 134 | 321
Defects (after release) | 29 | 86
People Worked on The Project | 3 | 5

## Slide 15: Size-Oriented Metrics:
Normalization:
Errors per KLOC
Defects per KLOC
$ per KLOC
Pages of Documentation per KLOC
Other measures:
Errors per person-month
KLOC per person-month
$ per page of documentation

## Slide 16: Function-Oriented Metrics
Function Point (FP)
Computation of FP is based on the software information domain and complexity
FP is programming language independent
Based on data that are to be known early in the evaluation of the project
Requires some skills
Subjective rather than objective

## Slide 17: Comparing LOC and FP
Representative values developed by QSM

## Slide 18: Project Planning Task Set-I
Establish project scope
Determine feasibility
Analyze risks
Define required resources
  Determine require human resources
  Define reusable software resources
  Identify environmental resources

## Slide 19: Project Planning Task Set-II
Estimate cost and effort
  Decompose the problem
  Develop two or more estimates using size, function points, process tasks or use-cases
  Reconcile the estimates
Develop a project schedule
    Establish a meaningful task set
    Define a task network
    Use scheduling tools to develop a timeline chart
    Define schedule tracking mechanisms

## Slide 20: Estimation SWE 23.1
Estimation is as much art as it is science
Estimation of resources, cost, and schedule for a software engineering effort requires
  experience
  access to good historical information (metrics)
  the courage to commit to quantitative predictions when qualitative information is all that exists
Estimation carries inherent risk and this risk leads to uncertainty
Estimation risk is measured by the degree of uncertainty in the quantitative estimates established for resources, cost, and schedule.

## Slide 21: Project Estimation SWE 23.5
Software cost and effort estimation will never be an exact science
A large cost estimation error can make a difference between profit and loss.
To achieve reliable cost and effort estimates, a number of options
are considered:
Delay estimates until late in the project
Base estimates on similar projects that has been completed
Use relatively simple decomposition techniques to generate cost and effort estimates
Use one or more empirical models for software cost and effort estimates

## Slide 22: Estimation Accuracy SWE 23.6
Predicated on …
  the degree to which the planner has properly estimated the size of the product to be built
  the ability to translate the size estimate into human effort, calendar time, and dollars (a function of the availability of reliable software metrics from past projects)
  the degree to which the project plan reflects the abilities of the software team
  the stability of product requirements and the environment that supports the software engineering effort.

## Slide 23: Functional Decomposition
functional
decomposition
Statement
of
Scope
Perform a Grammatical “parse”

## Slide 24: Conventional Methods: LOC/FP Approach
compute LOC/FP using estimates of information domain values
use historical data to build estimates for the project

## Slide 25: Empirical Estimation Models: COCOMO-II SWE 23.7
COCOMO II ( COnstructive COst MOdel) is actually a hierarchy of estimation models that address the following areas:
    Application composition model. Used during the early stages of software engineering, when prototyping of user interfaces, consideration of software and system interaction, assessment of performance, and evaluation of technology maturity are paramount.
    Early design stage model. Used once requirements have been stabilized and basic software architecture has been established.
    Post-architecture-stage model. Used during the construction of the software.

## Slide 26: COCOMO-II
COCOMO-II application composition model uses object points; counts of the number of
  Screens
  Reports
  Components likely required to build the application
  Screens, reports and components are weighted according to
Object type | Complexity Weight |  | 
 | Simple | Medium | Difficult
Screen | 1 | 2 | 3
Report | 2 | 5 | 8
3GL component |  |  | 10

## Slide 27: COCOMO-II
Once complexities are determined,
Object Point Count = Original number of object instances
X Weighting factor
NOP = (Object points) *[(100-% reuse)/100]
PROD = NOP / Person-Month
Estimated Effort = NOP / PROD

## Slide 28: The Software Equation
A dynamic multivariable model
E = [LOC x B0.333/P]3 x (1/t4)
where
E = effort in person-months or person-years
t = project duration in months or years
B = “special skills factor”
P = “productivity parameter”,
(typical value 2000 for real-time software, 28000 for business applications)