## Slide 1
<number>
Chapter 3:
Project Management Chapter 22 & 23 in Software Engineering Book

## Slide 2
<number>
Overview
Why do we need software project management?
Project management activities.
Team formation.
Project planning and scheduling.
Risk management.
Cost estimation.

## Slide 3
<number>
By the end of this chapter, you will..
Know the principal tasks of software managers.
Understand the need for planning in all software projects.
Understand how graphical presentations can be used for project schedules.
Understand the risk management process in software projects.

## Slide 4
<number>
Good management guarantees project success.
Do you agree?

## Slide 5
<number>
Bad management results in project failure.
Do you agree?

## Slide 6
<number>
Why do we need software project management?
Software engineering is subject to organisational budget and schedule constraints.
Project managers ensure that software meets these constraints.
How is software engineering different?
  Intangible products.
  Lack of standard software processes.
  One-off projects.

## Slide 7
<number>
What does a project manager do?
List the management tasks that you can think of with your team.

## Slide 8
<number>
Project Management Activities
Proposal writing, report writing and presentations.
Team formation (selecting people to work on projects).
Project planning and scheduling.
Project cost estimation.
Project monitoring and reviews (Quality assurance).

## Slide 9
<number>
Team Formation
Objective: having the right people in the right roles.
Challenges in forming the ideal team:
  Budget may not allow for the use of highly-paid staff;
  Staff with the appropriate experience may not be available;
  An organisation may wish to develop employee skills on a software project.
Project managers have to work within these constraints especially when there are shortages of trained staff.

## Slide 10
<number>
Project Planning
Probably the most time-consuming project management activity.
Continuous activity  Plans must be regularly revised as new information becomes available.
Objective: determine
  Resources available.
  Work breakdown.
  Schedule.

## Slide 11
<number>
Project Planning
Type of Project Plan | Description
Quality Plan | Describes the quality procedures and standards that will be used in a project.
Validation Plan | Describes the approach, resources and schedule used for system validation.
Configuration Management Plan | Describes the configuration management procedures and structures to be used.
Maintenance Plan | Predicts the maintenance requirements of the system, maintenance costs and effort required.
Staff Development Plan | Describes how the skills and experience of the project team members will be developed.

## Slide 12
<number>
Project Planning
Project Plan Structure:
  Introduction.
  Project organisation.
  Risk analysis.
  Hardware and software resource requirements.
  Work breakdown.
  Project schedule.
  Monitoring and reporting mechanisms.

## Slide 13
<number>
Risk Management
Risk identification: what can go wrong.
Analyse risks: determine the likelihood that of occurrences and consequences.
  Prioritise risks by probability and impact.
Develop a risk plan.
Monitor to manage risks with high probability and high impact.
Risk Identification
Risk
Analysis
Risk
Planning
Risk
Monitoring
List of potential risks
Prioritised risk list
Risk avoidance & contingency plans
Risk assessment

## Slide 14
<number>
Risk Management Process: 1. Risk Identification
Risk type | Possible risks
Technology | The database used in the system cannot process as many transactions per second as expected. Software components that should be reused contain defects that limit their functionality.
People | It is impossible to recruit staff with the skills required. Key staff are ill and unavailable at critical times. Required training for staff is not available.
Organisational | The organisation is restructured so that different management are responsible for the project. Organisational financial problems force reductions in the project budget.
Tools | The code generated by CASE tools is inefficient. CASE tools cannot be integrated.
Requirements | Changes to requirements that require major design rework are proposed. Customers fail to understand the impact of requirements changes.
Estimation | The time required to develop the software is underestimated. The rate of defect repair is underestimated. The size of the software is underestimated.

## Slide 15
<number>
Risk Management Process: 2. Risk Analysis and Prioritisation
Risk | Probability | Effects
Organisational financial problems force reductions in the project budget. | Low | Catastrophic
It is impossible to recruit staff with the skills required for the project. | High | Catastrophic
Key staff are ill at critical times in the project. | Moderate | Serious
Software components that should be reused contain defects which limit their functionality. | Moderate | Serious
Changes to requirements that require major design rework are proposed. | Moderate | Serious
The organisation is restructured so that different management are responsible for the project. | High | Serious

## Slide 16
<number>
Risk Management Process: 3. Risk Planning
Develop strategies for managing risks:
  Avoidance strategies: The probability that the risk will arise is reduced;
  Minimisation strategies: The impact of the risk on the project or product will be reduced;
  Contingency plans: plans to deal with risks if they happen.
Risk | Strategy | Type of strategy?
Staff illness | Reorganise team to increase overlap of work  people understand each other’s jobs. | Minimisation strategy
Defective components | Replace potentially defective components with bought-in components of known reliability. | Avoidance strategy
Organisational financial problems | Prepare a briefing document for senior management demonstrating how the project is making key contributions to the goals of the business. | Contingency plan

## Slide 17
<number>
Risk Management Process: 4. Risk Monitoring
Regularly assessing each of the identified risks:
  Are the risks becoming more or less probable?
  Have any changes occurred to the effects of the risks on the project?
Risk type | Potential indicators
Technology | Late delivery of hardware or support software, many reported technology problems.
People | Poor staff morale, poor relationships amongst team member, job availability.
Organisational | Organisational gossip, lack of action by senior management
Tools | Reluctance by team members to use tools, complaints about CASE tools, demands for higher-powered workstations.
Requirements | Many requirements change requests, customer complaints.
Estimation | Failure to meet agreed schedule, failure to clear reported defects.

## Slide 18
<number>
Work Breakdown
Activities in a project should be organised to produce tangible outputs for management to judge progress.
Milestones are the end-point of a process activity.
Deliverables are project results delivered to customers.
To establish milestones the software process must be broken down into basic activities with associated outputs.

## Slide 19
<number>
Milestones and Deliverables
Deliverables

## Slide 20
<number>
Project Scheduling
Project scheduling process:
Split project into tasks. For each task, estimate time & resources.
Organise tasks concurrently to make optimal use of workforce.
Minimise task dependencies.
Depends on project manager’s intuition and experience.

## Slide 21
<number>
Bar Charts and Activity Networks
Graphical notations used to illustrate the project schedule.
Show project breakdown into tasks. Tasks should not be too small. They should take about a week or two.
Activity charts show task dependencies and the critical path.
Bar charts show schedule against calendar time.

## Slide 22
<number>
The Activity of Building a House
Start
Build fence
Build Frame
Design landscaping
Walls & Interiors
Finish
Paint

## Slide 23
<number>
Activity Networks
Start
Build fence
Build Frame
Design landscaping
Walls & Interiors
Finish
Paint
Frame
Fence
Construction Complete
Activity
Milestone

## Slide 24
<number>
Activity Networks
Start
Build fence
Build Frame
Design landscaping
Walls & Interiors
Finish
Paint
Frame
Fence
Construction Complete
100 days
100 days
10 days
10 days
30 days
Critical Path  Longest path
Activity
Milestone

## Slide 25
<number>
Activity Networks
Start
T3:
Build fence
T1:
Build Frame
T4:
Design landscaping
T2:
Walls & Interiors
Finish
T5:
Paint
M1
Frame
M2
Fence
M3: Construction Complete
100 days
100 days
10 days
10 days
30 days
Critical Path  Longest path
Activity
Milestone
Activity | Duration | Dependencies
T1: Build Frame | 100 days | 
T2: Walls & Interiors | 100 days | T1 (M1: Frame)
T3: Build Fence | 10 days | 
T4: Design Landscaping | 30 days | T3 (M2: Fence)
T5: Paint | 10 | T2,T4 (M3: Construction Complete)

## Slide 26
<number>
Task Duration & Dependencies
Activity | Duration (days) | Dependencies
T1 | 8 | 
T2 | 15 | 
T3 | 15 | T1 (M1)
T4 | 10 | 
T5 | 10 | T2, T4 (M2)
T6 | 5 | T1, T2 (M3)
T7 | 20 | T1 (M1)
T8 | 25 | T4 (M5)
T9 | 15 | T3, T6 (M4)
T10 | 15 | T5, T7 (M7)
T11 | 7 | T9 (M6)
T12 | 10 | T11 (M8)

## Slide 27
<number>
Activity Network

## Slide 28
<number>
Activity Bar Chart

## Slide 29
<number>
Activity Network
The Quality Handbook: Activity Networks.
http://syque.com/quality_tools/toolbook/Activity/activity.htm

## Slide 30
<number>
Activity Network

## Slide 31
<number>
Project Cost Estimation
What are the parameters involved in computing the total cost of a software development project?
  Hardware and software costs including maintenance.
  Travel and training costs.
  Effort costs (paying software engineers).
For most projects, the dominant cost in software development is effort cost.

## Slide 32
<number>
Project Cost Estimation
Algorithmic cost modelling.
Expert judgment.
Estimation by analogy.
Parkinson’s law.
Pricing to win.
For large projects it is advisable to use several cost estimation techniques and compare the results.

## Slide 33
<number>
These models use one of the following techniques
Experience-based techniques The estimate of future effort requirements is based on the manager’s experience of past projects and the application domain. Essentially, the manager makes an informed judgment of what the effort requirements are likely to be.
Algorithmic cost modeling In this approach, a formulaic approach is used to compute the project effort based on estimates of product attributes, such as size, and process characteristics, such as experience of staff involved.
Project Cost Estimation

## Slide 34
<number>
Estimation Uncertainty

## Slide 35
<number>
People are an organisation’s most important assets.
The tasks of a manager are essentially people-oriented. Unless there is some understanding of people, management will be unsuccessful.
Poor people management is an important contributor to project failure.
Managing people

## Slide 36
<number>
Consistency
  Team members should all be treated in a comparable way without favourites or discrimination.
Respect
  Different team members have different skills and these differences should be respected.
Inclusion
  Involve all team members and make sure that people’s views are considered.
Honesty
  You should always be honest about what is going well and what is going badly in a project.
People management factors

## Slide 37
<number>
An important role of a manager is to motivate the people working on a project.
Motivation means organizing the work and the working environment to encourage people to work effectively.
  If people are not motivated, they will not be interested in the work they are doing. They will work slowly, be more likely to make mistakes and will not contribute to the broader goals of the team or the organization.
Motivation is a complex issue but it appears that their are different types of motivation based on:
  Basic needs (e.g. food, sleep, etc.);
  Personal needs (e.g. respect, self-esteem);
  Social needs (e.g. to be accepted as part of a group).
Motivating people

## Slide 38
<number>
Human needs hierarchy

## Slide 39
<number>
Need satisfaction
In software development groups, basic physiological and safety needs are not an issue.
Social
  Provide communal facilities;
  Allow informal communications e.g. via social networking
Esteem
  Recognition of achievements;
  Appropriate rewards.
Self-realization
  Training - people want to learn more;
  Responsibility.

## Slide 40
<number>
Teamwork
Most software engineering is a group activity
  The development schedule for most non-trivial software projects is such that they cannot be completed by one person working alone.
A good group is cohesive and has a team spirit. The people involved are motivated by the success of the group as well as by their own personal goals.
Group interaction is a key determinant of group performance.
Flexibility in group composition is limited
  Managers must do the best they can with available people.

## Slide 41
<number>
Group cohesiveness
In a cohesive group, members consider the group to be more important than any individual in it.
The advantages of a cohesive group are:
  Group quality standards can be developed by the group members.
  Team members learn from each other and get to know each other’s work; Inhibitions caused by ignorance are reduced.
  Knowledge is shared. Continuity can be maintained if a group member leaves.
  Refactoring and continual improvement is encouraged. Group members work collectively to deliver high quality results and fix problems, irrespective of the individuals who originally created the design or program.

## Slide 42
<number>
The effectiveness of a team
The people in the group
  You need a mix of people in a project group as software development involves diverse activities such as negotiating with clients, programming, testing and documentation.
The group organization
  A group should be organized so that individuals can contribute to the best of their abilities and tasks can be completed as expected.
Technical and managerial communications
  Good communications between group members, and between the software engineering team and other project stakeholders, is essential.

## Slide 43
<number>
Selecting group members
A manager or team leader’s job is to create a cohesive group and organize their group so that they can work together effectively.
This involves creating a group with the right balance of technical skills and personalities, and organizing that group so that the members work together effectively.

## Slide 44
<number>
Group communications
Good communications are essential for effective group working.
Information must be exchanged on the status of work, design decisions and changes to previous decisions.
Good communications also strengthens group cohesion as it promotes understanding.

## Slide 45
<number>
Group communications
Group size
  The larger the group, the harder it is for people to communicate with other group members.
Group structure
  Communication is better in informally structured groups than in hierarchically structured groups.
Group composition
  Communication is better when there are different personality types in a group and when groups are mixed rather than single sex.
The physical work environment
  Good workplace organisation can help encourage communications.

## Slide 46
<number>
Key points
People are motivated by interaction with other people, the recognition of management and their peers, and by being given opportunities for personal development.
Software development groups should be fairly small and cohesive. The key factors that influence the effectiveness of a group are the people in that group, the way that it is organized and the communication between group members.
Communications within a group are influenced by factors such as the status of group members, the size of the group, the gender composition of the group, personalities and available communication channels.