## Slide 1: Modern Systems Analysis and Design Third Edition
Chapter 3
Managing the Information Systems Project
3.1
Notes: <number>

## Slide 2: Managing the Information Systems Project
Focus of project management
  To ensure that information system projects meet customer expectations
    Delivered in a timely manner
    Meet time constraints and requirements
3.<number>
Project Manager
  is a Systems Analyst responsible for Project:
    Initiation
    Planning
    Execution
    Closing down
Notes: <number>

## Slide 3: Managing the Information Systems Project
Project Manager
  skills include:
    Management
    Leadership
    Technical
    Problem solving
    Conflict management
    Customer relations
    Team management
    Risk and change management
Notes: <number>

## Slide 4: Project Management Process
Project
  Planned undertaking of related activities to reach an objective that has a beginning and an end
Deliverable
  An end product in a phase of the SDLC
Feasibility Study
  Determines if the information system makes sense for the organization from an economic and operational standpoint
  The study takes place before the system is constructed
Project Management Process involves Four Phases
  Initiation
  Planning
  Execution
  Closing down
3.<number>
Notes: <number>

## Slide 5: Initiating the Project
Project Initiation:
The first phase of the project management process in which
activities are performed to assess the size, scope, and complexity
of the project and to establish procedures to support later project
activities
Establish project initiation team
Establish relationship with customer
Establish project initiation plan
Establish management procedures
Establish project management environment and workbook
Project workbook: An on-line or hard-copy repository for all project correspondence, inputs, outputs, deliverables, procedures, and standards used by all team members useful for project audits, orientation of new team members and performing post project reviews.
3.<number>
Notes: <number>

## Slide 6: Planning the Project
Project Planning – defining clear, discrete activities
Requires making assumptions about availability of resources
Short-term activities are easier to plan
Describe project scope, alternatives and feasibility
  Scope and Feasibility
    Understand the project
    What problem is addressed
    What results are to be achieved
    Measures of success
    Completion criteria
Divide the project into manageable tasks
  Work breakdown structure: The process of dividing the project into manageable tasks and logically ordering them to ensure a smooth evolution between tasks
  Some tasks may be performed in parallel whereas others must follow one another sequentially.
3.<number>
Notes: <number>

## Slide 7: Planning the Project
How to define tasks? A task
  Has a known method, can be done by one-person or well-defined group, has accepted predecessor and successor steps, is measurable so that percent complete can be determined
Divide the project into manageable tasks
  Gantt chart: A graphical representing of a project showing each task as a horizontal bar whose length is proportional to its time for completion.
  Gantt charts do not show how tasks must be ordered but simply shows when an activity must begin and end.
  Different colors, shades, shapes can be used to highlight each kind of task
Estimate resources and create a resource plan
  Estimate resource requirements for each project activity
  Resource plan helps assemble and deploy resources in most effective way
  People are most important and expensive part of resource planning
  Assign tasks to people that suit their skills and allows to learn new skills
3.<number>
Notes: <number>

## Slide 8
Planning the Project
Develop a preliminary schedule
  Assign time estimates to each activity in work breakdown structure
  time estimates allows creating target starting and ending dates for project
  Utilize Gantt and PERT charts
Program Evaluation Review Technique (PERT) Chart
  A diagram that shows project tasks and their relationships
  Ordering of tasks is shown by connecting tasks with its predecessor and successor tasks
  Only individual tasks are drawn and no summary tasks

## Slide 9: Planning the Project
Develop a communication plan
  Outline communication procedures among customers, team members and management
  Communication plan includes when and how written and oral reports will be provided by the team, how team members will coordinate work, what messages will be sent.
Determine project standards and procedures
  Specify how deliverables are tested and produced
Identify and assess risk
  Identify sources of risk
  Estimate consequences of risk
Create a preliminary budget
  Outline planned expenses and revenues of the project to study cost-benefit analysis
3.<number>
Notes: <number>

## Slide 10: Planning the Project
Develop a statement of work
  Occurs near the end of the project planning phase
  Developed primarily for the customer
  Outlines work that will be done and describe what the project will deliver and duration
Set a Baseline Project Plan
  Estimate of project’s tasks and resource requirements that guides the next project phase – execution.
3.<number>
Notes: <number>

## Slide 11: Executing the Project
Project Execution – plans created in prior phases are put into action
Occurs during analysis, design, implementation phases of SDLC
Execute Baseline Project Plan
  Acquire and assign resources
  Train new team members
  Keep project on schedule - as tasks are completed, mark them as completed by percent
Monitor project progress
  Adjust resources, budget and/or activities if project gets ahead or behind schedule
  Can result in modifications to current plan
3.<number>
Notes: <number>

## Slide 12: Executing the Project
Manage changes to Baseline Project Plan
  Slipped completion dates
  Changes in personnel
  New activities found later
  Bungled activities to be redone
Maintain project workbook to maintain complete records of all project events
Communicate project status with entire project team
3.<number>
Notes: <number>

## Slide 13: Closing Down the Project
Project closedown – bring project to an end
Occurs after implementation phase of SDLC
Termination
  Types of termination
    Natural
      Requirements have been met – project is completed successfully
    Unnatural
      Project stopped before completion – due to running out of time or money
  Documentation
  Personnel Appraisal – job and assignment changes, job termination, praising team members
3.<number>
Notes: <number>

## Slide 14: Closing Down the Project
Conduct post-project reviews
  Determine strengths and weaknesses of:
    Project deliverables
    Project management process
    Development process
Close customer contract
3.<number>
Notes: <number>

## Slide 15: Representing and Scheduling Project Plans
Gantt Charts
  Useful for depicting simple projects or parts of large projects
  Show start and completion dates for individual tasks
PERT Charts
  Show order of activities
3.<number>
Comparison of Gantt and PERT Charts
Gantt
  Visually shows duration of tasks
  Visually shows time overlap between tasks
  Visually shows slack time
PERT
  Visually shows dependencies between tasks
  Visually shows which tasks can be done in parallel
  Shows slack time by data in rectangles
Notes: <number>

## Slide 16: Figure 3-16 Graphical diagrams that depict project plans (a) A Gantt Chart (b) A PERT chart
3.<number>
Notes: <number>

## Slide 17: Project Management Software
Many systems are available
Three activities required to use:
  Establish project start or end date
  Enter tasks and assign task relationships
  Select scheduling method to review project reports
3.<number>
Notes: <number>