## Slide 1: Project Management
Jul 31, 2026
Dr.Bokkasam Sasidhar
<number>
An interrelated set of activities with definite starting and ending points, which results in a unique outcome for a specific allocation of resources.
Steps in planning projects –
Define work breakdown structure (statement of all work that has to be completed)
Diagram the network
Develop the schedule
Analyze cost-time trade-off
Assert risks

## Slide 2: NETWORK ANALYSIS
Jul 31, 2026
Dr.Bokkasam Sasidhar
<number>
It is a technique for planning and controlling large projects, such as construction work, R&D projects, computerization of systems etc. Its primary aim is to program and monitor the progress of a project so that the project is completed in the minimum time. In doing this, it pinpoints the parts of the project which are “crucial”.It can also be used in allocating resources such as labour and equipment and thus helps to make the total cost of a project minimum.

## Slide 3: CPM AND PERT
Jul 31, 2026
Dr.Bokkasam Sasidhar
<number>
Network analysis is operated in various forms under different titles, which include:
Critical Path Analysis (CPA) or
Critical Path Method (CPM);
(Deterministic)
Project Evaluation and Review Technique (PERT) (Probabilistic)

## Slide 4: Drawing the network diagram
Jul 31, 2026
Dr.Bokkasam Sasidhar
<number>
Estimate the time needed to complete each individual activity or task that makes up a part of the project
Sort out what activities must be done one after another, and which can be done at the same time, if required
Represent these in a network diagram

## Slide 5: The Project Network - CPM/PERT Activity-on-Arc (AOA) Network
Jul 31, 2026
Dr.Bokkasam Sasidhar
<number>
A branch reflects an activity of a project.
A node represents the beginning and end of activities, referred to as events.
Branches in the network indicate precedence relationships.
When an activity is completed at a node, it has been realized.

## Slide 6: The Project Network House Building Project Data
Number | Activity | Predecessor | Duration
1 | Design house and obtain financing | -- | 3 months
2 | Lay foundation | 1 | 2 months
3 | Order and receive materials | 1 | 1 month
4 | Build house | 2,3 | 3 months
5 | Select paint | 2, 3 | 1 month
6 | Select carper | 5 | 1 month
7 | Finish work | 4, 6 | 1 month
Jul 31, 2026
Dr.Bokkasam Sasidhar
<number>

## Slide 7
Activities can occur at the same time (concurrently).
Network aids in planning and scheduling.
Time duration of activities shown on branches.
The Project Network
Concurrent Activities
Figure: Concurrent activities for house-building project

## Slide 8
A dummy activity shows a precedence relationship but reflects no passage of time.
Two or more activities cannot share the same start and end nodes.
The Project Network
Dummy Activities
Figure: A dummy activity

## Slide 9
The Project Network
AON Network for House Building Project
Activity-on-Node (AON) Network
A node represents an activity, with its label and time shown on
the node
The branches show the precedence relationships
Figure: AON network
Jul 31, 2026
Dr.Bokkasam Sasidhar
<number>

## Slide 10
Jul 31, 2026
Dr.Bokkasam Sasidhar
<number>
AON Network for House Building Project using QM for Windows

## Slide 11
The Project Network
Paths Through a Network
Table:
Paths through the house-building network
Path | Events
A | 1247
B | 12567
C | 1347
D | 13567
Jul 31, 2026
Dr.Bokkasam Sasidhar
<number>

## Slide 12
The critical path is the longest path through the network; the minimum time the network can be completed. From Figure :
Path A: 1  2  4  7 3 + 2 + 3 + 1 = 9 months
Path B: 1  2  5  6  7 3 + 2 + 1 + 1 + 1= 8 months
Path C: 1  3  4  7 3 + 1 + 3 + 1 = 8 months
Path D: 1  3  5  6  7 3 + 1 + 1 + 1 + 1 = 7 months
The Project Network
The Critical Path
Jul 31, 2026
Dr.Bokkasam Sasidhar
<number>

## Slide 13
The Project Network
Activity Start Times
Figure: Activity start time

## Slide 14: The Project Network Activity Scheduling in Activity-on-Node Configuration
Figure: Activity-on-node configuration
Jul 31, 2026
Dr.Bokkasam Sasidhar
<number>

## Slide 15
ES is the earliest time an activity can start:
EF is the earliest start time plus the activity time:
The Project Network
Activity Scheduling : Earliest Times
Figure: Earliest activity start and finish times

## Slide 16
LS is the latest time an activity can start without delaying critical path time:
The Project Network
Activity Scheduling : Latest Times
Figure: Latest activity start and finish times
LF is the latest finish time:

## Slide 17
Slack is the amount of time an activity can be delayed without delaying the project: S = LS – ES = LF - EF
Slack Time exists for those activities not on the critical path for which the earliest and latest start times are not equal.
The Project Network
Activity Slack Time (1 of 2)
*Critical path
Activity | LS | ES | LF | EF | Slack, S
*1 | 0 | 0 | 3 | 3 | 0
*2 | 3 | 3 | 5 | 5 | 0
3 | 4 | 3 | 5 | 4 | 1
*4 | 5 | 5 | 8 | 8 | 0
5 | 6 | 5 | 7 | 6 | 1
6 | 7 | 6 | 8 | 7 | 1
*7 | 8 | 8 | 9 | 9 | 0

## Slide 18
Activity Slack Times for House Building Project using QM for Windows

## Slide 19
The Project Network
Activity Slack Time (2 of 2)
Figure: Activity slack

## Slide 20: Example 2
Draw the AON network for this project.
What is the Critical Path and Project Duration?

## Slide 21: Example 2 - Solution

## Slide 22: Problem 2 - Critical Path and Project Duration

## Slide 23: Problem 3 – Consider the following project network.
Jul 31, 2026
Dr.B.Sasidhar
<number>
Determine the critical path and the project duration.

## Slide 24
Jul 31, 2026
Dr.B.Sasidhar
<number>
 |  |  |  | Earliest | Latest | Earliest | Latest | Total | On Critical
 |  | Activity | Duration | Start | Start | Finish | Finish | Slack | Path?
 |  | A | 2 | 0 | 0 | 2 | 2 | 0 | Yes
 |  | B | 4 | 2 | 3 | 6 | 7 | 1 | No
 |  | C | 5 | 2 | 2 | 7 | 7 | 0 | Yes
 |  | D | 2 | 6 | 15 | 8 | 17 | 9 | No
 |  | E | 1 | 6 | 16 | 7 | 17 | 10 | No
 |  | F | 8 | 7 | 7 | 15 | 15 | 0 | Yes
 |  | G | 3 | 8 | 17 | 11 | 20 | 9 | No
 |  | H | 5 | 15 | 15 | 20 | 20 | 0 | Yes
 |  | I | 4 | 15 | 16 | 19 | 20 | 1 | No
 |  | J | 7 | 20 | 20 | 27 | 27 | 0 | Yes
Problem 3 – Solution:
The critical path is A–C–F–H–J with a completion time
of 27 days.

## Slide 25
Activity time estimates usually cannot be made with certainty.
PERT used for probabilistic activity times.
In PERT, three time estimates are used: most likely time (m), the optimistic time (a), and the pessimistic time (b); using Beta Distribution.
These provide an estimate of the mean and variance of a beta distribution:
variance:
mean (expected time):
Probabilistic Activity Times
Jul 31, 2026
Dr.Bokkasam Sasidhar
<number>

## Slide 26
Probabilistic Time Estimates
Mean
m
a
b
Time
Probability
Beta Distribution
Pessimistic
Optimistic
Notes: 72

## Slide 27: Probabilistic Activity Times Another Example
Jul 31, 2026
Dr.Bokkasam Sasidhar
<number>
To demonstrate the use of probabilistic activity times, we will employ a new example. (We could use the house-building network from the previous section; however, a network that is a little larger and more
complex will provide more experience with different types of projects.)

## Slide 28: Probabilistic Activity Times - Another Example
Jul 31, 2026
Dr.Bokkasam Sasidhar
<number>
The Southern Textile Company has decided to install a new computerized order processing system that will link the company with customers and suppliers online. In the past, orders for the cloth the company produces were processed manually, which contributed to delays in delivering orders and resulted in lost sales. The company wants to know how long it will take to install the new system.
We will briefly describe the activities and the network for the installation of the new order processing system.

## Slide 29: The Southern Textile Company - Activities
Jul 31, 2026
Dr.Bokkasam Sasidhar
<number>
The network begins with three concurrent activities: The new computer equipment is installed (activity 1); the computerized order processing system is developed (activity 2); and people are recruited to operate the system (activity 3). Once people are hired, they are trained for the job (activity 6), and other personnel in the company, such as marketing, accounting, and production personnel, are introduced to the new system (activity 7). Once the system is developed (activity 2), it is tested manually to make sure that it is logical (activity 5). Following activity 1, the new equipment is tested, and any necessary modifications are made (activity 4), and the newly trained personnel begin training on the computerized system (activity 8). Also, node 9 begins the testing of the system on the computer to check for errors (activity 9). The final activities include a trial run and changeover to the system (activity 11) and final debugging of the computer system (activity 10).

## Slide 30: Precedence relations and Activity Times– Textile Company
Task a m b Preceding Tasks
Task 1 6 8 10
Task 2 3 6 9
Task 3 1 3 5
Task 4 2 4 12 Task 1
Task 5 2 3 4 Task 2
Task 6 3 4 5 Task 3
Task 7 2 2 2 Task 3
Task 8 3 7 11 Task 1 Task 5 Task 6
Task 9 2 4 6 Task 1 Task 5 Task 6
Task 10 1 4 7 Task 4
Task 11 1 10 13 Task 7 Task 8 Task 9

## Slide 31
Probabilistic Activity Times
The Southern Textile Company
Activity time estimates for figure

## Slide 32
The Southern Textile Company Probabilistic Activity Times –
QM for Windows Output

## Slide 33
Probabilistic Activity Times
The Southern Textile Company
Network for order processing system installation

## Slide 34
The Southern Textile Company Network – QM for Windows Output

## Slide 35
Probabilistic Activity Times
The Southern Textile Company
Earliest and latest activity times

## Slide 36
Expected project time is the sum of the expected times of the critical path activities.
Project variance is the sum of the critical path activities’ variances
The expected project time is assumed to be normally distributed (based on central limit theorem).
In example, expected project time (tp) and variance (vp) interpreted as the mean () and variance (2) of a normal distribution:
= 25 weeks
2 = 62/9
= 6.9 weeks2
Probabilistic Activity Times
Expected Project Time and Variance

## Slide 37
Using the normal distribution, probabilities are determined by computing the number of standard deviations (Z) a value is from the mean.
The Z value is used to find the corresponding probability.
Probability Analysis of a Project Network
Jul 31, 2026
Dr.Bokkasam Sasidhar
<number>

## Slide 38
Probability Analysis of a Project Network
The Southern Textile Company
Normal distribution of network duration
Jul 31, 2026
Dr.Bokkasam Sasidhar
<number>

## Slide 39
Probability Analysis of a Project Network
The Southern Textile Company
Probability that the network will be completed in 30 weeks or less
Jul 31, 2026
Dr.Bokkasam Sasidhar
<number>

## Slide 40
What is the probability that the new order processing system will be ready by 30 weeks?
Probability Analysis of a Project Network
The Southern Textile Company
Z value of 1.90 corresponds to probability of .4713 in Table A.1, Appendix A. The probability of completing project in 30 weeks or less:
(.5000 + .4713) = .9713.
Jul 31, 2026
Dr.Bokkasam Sasidhar
<number>

## Slide 41
Probability Analysis of a Project Network
The Southern Textile Company
Probability the network will be completed in 22 weeks or less
Jul 31, 2026
Dr.Bokkasam Sasidhar
<number>

## Slide 42
A customer will trade elsewhere if the new ordering system is not working within 22 weeks. What is the probability that she will be retained?
Z = (22 - 25)/2.63 = -1.14
Z value of 1.14 (ignore negative) corresponds to probability of .3729 in Z Table.
Probability that customer will be retained is .1271 (.5000-.3729)
Probability Analysis of a Project Network
The Southern Textile Company
Jul 31, 2026
Dr.Bokkasam Sasidhar
<number>

## Slide 43: CPM/PERT Analysis Output with QM for Windows
Jul 31, 2026
Dr.Bokkasam Sasidhar
<number>

## Slide 44: CPM/PERT Analysis with QM for Windows
QM for Windows solution output for system installation
Jul 31, 2026
Dr.Bokkasam Sasidhar
<number>

## Slide 45
Solved Problem 2
What is the probability of completing the project in 23 weeks?

## Slide 46
Solved Problem 2

## Slide 47
Solved Problem 2
Using the Normal Distribution, we find that the probability of completing the project in 23 weeks or less is 0.9357.
Notes: 70