Discussion 2

True or False Questions:

1. Preceding activities are those that must occur before others can be done.

2. The sequence of activities in a project is depicted by the precedence relationships.

3. A work breakdown structure breaks down a project into subcomponents, components, activities, and tasks.

4. A work breakdown structure is a useful tool because it addresses the timing of individual work elements.

5.  Gantt charts can display early start or late start logic.

6. The horizontal axis for a Gantt chart is time.

7. Each individual bar on a Gantt chart represents an activity.

8.  Projects are typically ongoing, day-to-day activities that have goods and services as outputs.

9.  The special nature of projects relieves project managers from their routine of planning, organizing, motivating, directing, and controlling.

10. Client interest in a project is highest during the termination and conceptual phases.

11.  Process refers to ongoing, day-to-day activities in which an organization engages while producing goods and services.

12.  The stages in a project's development and execution are known as the project life cycle.

13. Gantt charts represent one of the first attempts to develop a network diagram that orders project activities by baseline calendar dates.

Multiple-Choice Questions

14. Use the Gantt chart and the activity list to determine when resource 2 is free.

| Activity | Resources | Activity | Resources |
| --- | --- | --- | --- |
| A | 1 | F | 1 |
| B | 5 | G | 2 |
| C | 4 | H | 5 |
| D | 3 | J | 3 |
| E | 2 | K | 2 |

A) between 0 and 15

B) between 15 and 30

C) between 30 and 45

D) between 45 and 60

15. Use the Gantt chart and the activity list to determine which resource is needed earliest in this project.

| Activity | Resources | Activity | Resources |
| --- | --- | --- | --- |
| A | 5 | F | 2 |
| B | 6 | G | 3 |
| C | 7 | H | 4 |
| D | 1 | J | 5 |
| E | 2 | K | 1 |

A) Resource 2

B) Resource 3

C) Resource 1

D) Resource 4

Use the following Gantt chart and activity list to answer questions 16 to 19:

| Activity | Resources | Activity | Resources |
| --- | --- | --- | --- |
| R | 3 | M | 1 |
| H | 1 | K | 5 |
| G | 4 | J | 3 |
| F | 2 | P | 1 |
| B | 2 | S | 2 |
| T | 4 | W | 3 |

16. Determine when resource 3 is free.

A) between 0 and 10

B) between 10 and 20

C) between 20 and 30

D) between 30 and 40

17.  Determine which resource has the greatest continual use.

A) Resource 4

B) Resource 2

C) Resource 3

D) Resource 5

18.  Determine which resource is used the least.

A) Resource 1

B) Resource 2

C) Resource 4

D) Resource 5

19.  Determine which resource is used the most.

A) Resource 1

B) Resource 2

C) Resource 4

D) Resource 5

Use the following Gantt chart and activity list to answer questions 20 and 21:

| Activity | Resources | Activity | Resources |
| --- | --- | --- | --- |
| R | 3, 5 | M | 1, 2 |
| H | 1 | K | 4 |
| G | 2, 5 | J | 3 |
| F | 4, 1 | P | 1 |
| B | 2 | S | 3, 4 |
| T | 4 | W | 3 |

20. Determine which resource is used the least.

A) Resource 4

B) Resource 2

C) Resource 1

D) Resource 3

21.  Determine which resource is released from this project for use in another project the earliest.

A) Resource 2

B) Resource 4

C) Resource 1

D) Resource 3

Use the following Gantt chart and activity list to answer questions 22 and 23:

| Activity | Resources | Activity | Resources |
| --- | --- | --- | --- |
| A | 1 | F | 2 |
| B | 3 | G | 3 |
| C | 4 | H | 4 |
| D | 2 | J | 5 |
| E | 2 | K | 1 |

22. Determine which resource is used the most.

A) Resource 4

B) Resource 3

C) Resource 1

D) Resource 2

23.  Determine which resource is free for use in another project before the others.

A) Resource 4

B) Resource 3

C) Resource 1

D) Resource 2

24. Use the information in the table to create a baseline Gantt chart for the project where activity lengths are given in days.

| Activity | Duration | Predecessor |
| --- | --- | --- |
| A | 6 | -- |
| B | 3 | A |
| C | 7 | A |
| D | 5 | B |
| E | 10 | C |
| F | 8 | D, E |
| G | 6 | F |
| H | 4 | G |
| J | 10 | G |
| K | 5 | H, J |