Discussion 3

True or False Questions:

1.  Preceding activities are those that must occur before others can be done.

2. The CPM technique assumes that durations are deterministic.

3. Dummy activities are used in AOA networks to indicate the existence of precedent relationships between activities and their event nodes.

4. An activity of duration zero whose sole purpose is to maintain network logic is a dummy activity.

5. The critical path is the shortest path through the project network.

6. The critical path is the longest path through the project network.

7. Slack is the amount of time an activity can be delayed without delaying the project.

8. The critical path activities have no slack.

9. An AOA network will never require dummy activities.

10. An AON network will never require dummy activities.

11. Two concurrent activities in a project can be represented in an AOA network by starting and ending on the same node.

12. The early start for an activity on the critical path is always equal to the earliest finish of the preceding activity.

13. The early start for a non-critical activity is always equal to the earliest finish of the preceding activity.

14. The early finish for an activity on the critical path is equal to the latest finish of the preceding activity.

15. When earliest finish is subtracted from latest finish, we obtain the slack value for the activity.

16. The earliest finish time for the final activity on a project network is also the total completion of the project.

Multiple-Choice Questions:

17. A sequence of activities defined by the project network logic is a(n):

A) event.

B) path.

C) node.

D) route.

18. An activity with two or more immediate predecessors is a(n):

A) merge activity.

B) burst activity.

C) float activity.

D) event.

19. Serial activities are those that:

A) flow from one to the next in sequence.

B) have sequential numbers.

C) have the same numbers.

D) should be performed simultaneously.

20. Concurrent activities are:

A) activities that must be done one after the other.

B) activities that can be performed at the same time.

C) activities that use labor from the same group of workers.

D) activities that use resources from the same resource pool.

21. Which of these statements about this network is best?

A) Activities A and B are serial activities.

B) Activities B and C are serial activities.

C) Activities A and C are serial activities.

D) Activity D is a merge activity.

22. Network logic suggests that:

A) Activity D can start any time.

B) Activity A must be complete before Activity B can be done.

C) Activities A, B and C must be complete before Activity D can be done.

D) Activity C must begin before Activity B begins.

23. Based on the activity network pictured, what is the best statement?

A) Before starting Activity C, Activity A and Activity B must be completed.

B) Before starting Activity D, Activity A and Activity B need to be completed.

C) Before starting Activity E, Activity A and Activity B need to be completed.

D) Before starting Activity C, Activity A and Activity D must be completed.

24. What is the early start time for Activity D given the activity times and precedence requirements shown in the table?

| Activity | Time | Predecessor |
| --- | --- | --- |
| A | 5 | -- |
| B | 8 | A |
| C | 4 | A |
| D | 5 | B, C |

A) 5

B) 9

C) 13

D) 18

Use the following information for questions 25 to 27:

Given the activity times and precedence requirements shown in the table below:

| Activity | Time | Predecessor |
| --- | --- | --- |
| A | 4 | -- |
| B | 7 | -- |
| C | 8 | A |
| D | 2 | A |
| E | 4 | B |
| F | 5 | C, D |
| G | 9 | E, F |
| H | 7 | G |

25. What is the late start time for Activity E?

A) 12

B) 13

C) 14

D) 15

26. What is the early start time for Activity G?

A) 14

B) 15

C) 16

D) 17

27. What is the slack time for Activity C ?

A) 2

B) 1

C) 0

D) 3

Use the following information for questions 28 to 32:

Given the information in the table:

| Task | Predecessor | Duration | Early Start | Early Finish | Late Start | Late Finish |
| --- | --- | --- | --- | --- | --- | --- |
| A | -- | 8 |  |  |  |  |
| B | A |  |  |  | 14 |  |
| C | A |  |  | 23 | 8 |  |
| D | C, B | 6 | 23 |  | 26 |  |
| E | C |  |  | 32 |  |  |
| F | D, E |  | 32 |  |  | 38 |

28. Determine the early start time for Activity B.

A) day 10

B) day 8

C) day 9

D) day 11

29.  Determine the early finish time for Activity D.

A) day 23

B) day 26

C) day 29

D) day 32

30.  Determine the late finish time for Activity B.

A) day 17

B) day 26

C) day 20

D) day 23

31.  Determine the slack time for Activity B.

A) 6 days

B) 4 days

C) 2 days

D) 0 days

32. What is the slack time for activity E?

A) 1 day

B) 0 days

C) 2 days

D) 4 days

Use the following information for questions 33 to 37:

Use the network diagram and activity lengths in the nodes.

33. The early start time for activity D is

A) 8

B) 13

C) 14

D) 21

34.  The early finish time for activity G is

A) 26

B) 25

C) 24

D) 23

35.  The late finish time for activity C is

A) 12

B) 13

C) 14

D) 15

36.  The slack time for activity D is

A) 3

B) 2

C) 1

D) 0

37.  The early start time for activity D is

A) 8

B) 13

C) 14

D) 21

Questions

38. Sketch the network described in the table in AOA format.

| Activity | Predecessor |
| --- | --- |
| A | -- |
| B | A |
| C | A |
| D | B |
| E | B, C |
| F | D |
| G | D |
| H | F, G |
| K | G |
| L | H, K |

39. The critical path of this network is:

40. The fastest completion time for this project is:

41. What is the duration of the project shown in the network?

Use the following network for questions 42 and 43:

42. The early start for activity 2 is _____

43.  The latest start for activity 3 is _____

Use the following information for a project for questions 44 to 52:

| Activity | Immediate Processor | Activity Time (days) |
| --- | --- | --- |
| A | - | 6 |
| B | - | 8 |
| C | A, B | 5 |
| D | B | 4 |
| E | C | 7 |
| F | C, D | 3 |
| G | D | 6 |
| H | E, F, G | 5 |

44. Draw the AON (Activity-On-Node) project network.

45. Calculate ES, EF, LS, LF, Slack for each activity and hence the critical path. What is the total completion time of the project?

46. What are the estimated slack times (in weeks) for activities A to H?

47. What is the slack time for activity C?

48. What is the slack time for activity F?

49. What is the latest possible time that Activity E can be started without delaying the completion of the project?

50. What is the latest finish time for activity D?

51. What is the latest time that activity C can start without delaying the project?

52. What is the latest time that activity C can finish without delaying any other activities?

53. Phoebe B. Beebee is constructing a canal for the annual canoe races and has identified eleven activities that are required to complete this important project. She calculated early and late start times and early and late finish times but spilled coffee all over her printout. Use the remaining information to reconstruct the table for Phoebe B. Beebee and her new canoe canal.

| Activity | Predecessor | Length | Early Start | Late Start | Early Finish | Late Finish |
| --- | --- | --- | --- | --- | --- | --- |
| A | -- |  |  |  | 12 |  |
| B | A | 20 |  |  |  |  |
| C | A |  |  |  |  |  |
| D | B, E |  |  | 42 |  |  |
| E | C |  | 28 |  |  | 42 |
| F | E |  | 42 |  | 50 |  |
| G | D |  | 53 | 53 |  |  |
| H | G |  | 70 |  |  |  |
| I | G |  |  | 72 |  |  |
| J | F | 4 |  |  |  |  |
| K | H, I, J |  |  | 81 |  | 91 |

54.

Calculate ES, EF, LS, LF, Slack for each activity and hence the critical path. What is the total completion time of the project?