Discussion 4

True or False Questions:

1. The PERT technique assumes that durations are deterministic.

2. PERT analysis is based on estimates, which, if unreasonably determined, can lead to inaccurate and misleading project schedules.

3. In PERT, three time estimates (optimistic, most likely, and pessimistic) provide an estimate of the mean and variance for each activity, based on the normal distribution.

4. In PERT, the project variance is the sum of the variance of all project activities.

5. In PERT, the expected project completion time is assumed to be distributed according to a beta distribution.

6. In PERT, the expected project completion time is assumed to be normally distributed.

7. In the beta distribution, the longer tail is located to the right (on the pessimistic end).

8. The PERT pessimistic time estimate is an estimate of the minimum time an activity will require.

9. In PERT, the path with the fewest activities is referred to as the critical path.

10. The standard deviation of project duration is the average of the standard deviation of all activities on the critical path.

Multiple-Choice Questions:

11. An activity has an optimistic time estimate of 15 days, a most likely estimate of 24 days, and a pessimistic estimate of 40 days. What is the expected duration of the activity?

A) less than 27 days but greater than or equal to 26 days

B) less than 26 days but greater than or equal to 25 days

C) less than 25 days but greater than or equal to 24 days

D) less than 24 days

12. An activity has an optimistic time estimate of 15 days, a most likely estimate of 24 days, and a pessimistic estimate of 40 days. What is the variance of the activity?

A) 4.17

B) 25.17

C) 17.36

D) 10.33

13. An activity has an optimistic time estimate of 7 days, a most likely estimate of 12 days, and a pessimistic estimate of 20 days. What is the expected duration of the activity?

A) 13 days

B) 13.5 days

C) 12 days

D) 12.5 days

14. An activity has an optimistic time estimate of 7 days, a most likely estimate of 12 days, and a pessimistic estimate of 20 days. What is the expected standard deviation of the activity?

A) between 2 and 3 days

B) between 3 and 4 days

C) between 4 and 5 days

D) between 5 and 6 days

15. An activity has a pessimistic time that is three times as long as its most likely time and five times as long as its optimistic time. If the activity variance is 10, what is the expected time?

A) about 10 days

B) about 14 days

C) about 19 days

D) about 23 days

16. Activity Z has estimates a = 5, b = 10, m = 7; activity X has estimates a = 4, b = 11, m = 6; and activity Y has estimates a = 3, b = 12, m = 8. Which of the following statements is best?

A) Activity X is longer than Activity Y.

B) Activity X has a higher standard deviation than Activity Z.

C) Activity Z is shorter than Activity Y.

D) Activity Y has a smaller variance than Activity Z.

A gentleman farmer maniacally works on academic projects to raise funds for his true passion, farming. He has identified seven tasks and developed three time estimates (all in days) of the next big project on the farm, replacing the fence at the comedy pasture. Tasks, precedence requirements, and time estimates are shown in the table.

| Activity | Optimistic time | Most Likely time | Pessimistic time | Predecessor |
| --- | --- | --- | --- | --- |
| Corner Posts | 4 | 5 | 6 | -- |
| String Line | 7 | 8 | 9 | -- |
| Dig Holes | 10 | 12 | 14 | Corner Posts |
| Plant Posts | 11 | 14 | 17 | String Line |
| Weld Top Bar | 8 | 11 | 14 | String Line |
| Paint | 9 | 11 | 13 | Dig Holes, Plant Posts |
| Tack Wire | 9 | 12 | 16 | Weld Top Bar |

Using the above data, answer questions 17 to 20.

17. What is the expected completion time of the project?

A) 32 days

B) 33 days

C) 34 days

D) 35 days

18.  What is the standard deviation of the project's critical path?

A) 1.33 days

B) 1.56 days

C) 1.25 days

D) 1.75 days

19. What is the probability that the project is completed in 31 days?

A) 0.055

B) 0.092

C) 0.125

D) 0.187

20.  What is the probability that the project takes more than 34 days?

A) 0.788

B) 0.212

C) 0.945

D) 0.055

21.

A project consisting of eight activities have the following three-time-estimates as given below:

Analysis using QM for Windows provided the following outputs:

Optimistic	Most Likely 	Pessimistic	Activity time	Standard Deviation	Variance

A	9		15		21		15		2			4

B	13		21		23		20		1.666667		2.777778

C	6		9		18		10		2			4

D	23		35		47		35		4			16

E	19		26		27		25		1.333333		1.777778

F	23		29		41		30		3			9

G	14		20		26		20		2			4

H	2		5		8		5		1			1

Project results

Total of critical Activities								25

Square root of total						5

Activity time	ES	EF	LS	LF	 Slack	Standard Deviation

Project  75							5

A		15		0	15	0	15	0	2

B		20		0	20	5	25	5	1.666667

C		10		15	25	30	40	15	2

D		35		15	50	15	50	0	4

E		25		20	45	25	50	5	1.333333

F		30		25	55	40	70	15	3

G		20		50	70	50	70	0	2

H		5		70	75	70	75	0	1

Using the output results answer the questions 22 to 34:

22. What are the estimated expected completion (mean) times (in weeks) for activities A to H?

23. What is the critical path for this project network?

24. If the early start for activity A is equal to 23 months and the duration of activity A is equal to 5 months, what is the earliest finish for activity A?

25. If the earliest finish for activity C is equal to 10 months and its duration 3 months, what is its earliest start?

26. Determine the latest start for activity E?

27. What are the estimated slack times (in weeks) for activities A to H?

28. What are the estimated standard deviations (in weeks) in the times for activities A to H?

29. What is the estimated expected mean time (in weeks) for the project completion?

30. What is the estimated standard deviation (in weeks) for the critical path completion time?

31. What is the probability that the critical path for this project will be completed within 75 weeks?

32. What is the probability that the critical path for this project will be completed within 80 weeks?

33. Within what amount of time (in weeks) is there a 90% probability that the critical path for this project will be completed?

34. Within what amount of time (in weeks) is there a 99% probability that the critical path for this project will be completed?