Discussion 5

True or False Questions:

1. Crashing cost is always higher than the normal cost.

2. Shortening the project's duration by deleting unnecessary activities is called crashing.

3. The process of accelerating a project is referred to as crashing.

4. In order to accelerate completion of a project, the manager must crash critical path activities.

5.  The process of accelerating a project is referred to as crashing.

6. The critical path may not contain a dummy activity.

7. Most project management software employs AOA diagramming

Multiple-Choice Questions

8. One reason for crashing a project is:

A) the project has slipped behind schedule.

B) that the initial schedule may be too pessimistic.

C) market needs change and the project is not in demand any more.

D) there are no repercussions for delivering the project late.

9. If an activity's cost is plotted against its duration on axes with zeros at the origin:

A) the slope of the line is positive because it costs more to finish an activity more quickly.

B) the slope of the line is negative because a shorter activity costs less than a longer one.

C) the slope of the line is negative because it costs more to finish an activity more quickly.

D) the slope of the line is positive because a longer activity costs more than a shorter one.

10. An activity performed by a subcontractor is scheduled for 20 weeks at an anticipated cost of $100,000. Due to slippage on the critical path you need to reduce this activity by three weeks. If the subcontractor informs you that the activity can be completed in 15 weeks for $200,000, what is the slope for the activity?

A) $20,000 per week

B) $33,333 per week

C) $5,000 per week

D) $13,333 per week

11. Given the cost information in the table, what is the cheapest activity to crash on a per week basis?

A) Activity A

B) Activity B

C) Activity C

D) Activity D

12. Use the information in the table (all times are in days) to determine the lowest cost minimum completion time?

| Activity | Normal Time | Minimum Time | Crash Cost ($/day) | Predecessor |
| --- | --- | --- | --- | --- |
| A | 10 | 6 | $50 | -- |
| B | 6 | 3 | $30 | -- |
| C | 2 | 2 | -- | B |
| D | 4 | 2 | $40 | C |
| E | 6 | 4 | $80 | A |
| F | 8 | 5 | $100 | D, E |

A) $1,040

B) $1,020

C) $740

D) $720

13. Use the information in the table (all times are in days) to determine the lowest extra cost for a 20-day project.

| Activity | Normal Time | Minimum Time | Crash Cost ($/day) | Predecessor |
| --- | --- | --- | --- | --- |
| A | 10 | 6 | $50 | -- |
| B | 6 | 3 | $30 | -- |
| C | 2 | 2 | -- | B |
| D | 4 | 2 | $40 | C |
| E | 6 | 4 | $80 | A |
| F | 8 | 5 | $100 | D, E |

A) $200

B) $130

C) $120

D) $100

14. A project has the activity duration and cost information indicated in the table where all times are in weeks. There is a penalty of $250 per week for every week the project extends beyond 50 weeks. What is the duration of the least expensive project possible?

| Activity | Normal time | Crash time | Normal Cost | Crash Cost | Predecessor |
| --- | --- | --- | --- | --- | --- |
| A | 5 | 3 | 500 | 1100 |  |
| B | 18 | 15 | 900 | 2300 | A |
| C | 12 | 9 | 2500 | 3000 | A |
| D | 9 | 7 | 500 | 650 | B |
| E | 15 | 12 | 3000 | 5000 | B |
| F | 12 | 10 | 4000 | 5000 | C, D |
| G | 20 | 15 | 3600 | 4800 | E, F |

A) 60 weeks

B) 57 weeks

C) 53 weeks

D) 50 weeks

15. Given the cost information in the table, what is the cheapest activity to crash on a per week basis?

A) Activity A

B) Activity B

C) Activity C

D) Activity D

Use the following information for questions 16-19:

The diagram below shows the activities on the nodes, and the table shows the normal time and crash time (in days) and cost for each activity:

| Activity | Normal Time | Crash Time | Normal cost | Crash cost | Cost per day to crash |
| --- | --- | --- | --- | --- | --- |
| A | 6 | 6 | $3000 | $3000 | --- |
| B | 10 | 8 | $1000 | $1200 | $100 |
| C | 5 | 4 | $300 | $600 | $300 |
| D | 4 | 1 | $700 | $2800 | $700 |
| E | 9 | 7 | $500 | $1500 | $500 |
| F | 2 | 1 | $650 | $1300 | $650 |

Analysis using QM for Windows provided the following outputs:

Normal time Crash time Normal Cost Crash Cost  CrashCost/pd  Crash by   Crashing cost

Project 20	15

A	6		6	    3000		3000		0	  0		0

B	10		8	    1000		1200		100	  2		200

C	5		4	      300		600		300	  1		300

D	4		1	      700		2800		700	  1		700

E	9		7	      500		1500		500	  2		1000

F	2		1	      650		1300		650	  1		650

TOTALS		     6150							2850

Project time	Period cost	Cumulative cost	A	B	C	D	E	F

20			0		0

19			300		300					1

18			500		800					1		1

17			600		1400				1	1		2

16			650		2050				1	1		2	1

15			800		2850				2	1	1	2	1

Using the output results answer the following questions:

16. What is the Normal completion time of the project? What is the associated cost?

.

17. Determine which activities should be crashed to shorten the project by 1 day. What is the cost?

18. Determine which activities should be crashed to shorten the project by 2 days. What is the cost?

19. Determine which activities should be crashed to shorten the project by 3 days.  What is the cost?

20. What is the cost to finish the following project as quickly as possible? (all activity durations are in weeks and costs in US dollars)

Analysis using QM for Windows provided the following outputs:

| Activity | Predecessor | Normal Time | Minimum Time | Normal Cost | Crash Cost |
| --- | --- | --- | --- | --- | --- |
| A |  | 12 | 10 | 1000 | 1500 |
| B | A | 5 | 3 | 1200 | 1950 |
| C | A | 9 | 7 | 1500 | 2100 |
| D | B, C | 14 | 10 | 1800 | 2100 |
| E | B | 4 | 3 | 1400 | 1875 |
| F | D | 9 | 8 | 1000 | 1450 |
| G | E | 7 | 5 | 700 | 1200 |
| H | F, G | 11 | 8 | 2000 | 3000 |
| I | H | 8 | 6 | 1100 | 1700 |

Normal time Crash time Normal Cost Crash Cost   Crash cost/pd   Crash by     Crashing cost

Project	63	49

A	12	10	1000	1500		250		2	500

B	5	3	1200	1950		375		0	0

C	9	7	1500	2100		300		2	600

D	14	10	1800	2100		75		4	300

E	4	3	1400	1875		475		0	0

F	9	8	1000	1450		450		1	450

G	7	5	700	1200		250		0	0

H	11	8	2000	3000		333.3333	3	1000

I	8	6	1100	1700		300		2	600

TOTALS		11700						3450

Project time	Period cost	Cumulative cost	A	B	C	D	E	F	G	H	I

63		0		0

62		75		75						1

61		75		150						2

60		75		225						3

59		75		300						4

58		250		550			1			4

57		250		800			2			4

56		300		1100			2		1	4

55		300		1400			2		2	4

54		300		1700			2		2	4					1

53		300		2000			2		2	4					2

52		333.3333	2333.333		2		2	4				1	2

51		333.3335	2666.667		2		2	4				2	2

50		333.3333	3000			2		2	4				3	2

49		450		3450			2		2	4		1		3	2