## Slide 1: ENGINEERING MANAGEMENT (GE 404)
Tutorial # 6
Time-Cost Trade-Off
(Time Shortening)
بسم الله الرحمن الرحيم
Instructor: Eng.Alothman
Notes: This is a title slide.

## Slide 2
Basic Steps for crash calculation
Compute the crash cost per time period, considering crash costs are linear over time
Using current activity times, find the critical path and identify the critical activities
Select the activity on the critical path of which (a) it can still be crashed, and (b) it has the smallest crash cost per period.
If there is more than one critical path, then select one activity from each critical path such that (a) each selected activity can still be crashed, and (b) the total crash cost of all selected activities is the smallest.
Note that the same activity may be common to more than one critical path
5. Update all activity times. If the desired due date has been reached, stop. If not, return to Step 2
4. Determine the compression limit (Nil)

## Slide 3
Example1:
The below network shows the activities of a small engineering project. Data of the project is given in the below table. The indirect cost is estimated to be SR 90/day. Determine the optimum contract duration.
Activity Code | Time (day) |  | Cost (SR) | 
 | Normal | Crash | Normal | Crash
A | 7 | 3 | 1500 | 2300
B | 9 | 5 | 1400 | 1840
C | 8 | 5 | 1280 | 1430
D | 14 | 9 | 1100 | 1400
E | 4 | 2 | 1200 | 1500
F | 9 | 7 | 1500 | 1680
G | 7 | 3 | 1200 | 1520
H | 11 | 7 | 1750 | 1910
I | 11 | 7 | 1500 | 1720

## Slide 4
1- Develop AON, calculate times, find critical path
Project completion time = 40 working days
Critical Path: B, F, H, I.
 | ES | EF | LS | LF | TF | FF | CP
A | 0 | 7 | 10 | 17 | 10 | 0 | N
B | 0 | 9 | 0 | 9 | 0 | 0 | Y
C | 7 | 15 | 17 | 25 | 17 | 8 | N
D | 9 | 23 | 11 | 25 | 2 | 0 | N
E | 23 | 27 | 25 | 29 | 2 | 2 | N
F | 9 | 18 | 9 | 18 | 0 | 0 | Y
G | 18 | 29 | 22 | 29 | 4 | 4 | N
H | 18 | 29 | 18 | 29 | 0 | 0 | Y
I | 29 | 40 | 29 | 40 | 0 | 0 | Y

## Slide 5
Activity Code | Time (day) |  | Cost (SR) |  | Time can be crashed | Slope, SR/day | Total Crash Cost, SR
 | Normal | Crash | Normal | Crash |  |  | 
A | 7 | 3 | 1500 | 2300 | 4 | 200 | 800
B | 9 | 5 | 1400 | 1840 | 4 | 110 | 440
C | 8 | 5 | 1280 | 1430 | 3 | 50 | 150
D | 14 | 9 | 1100 | 1400 | 5 | 60 | 300
E | 4 | 2 | 1200 | 1500 | 2 | 150 | 300
F | 9 | 7 | 1500 | 1680 | 2 | 90 | 180
G | 7 | 3 | 1200 | 1520 | 4 | 80 | 320
H | 11 | 7 | 1750 | 1910 | 4 | 40 | 160
I | 11 | 7 | 1500 | 1720 | 4 | 55 | 220
 |  | ∑ | 12430 | 15300 |  | ∑ | 2870
2- Calculate cost slope

## Slide 6
3- prepare data for crash analysis
Add the crash limit on node diagram and table of iteration
Cycle # | Activity to Shorten | Can Be Shortened | NIL | day Shortened | Cost / day, SR | Cost / Cycle, SR | Total Direct Cost, SR | Project Duration
0 | - |  |  |  |  |  | 12430 | 40
1 |  |  |  |  |  |  |  | 
2 |  |  |  |  |  |  |  | 

## Slide 7
4- Start to Short Critical Activities beginning with activity having lowest cost activity
a) Find compression time to reduce activity (H) time
Activity (H) can reduced 4 days, but non critical activity (E) on other paths has only FF=2 Then Nil is 2 day
b) Calculate solution and organize data in the table of iteration table of cycle reduction
Cycle # | Activity to Shorten | Can Be Shortened | NIL | days Shortened | Cost / day, SR | Cost / Cycle, SR | Total Direct Cost, SR | Project Duration
0 | - |  |  |  |  |  | 12430 | 40
1 | H | 4 | 2 (Due FF of E) | 2 | 40 | 80 | 12510 | 38
2 |  |  |  |  |  |  |  | 
Cycle1: reduce critical Activity (H) time which has low cost

## Slide 8
5- Update the project AON
Cycle 1: Modified AON After Time reduction of Activity (H) by 2 days
After reduction other critical Path is developed: B, D, E, I

## Slide 9
4- Start to Short Critical Activities beginning with activity having lowest cost activity
a) Find compression time to reduce activity (I) time
Activity (I) can reduced 4 days, without any constraint for FF, Then NIL =4
b) Calculate solution and organize data in the table of iteration table of cycle reduction
Cycle # | Activity to Shorten | Can Be Shortened | NIL | Days Shortened | Cost / day, SR | Cost / Cycle, SR | Total Direct Cost, SR | Project Duration
0 | - |  |  |  |  |  | 12430 | 40
1 | H | 4 | 2 (Due FF of E) | 2 | 40 | 80 | 12510 | 38
2 | I | 4 | 4 | 4 | 55 | 220 | 12730 | 34
3 |  |  |  |  |  |  |  | 
Cycle2: reduce critical Activity (I) time which has low cost

## Slide 10
5- Update the project AON
Cycle 2: Modified AON After Time reduction of Activity (I) by 4 days

## Slide 11
4- Start to Short Critical Activities beginning with activity having lowest cost activity
a) Find compression time to reduce activity (H,D) time
b) Calculate solution and organize data in the table of iteration table of cycle reduction
Cycle # | Activity to Shorten | Can Be Shortened | NIL | Days Shortened | Cost / day, SR | Cost / Cycle, SR | Total Direct Cost, SR | Project Duration
0 | - |  |  |  |  |  | 12430 | 40
1 | H | 4 | 2 (Due FF of E) | 2 | 40 | 80 | 12510 | 38
2 | I | 4 | 4 | 4 | 55 | 220 | 12730 | 34
3 | H,D | (2,2) | 2(Due FF of G) | 2 | (40,60) | 200 | 12930 | 32
Cycle3: reduce critical Activity (H,D) times which has low cost and satisfy the Critical Paths
Activity (H,D) can be reduce by 2 days. Also Activity (G) can be reduced by 2 and has FF=2, Then NIL =2

## Slide 12
5- Update the project AON
Cycle 3: Modified AON After Time reduction of Activity (H,D) by 2 days
After reduction other critical Path is developed: B, F, G, I

## Slide 13
4- Start to Short Critical Activities beginning with activity having lowest cost activity
a) Find compression time to reduce activity (B) time
b) Calculate solution and organize data in the table of iteration table of cycle reduction
Cycle4,5: reduce critical Activity (B), (D,F )times which has low cost and satisfy the Critical Paths
Activity (B) can be reduce by 4 days., Then NIL =4
Activity (D,F) can be reduce by 2 days., Then NIL=2
Cycle # | Activity to Shorten | Can Be Shortened | NIL | days Shortened | Cost / day, SR | Cost / Cycle, SR | Total Direct Cost, SR | Project Duration
0 | - |  |  |  |  |  | 12430 | 40
1 | H | 4 | 2 (Due FF of E) | 2 | 40 | 80 | 12510 | 38
2 | I | 4 | 4 | 4 | 55 | 220 | 12730 | 34
3 | H,D | (2,2) | 2(Due FF of G) | 2 | (40,60) | 200 | 12930 | 32
4 | B | 4 | 4 | 4 | 110 | 440 | 13370 | 28
5 | D,F | (2,2) | 2 | 2 | (60,90) | 300 | 13670 | 26

## Slide 14
5- Update the project AON
Cycle 4,5: Modified AON After Time reduction of Activity (B) by 4 days, and (D,F) 2 days
After reduction other critical Path is developed: A, C, E, I
Remark:
All Activity on network are critical and no further reduction is possible
0
0
0

## Slide 15
28
13370
2520
15890

## Slide 16: Thank You
Questions Please