## Slide 1: ENGINEERING MANAGEMENT (GE 404)
Lecture #10
Cash Flow Analysis
بسم الله الرحمن الرحيم
Notes: This is a title slide.

## Slide 2: Contents
Objectives of the present lecture
Introduction
Terminologies
Cash Flow: Cash in and Cash out
Most common types of construction contracts
Contract cash flow curves
Financial Charges
Simplified approach to forecast contract revenue/income curve
Simplified approach to forecast contract cost/expense curve
Problem
Further reading

## Slide 3: Objectives of the Present lecture
To discuss the fundamentals of cash flow analysis
To explain the steps involved in drawing the contract cash flow curves

## Slide 4: Introduction
As with any businesspersons, contractors are primarily concerned with making money in their businesses.
The decisions they make in preparing for and running each of their projects are inevitably related to costs and income.
The application of resources (materials, workforce, and machines) relates directly to another resource, money.
CPM provides a means for relating time and money.

## Slide 5: Terminologies
Bid: to offer to do work or provide a service for a particular price
  French firm will be bidding for the contract.
Tender: a formal offer to do work at a stated price
  A local firm submitted the lowest tender
Disbursement: the process of paying money; an amount of money paid There have been delays in the disbursement of funds
Retainage:Portion of a contract's final payment withheld by a principal (client or owner) until the project is complete in all respects
Lien: the right to keep somebody’s property until a debt is paid
Markup: an increase in the price of something based on the difference between the cost of producing it and the price it is sold at
  an average markup of 10%
  The markup on food in a restaurant is at least 100%.
Notes:   bid (for something); bid (on something) ;bid (to do something)

## Slide 6: Cash Flow
A cash flow analysis is an investigation of a project in which the focus is on the flow of money.
Thus Cash flow refers to a contractor's income and outgo of cash.
The net cash flow is the difference between cash out and income at any point in time.
A positive cash flow is when the cumulative revenues exceed the cumulative expenditures (meaning that surplus cash is available)
A negative cash flow can also occur, and this means that more money is being spent than received.
A negative cash flow will mean that the firm will need to take the appropriate steps to borrow from within the firm or financial institutions to cover the shortfall in funds.

## Slide 7: Factors that Minimize Contractor’s Negative Cash Flow
Front end rate loading: earlier items in bill of quantities carry a higher mark-up than later items. This reduces negative cash flows in contract early stages
Reduction of delays in receiving revenue
Adjustment of work schedule to late start timing
Coinciding the timing of delivery of large materials orders with the submittal of the contractor's monthly pay estimate
Delay in paying labor, plant hirers, materials suppliers, and subcontractors. This would reduce negative cash flows but undermine commercial confidence in the company
Increasing the mark-up and reducing the retentions
Increasing advance payment
Achievement of maximum production in the field
Quick settlement of claims

## Slide 8: Cash in
Owner shall make progress payments of the contract amount to the prime contractor as the work progresses
Cash in = Cash receipt = income
Principal components of cash in
Value of work actually performed in the field
Material stored on the site, but not yet incorporated into work, as well as any prefabrication or pre assembly work that the contractor may have done at some location other than the job site
A step curve is used to represent contract cash income
An income is the actual receipt of revenue.
Contract revenue and income curves

## Slide 9: Cash Out
Cash out = payment of costs = expense
An expense is the actual payment of costs.
Principal components of cash out
“Up-front" costs = initial expenses = start-up costs are costs necessary to start the project such as costs of moving in workers and equipment; erecting field offices, storage sheds, fences; job layout; installation of temporary electrical, water, telephone, sanitary, and other services; bonds; permits and project insurance.
Payment of direct job costs. These include costs associated with payrolls, materials, equipment, and subcontractor payments.
Payments for filed overhead expense and tax.
An S-curve (a smooth curve) is used to represent contract cash out.
Contract cost and expense curves

## Slide 10: Most Common Types of Construction Contracts
A construction contract is an agreement that outlines the way a construction job is executed and the specific amount of compensation for the job.
Unit price contract – This contract type is based on anticipated quantities of items which are counted in the project in addition to their unit prices. The final price of the project depends upon the quantities required to carry out the work.
  Generally, this contract is suitable only for construction and supplier projects which involve accurate identification of different types of items, but not their numbers, in the contract documents.
Lump sum contract – Under this contract type, the engineer or contractor agrees to perform the specified and described project for a fixed price. This type of contract is also referred to as a “Fixed Price Contract”.
  A Lump Sum or Fixed Price contract is appropriate where scope and schedule of the project are defined sufficiently thus allowing the contractor or engineer to estimate the costs of the project.

## Slide 11: Contd.
Cost plus contract – The cost plus contract is an agreement which involves the buyer’s consent to pay the complete cost for material and labor in addition to the amount for contractor overhead and profit.
  This contract type is favored where the scope of work is highly uncertain or indeterminate in addition to the types of labor, material, and equipment being similarly uncertain in nature.
Incentive contracts – The incentive contracts feature compensation based on the contracting and/or engineering performance in accord with an agreed target – schedule, quality, and budget.
  Incentive contracts commonly fall into one of two common categories: Fixed Price Incentive Contracts and Cost Reimbursement Incentive Contracts.
Percentage of construction contracts—This contract type is common for engineering contracts. The compensation involved in these contracts is based on a percentage of the cost of construction.

## Slide 12: Payment request for unit price contract
  The quantities of work done on unit-price contracts are determined by actual field measurement of the bid items put into place.
  The total quantity accomplished to date on each bid item is multiplied by its corresponding contract unit price.
  All of the bid items are totaled and the value of materials stored on the site as well as any prefabrication or pre assembly work that the contractor may have done at some location other than the job site is then added.
  The prescribed retainage is subtracted from this total.
  The resulting figure represents the entire amount due to the contractor for his work to date. The sum of all prior progress payments that have already been paid is then subtracted, this yielding the net amount of money payable to the contractor for his work that month.

## Slide 13: Payment request for lump sum contract
  Under lump sum contract the project is divided for payment purposes into relatively few work classifications (major job components). Contracts progress is measured in terms of estimated percentages of completion of work classifications.
  The contractor estimates the percentage completed and in place.
  The total value of each work classification is multiplied by its percent completion.
  To the total of completed work is added the value of all materials stored on the site. From this total is subtracted the retainage. This gives the total amount of money due to the contractor (up to the date of the pay request).
  Form this is subtracted the amount of progress payments already made. The resulting figure gives the net amount now payable to the contractor.

## Slide 14: Payment Request for Negotiated (e.g. Cost-Plus) Contract
  Negotiated contracts of the cost-plus variety usually provide for the contractor's submission of payment vouchers to the owner at specified intervals during the life of the contract.
  The contractor must make periodic accountings to the owner for the cost of the work, either to receive direct payment form the owner or to obtain further advances of funds.
  A common provision is weekly reimbursement of payrolls and monthly reimbursement of all other costs, including a proportion of the contractor's fee.

## Slide 15: Contract Provisions that Impact Cash in
Advanced payment
Progress payment
Materials stored on the site
Final Payment
Retention
…….

## Slide 16: Retainage or Retention
A prescribed percentage of each progress payment is usually retained by the owner in accordance with the terms of the contract
The retainage may be held by the owner until the work receives final certification by the A/E, the owner accepts the project
Final payment is then made to the contractor, including the accumulated retainage

## Slide 17: Final Payment
After the work has been finalized and all deficiencies remedied, the owner makes formal written acceptance of the project and the contractor presents his application for final payment
Under a lump-sum form of contract, the final payment is the final contract price less the total of all previous payment installments made
With a unit-price contract, the final total quantities of all payment items are measured and the exact final contract price is determined. Final payment is again equal to the contract price less the sum of all progress payments previously made
In all cases, final payment by the owner includes all retainage that has been held by him

## Slide 18: Cash Flow Forecasting
A determination of the future rates of cash outs and cash income together with their combined effect on the project cash balance is called a "cash flow forecast"
Cash flow forecasting is required to determine whether or not the funds to execute the plan are available.
Cash flow forecasting is the forecasting of both cash in and cash out of the project.
Forecast of cash flow is required:
  To determine the negative cash flow and how to cover it
  To determine the positive cash flow and how to use it (the positive cash flow of one contract may be used to handle the negative cash flow of another)

## Slide 19: Simplified Approach to Forecast Contract Cash Flow (Contract Revenue/Income Curve)
Produce an activity schedule in bar chart or time-scaled form. Determine the value/price of each activity per week
Find the monthly revenue
Adjust the revenue for advanced payment and retention
Draw cumulative adjusted revenue versus time curve
Shift the above curve by the lag between submitting payment requests and receiving revenue to get the income curve

## Slide 20: Simplified Approach to Forecast Contract Cash Flow (Contract Cost/Expense Curve)
When the mark-up is uniformly spread throughout the contract, the cost/expense curve can be derived as follows:
If the mark-up; M, is expressed as a percentage of tender price, then:
Cumulative cost = cumulative revenue × (1- M)
Draw cumulative cost versus time curve
Group cost headings that have the same payment delay between incurring the cost and making the payment
Calculate the proportion of costs due to each group
Shift the cumulative cost of each group by the specified amount to get its cumulative expense
Sum up contract cumulative expenses
Draw cumulative expense curve
Notes: incur something if you incur costs, you have to pay them
You risk incurring bank charges if you exceed your overdraft limit.

## Slide 21: Contract Cash Flow Curves
Having determined the contract cumulative income and expense curves, one can combine them on one graph to represent the contract cumulative cash flow curves
The difference between contract cumulative income and expense curves can be drawn to represent the contract cumulative net cash flow

## Slide 22: Financial Charges
The cash invested in the contract is represented by the negative area between the expense and income curves.
This area, A, can be calculated in units of “SR. weeks” if the vertical scale is in Saudi Riyal and the horizontal scale in weeks.
If the rate of investment is r% per year, then the financial charges can be calculated as follows:
Financial charges = A × r / 52
It is important to point out that if the contractor borrows the negative cash with interest, then r equals the interest rate.

## Slide 23: Note
Cost = Price × (1- M)
Price = Cost × (1+M)
Cost/Price = 1-M
Price/Cost = 1+M
M is in fraction (e.g. 20% in fraction will be 0.2)

## Slide 24: Problem-1
The following network shows the activities of small project. The activities’ durations are in weeks. The price of each activity is shown in below table.
According to contract conditions, the contractor will receive advanced payment of 20%. This will be deduced from each monthly revenue.
Applications of payments will be submitted by the contractor to the client every 4 weeks and payment will be after 2 weeks from the submission of the application.
The client will deduct 10% from each payment as retention. All retentions will be paid to the contractor with the last payment.
The ratio between project price to project cost is 1.1 (project price /project cost = 1.1). There is no delay in paying the costs by the contractor.
Calculate and draw the cash flow curves (cash-in and cash-out) based on early start time.
3

## Slide 25
∑ =161
20%*161
10%*161
(72/1.1)
32.2
32.2
(72-.1*72-.2*72)
Solution

## Slide 26
32.2
Solution
(Contd.)
To get the cost in each week distribute the monthly cost evenly over 4 weeks.
For example, Cost after 2 weeks from the start will be:
65.45/4*2=32.73.

## Slide 27: Problem-2
The actives involved in a small engineering project are given in the table. The value of the work involved in each activity is listed in the table.
The mark-up is 10% of tender value and is assumed to be uniformly distributed over the contract.
The contractor will receive an advanced payment of 10% of tender value. This will be deduced from each monthly revenue.
Retention is 5% and is paid on contract completion.
Labor cost is assumed to be 30% of total contract cost.
The delay for other payment is one month.
Revenue is received after 4 weeks from submitting invoices
Assume all the activities are scheduled on their early start timings
Derive income and expanse curve and contract cash flow curves.

## Slide 28: Solution
(24-.1×24-.0.05×
24)

## Slide 29
Sample Mid Month expense Calculations
=[(72.54-32.67)/4]×2+32.67= 52.605
=(72.54-32.67)/2+32.67= 52.605
Similarly
=(137.7-114.21)/2+114.21=125.96
Similarly
=(144-137.7)/2+137.7=140.85
Sample Cash flow Calculations:
16-6.48=9.52
16-32.67=-16.67
36.4-72.54=-36.14

## Slide 30
Sample Mid Month expense Calculations
=[(72.54-32.67)/4]×2+32.67= 52.605
=(72.54-32.67)/2+32.67= 52.605
Similarly
=(137.7-114.21)/2+114.21=125.96
Similarly
=(144-137.7)/2+137.7=140.85
Sample Cash flow Calculations:
16-6.48=9.52
16-32.67=-16.67
36.4-72.54=-36.14

## Slide 31
The following Time scaled network shows the activities of a small engineering project. The cost of each activity is shown in the table below.
H | G | F | E | D | C | B | A | Activity
15000 | 7500 | 5000 | 15000 | 5000 | 10000 | 25000 | 10000 | Total cost
The contractor will receive advance payment of 15% of the project price. This will be deducted from each monthly revenue.
Application of payment will be submitted by the contractor to the client every month and payment will be after 4 weeks from the submission of the application.
The client will deduct 5% from each payment as retention . All retention will be paid to the contractor with the final payment .
Assume the markup is 20% of the total project cost and is uniformly distributed over the work. There is no delay in paying costs by the contractor.
Calculate the cash-in and cash-out values and find maximum negative cash flow.
Problem-3
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
 | A |  |  | B |  |  | C |  |  | D |  | 
 |  |  |  |  |  | G |  |  | H |  |  | 
E |  |  |  |  | F |  |  |  |  |  |  | 

## Slide 32: Solution
Price = Cost×(1+M) ; M:markup= 20%=0.02
Total | H | G | F | E | D | C | B | A | Activity
92500 | 15000 | 7500 | 5000 | 15000 | 5000 | 10000 | 25000 | 10000 | Total cost
111000 | 18000 | 9000 | 6000 | 18000 | 6000 | 12000 | 30000 | 12000 | Revenue
Advanced payment = 0.15×111000 = 16650
Retention = 0.05×111000 = 5550

## Slide 34
Solution (contd.)

## Slide 35: Problem-4
The table below lists the cumulative monthly expenses incurred by contractors and the corresponding monthly incomes which are received from the owner of a project.
End of Month | Cumulative Expense, (1000SR) | Cumulative Income, (1000SR)
0 | 0 | 0
1 | 12 | 0
2 | 20 | 0
3 | 54 | 0
4 | 90 | 14
5 | 130 | 40
6 | 180 | 100
7 | 220 | 130
8 | 240 | 190
9 | 260 | 210
10 | 290 | 300
11 | 290 | 320
12 | 290 | 340
If the owner makes all his payments one month later than anticipated in the table above, by what percentage will the cash invested (i.e. negative area between the expense and income curves) increase?

## Slide 36: Solution
End of Month | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Total
Cumulative Expense (1000 SR) | 0 | 12 | 20 | 54 | 90 | 130 | 180 | 220 | 240 | 260 | 290 | 290 | 290 | 
Cumulative Income (1000 SR) | 0 | 0 | 0 | 0 | 14 | 40 | 100 | 130 | 190 | 210 | 300 | 320 | 340 | 
Negative Area | 0 | 6 | 16 | 37 | 72 | 96 | 115 | 100 | 100 | 60 | 65 | * | * | 667
Additional Negative Area |  |  |  |  |  | 14 | 26 | 60 | 30 | 60 | 20 | 80 |  | 290
 |  |  |  |  |  |  |  |  |  |  |  |  |  | 957
a
b
c
Sample Calculation:
=0.5(12+20)×1=16
=0.5(20+54) ×1=37
=0.5(54+90) ×1=72
=0.5(130+90) ×1-14×1=96

## Slide 37: Further Reading
Jimmie W. Hinze. “Construction Planning and Management,” Fourth Edition, 2012, Pearson.
Read more about the Cash-flow from:

## Slide 38: Thank You
Questions Please