## Slide 1: ENGINEERING MANAGEMENT (GE 404)
Lecture #12
Project Cost-Control
بسم الله الرحمن الرحيم
Notes: This is a title slide.

## Slide 2: Contents
Objectives of the present lecture
Integration of cost and schedule
Aim of project cost control system
Cost control
Three Key indicators in performance measurement
Performance equations
Cost forecasting equations
Problems
Further reading

## Slide 3: Objectives of the Present lecture
To discuss key indicators in performance measurement of a project
To learn how to estimate and forecast different types of costs

## Slide 4: Integration of Cost and Schedule
The integration of cost and schedule control systems is of natural interest to construction professionals, because the true “status” of a project can only be assessed if both cost and schedule data are examined in conjunction with one another
  Example: A project may appear to be well under budget based on the amount of money spent to date compared to what was projected. However, this figure alone could be very misleading; costs may be very low because the project is well behind the schedule.
  Thus it is necessary to know what actual project costs are relative to expected costs while knowing where the project is on a time basis.
The critical path method (CPM) system can also be used as a cost-monitoring system
In the1960s, U.S. defense agencies combined guides and requirements related to integration of cost and schedule data into a single system

## Slide 5: Aim of Project Cost Control System
To identify those work types having excessive costs and to give an indication of how serious those overruns are
To forecast the final total job cost
To indicate the trend for each cost code, that is, whether the unit cost involved has been increasing or decreasing (evaluation of the effectiveness of cost reduction efforts)
To update the database of the company that will be used to estimate future works

## Slide 6: Cost Control
The cost estimate prepared for the project during the bidding process is the basis for cost control
Cost control for an engineering project is limited to the cost of labor, equipment, materials and site overheads
Control of cost and time should be linked together

## Slide 7: Three Key Indicators in Performance Measurement
Budgeted Cost of Work Scheduled (BCWS)
Budgeted Cost of Work Performed (BCWP)
Actual Cost of Work Performed (ACWP)

## Slide 8: BCWS
BCWS is the budgeted amount of cost of the work scheduled to be accomplished in a given time period
This can be referred to as planned value of work to be accomplished [PV]

## Slide 9: BCWP
BCWP is the budgeted amount of cost for the work completed in a given time period.
This can be referred to as earned value of work accomplished [EV]
How to calculate BCWP
Budgeted cost for work performed (BCWP) = Earned value of an activity = Percent completed for the activity × the activity budget
Percent completed for an activity = [(Projected duration – Remaining duration) / Projected duration] ×100
Project Cost (SR)
BCWP
BCWS
SV=BCWP-BCWS
Time
Time Now
Schedule Variance, SV
SV>0: ahead of schedule
SV<0: behind schedule

## Slide 10: ACWP
ACWP is the amount reported as actually spent in completing the particular work accomplished within a given time period
Project Cost (SR)
ACWP
BCWP
CV=BCWP-ACWP
Time
Time Now
Cost variance, CV
CV>0: under budget
CV<0: over budget

## Slide 11
BCWP
ACWP
= 0
> 0
< 0
Under budget
Work performed cost > Actual cost
Within budget
Work performed cost = Actual cost
Over budget
Work performed cost < Actual cost
Cost Performance
BCWP
ACWP
= 0
> 0
< 0
Under run
Performed cost > Earned
on run
Performed cost = Earned
Over run
Performed cost < Earned
Cost Performance
The “Cost Overrun” curve is a plot of the calculated percent ver- or underrun at any given time.
BCWP
ACWP
= 1
> 1
< 1
Under budget
Work performed cost > Actual cost
Within budget
Work performed cost = Actual cost
Over budget
Work performed cost < Actual cost
Cost Performance
Performance Equations
Symbol | Definition | التعريف
(BCWS) [PV]” | Budgeted Cost of Work Scheduled “planned value of work to be accomplished | تكلفة موازنة للأعمال المجدولة وفقا للخطة
(BCWP) [EV] | Budgeted Cost of Work Performed “earned value of work accomplished | تكلفة موازنة لما تم من أعمال
(ACWP) [AC] | Actual Cost of Work Performed | التكلفة الفعلية لما تم من أعمال وتم دفعها
Cost Performance Index | CPI = BCWP/ACWP
Cost Variance | CV = BCWP-ACWP
% Cost Overrun/ Underrun | 
% Cost Overrun/ Underrun | 
Notes: Under run: Amount by which the actual cost is below the budgeted, estimated, original, or target cost. http://www.businessdictionary.com/definition/cost-underrun.html

## Slide 12: Performance Equations (Contd.)
BCWP
BCWS
= 1
> 1
< 1
Ahead schedule
Work performed > Work scheduled
On schedule
Work performed = Work scheduled
Behind scheduke
Work performed < Work scheduled
Schedule (Time) Performance
BCWP
BCWS
= 0
> 0
< 0
Ahead schedule
Work performed > Work scheduled
On schedule
Work performed = Work scheduled
Behind scheduke
Work performed < Work scheduled
Schedule (Time) Performance
Schedule Performance Variance | SV = BCWP-BCWS
Schedule Performance Index | SPI = BCWP/BCWS

## Slide 13: BCWP, BCWS and ACWP

## Slide 14: Cost Forecasting Equations
Estimated Cost At Completion | 
Estimate to Completion | ETC = EAC - ACWP
Budget Cost At Completion | BAC = BCWSend
Variance from original budget | VB = EAC - BAC
Or

## Slide 15: BCWS [PV], BCWP [EV], and ACWP[AC] – S-curves

## Slide 16: Contd.

## Slide 17: Problem-1
For the following network, compute the early and late start cumulative costs for the project, and draw the conclusion.
Activity | Depend on | Duration Week | ES Time | LS Time | Cost per week, SR
A |  | 2 | 0 | 0 | 400
B |  | 4 | 0 | 3 | 200
C | A | 5 | 2 | 2 | 300
D | A | 6 | 2 | 5 | 400
E | B, C | 4 | 7 | 7 | 350
F | B, C | 2 | 7 | 7 | 200
G | E | 3 | 11 | 11 | 300
H | D, F | 3 | 9 | 11 | 200

## Slide 18: Solution (Cost based on ES)

## Slide 19: Solution (Contd.) (Cost based on LS)

## Slide 20: Conclusion
Chart: Weeks
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Cumulative Cost based on ES | 600 | 1200 | 2100 | 3000 | 3700 | 4400 | 5100 | 6050 | 6600 | 7150 | 7700 | 8200 | 8500 | 8800
Cumulative Cost based on LS | 400 | 800 | 1100 | 1600 | 2100 | 3000 | 3900 | 4850 | 5800 | 6550 | 7300 | 7800 | 8300 | 8800
The above curves show that although the final cumulative cost is the same at the end of the project but the cumulative cost at the early age of project is substantially lesser in LS based schedule.

## Slide 21: Problem-2
You are required to submit a progress report to your boss about the performance of an activity of a project. The activity’s information as follow: number of units is (800); unit cost is SR 12 ; and planned productivity is 100 unit/day. Performances were measured at the end of day (3) and day (6) as follows:
Period | Cost at this period | Number of units finished
day 0 to day 3 | SR 3,600 | 250
day 4 to day 6 | SR 3,700 | 320
Calculate BCWP, ACWP, and BCWS for (i) each of the two periods (i.e. day 0 to day 3 and day 4 to day 6) and (ii) to date (i.e. day 0 to day 3 and day 0 to day 6).
Draw a graphical report for ACWP and BCWP. Also calculate estimated cost at completion and days by which activity is ahead or behind.

## Slide 22: Solution part a(i)
Summary |  |  |  |  |  |  | 
Period | BCWP | ACWP | BCWS | Variance |  | STATUS | 
 |  |  |  | Cost | Sch. | Schedule | Cost
0 - 3 | SR 3000 | SR 3600 | SR 3600 | -600 | -600 | Behind | Over Bud.
4 - 6 | SR 3840 | SR 3700 | SR 3600 | 140 | 240 | Ahead | under Bud.
SV=BCWP-BCWS
CV = BCWP-ACWP
BCWP= (250×12)=3000
BCWS= (300×12)=3600
0-3 period
ACWP= 3600 (Given)
CV = BCWP-ACWP=3000-3600=-600 (over budget)
SV = BCWP-BCWS=3000-3600=-600 (Behind schedule)
Following the above procedure the above parameters can also be estimated for 4-6 period

## Slide 23: Solution part a(ii)
To Date Summay |  |  |  |  |  |  |  |  | 
Period | BCWP | ACWP | BCWS | Variance |  | STATUS |  | Estimate at | Day ahead
 |  |  |  | Cost | Sch. | Sch. | Cost | completion | or behind
0 - 3 | SR 3000 | SR 3600 | SR 3600 | -600 | -600 | Behind | Over Bud. | SR 11,520 | 0.5
0 - 6 | SR 6840 | SR 7300 | SR 7200 | -460 | -360 | Behind | Over Bud. | SR 10,246 | 0.3
SV=BCWP-BCWS
CV = BCWP-ACWP
× BAC=3600/3000×(800×12)=11,520
No. of units behind = 300-250=50 which will require =50/100 = 0.5 day to finish
BAC =BCWSend = (800×12)
BCWP= (250×12)=3000
BCWS= (300×12)=3600
At 3rd day,
At 6th day,
× BAC=7300/6840×(800×12)=10,246
BAC =BCWSend = (800×12)
At 6th day, No. of units behind = 600-570=30 which will require =30/100 = 0.3 day to finish

## Slide 24: Solution Part (b)
b) At this rate, the contractor needs actions to reduce the cost and accelerate the time.
BCWP
ACWP

## Slide 25: Problem-3
The following time-scale diagram represents a small engineering project. The budgeted cost of each activity is shown in the table below. At the end of the 10th week, the field progress report gives you the following information:
Activity “A” was completed on schedule.
Activity “B” started as planned but it is expected to take four weeks more.
Activity “C” started as planned but finished one week later.
Percentage completion of activity “D” is 60%.
ACWP at the end of week 10 = SR 90,400
Calculate the CV, SV, BAC, EAC, ETC, and comment on the progress of the work.
Time (week) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
A (5 weeks) |  |  |  |  | B (8 weeks) |  |  |  |  |  |  |  | E (7 weeks) |  |  |  |  |  |  | F (3 weeks) |  | 
C (5weeks) |  |  |  |  | D (6 weeks) |  |  |  |  |  |  |  | G (4 weeks) |  |  |  |  |  |  |  |  | 
Activity | A | B | C | D | E | F | G
Budgeted cost (SR) | 50000 | 12000 | 16000 | 24000 | 12000 | 21000 | 20000

## Slide 26
Percentage completion of activity “A” = 100%
Projected duration of activity “B” = 8 + 4 = 12 weeks
Percentage completion of activity “B” = 5/12×100 = 41.67%
Percentage completion of activity “C” = 100%
BCWS10 = A + C + 5/8×B + 5/6×D = 50000 + 16000 + 5/8×12000 + 5/6×24000 = SR 93500 [Note: 5/8 & 5/6 represent ratio of completion of activities B&D with respect to scheduled duration]
BCWP10 = A + C + 0.4167×12000 + 0.60×24000 = SR 85400 [Note: 0.4167 & 0.6 represent ratio of completion of activities B&D with respect to actual completion duration]
CV = BCWP – ACWP = 85400 – 90400 = SR -5000 (Over Budget)
SV = BCWP – BCWS = 85400 – 93500 = SR -8100 (Behind Schedule)
BAC = 50000 + 12000 + 16000 + 24000 + 12000 + 21000 + 20000 = SR 155000
EAC = [ACWP/BCWP] ×BAC = [90400/85400] × 155000 = SR 164075
ETC = EAC – ACWP = 164075 – 90400 = SR 73675
Solution

## Slide 27: Problem-4
The following eight activities constitute an overall bar chart project that has twenty-week. Now 10 weeks finished on the project with and the project manager has the following Data:
The weekly planned percentage of completion (inside each activity bar),
The actual percentage of completion up to week 10 (in below activity bar and table),
The Budget cost of each activity (in the table),
Actual Expenses up to week 10 of each activity (in below table),
The Critical Path is A-B-C-D (Colored bar), and Total Float of each activity (dash lines)

## Slide 28: Problem-4 (contd.)
For this point in time (10 weeks after the start date):
Calculate the values of the BCWP and BCWS for each activity?
For each activity in progress, calculate the Cost and Schedule Performed Indices and state its budget and schedule status.
Draw the weekly cumulative BCWS of activity B, determine its delay/ahead week, and whether it will delay/accelerate the project or not and why.
Determine the project cost variance and state if the project is over or under budget.
Based on the performance of past 10 weeks, forecast the project completion cost at the end of the project, and its variance from original project budget.

## Slide 29: Solution
Parts (a) and (b)
Over Bud.
On Sched.
Under Bud.
On Sched.
Under Bud.
On Sched.

## Slide 30: Solution (Contd.)
0
1000
2000
3000
4000
5000
6000
7000
8000
9000
10000
11000
0
1
2
3
4
5
6
7
Week
SR
½
Week
Part (c): Cumulative BCWS of activity B with time
This activity (i.e. B) will delay the project because it is a critical activity.
Note:
The cost is cumulative
and weeks are the weeks of activity B (not the weeks of the project)
From the graph, as per schedule, SR 6000 should have been spent at the end of 4.5th week, but actually it is spent at the end of 5th week. This shows that the activity is delayed by 0.5 week.
ACWP at the end of week 10 (i.e. at the end of week 5 of activity B) = SR 6000.

## Slide 31: Solution(Contd.)
Part (d)
Project cost Variance = BCWPproject ACWPproject
= 30,70030,400 = SR 300 (under budget)
Part (e)
Budgeted Cost At Completion (BAC) =  Budget Cost = SR 54,000
Estimated Cost At Completion (EAC) = [ACWP/BCWP]×BAC = SR 53,472.3
OR
Estimated Cost At Completion (EAC) = ACWP + [(BAC – BCWP) / CPI] = SR 53,472.3
Variance from original project budget = EAC  BAC = SR -527.7 (Over Under budget)
Since EAC < BAC Project is performing under budget.

## Slide 32: Further Reading
Jimmie W. Hinze. “Construction Planning and Management,” Fourth Edition, 2012, Pearson.
Read more about the Project Cost Control from Chapter 10 of:

## Slide 33: Thank You
Questions Please