## Slide 1: ENGINEERING MANAGEMENT (GE 404)
Lecture #14
Outlines of Microsoft Project
بسم الله الرحمن الرحيم
Dr. Nadeem A. Siddiqui
Presented by
Notes: This is a title slide.

## Slide 2: Contents
Objectives of the present lecture
Basic Interface of Microsoft Project 2013
Defining Project Information and Project Properties
Creating and Assigning Calendar to the Project
Entering and Editing Project Tasks (or Activities)
Assigning, Leveling and Allocating Resources
Creating Baseline, Tracking Progress and Rescheduling Tasks
Cash Flow and Project Reports

## Slide 3: Objectives of the Present lecture
To give an outline of MS Project 2013 software
To explore the capabilities of MS Project 2013

## Slide 4: Basic Interface of MS Project
Note: The shown interface is for Microsoft Project 2010. Similar interface exists for Microsoft Project 2013

## Slide 5: Defining Project Information and Project Properties
Create a New Project:
  File→ New → Blank Project
Project Information
  Project →Properties → Project Information (Enter dates e.g. start date, finish date; status date; current date etc.)
Project Properties (e.g. Project title, Project manager etc.)
  File → Info →Project Information → Advanced Properties
To set ES or LS based schedule
  Schedule From → Project start date (all tasks begin on ES i.e. as soon as possible)
  Schedule From → Project Finish date (all tasks begin on LS i.e. as late as possible)

## Slide 6: Creating and Assigning Calendar to the Project
Create New Calendar
  Project → Change working time →Create New calendar
  Work Weeks →Details →Set days to working times (or Set days to nonworking time)
  To Set Working Time: Enter the working time e.g. : 8:00 AM – 12:00 PM; 1:00 PM-5:00 PM
Assign ‘new calendar’ to the Project
  Project → Properties → Project Information →Calendar (Select the defined calendar)

## Slide 7: Entering and Editing Project Tasks (or Activities)
Entering tasks
  Task →Gantt Chart → Gantt Chart or Task sheet (Enter the tasks)
Organizing tasks into phases
  In the entered tasks use indent to create phases
Adding a recurring tasks
  Task →Insert → +Task → Recurring task
Displaying WBS Codes
  In the work sheet add new Column → Select the Name → WBS

## Slide 8: Contd.
Defining predecessors
  In a cell of Predecessor column→ Right click → Information→ Predecessors →Enter Task ID, Type and Lag
Splitting tasks
  Task →Schedule → Split task
Setting task constraints
  In a cell→ Right click → Information→ Advanced →Enter constraint information
Setting milestones
  Enter in the worksheet a task with zero duration

## Slide 9: Precedence Diagram and Critical Tasks
Seeing Critical Tasks
  Task →view → Gantt Chart → Format →Critical Tasks
To see Total slack and/or Free slack
  In a work sheet select new column and in the top cell (click twice)→Total Slack
To see Network diagram
  Task →view → Gantt Chart → Network Diagram
To Print Network diagram
  File→ Print→ Page setup →Fit to 1 pages wide by 1 tall →Print

## Slide 10: Assigning, Leveling and Allocating Resources
Adding Resources
  View → Resource views→ Resource Sheet (Enter resource Name, Type Cost (rate /hour or /day) etc.)
Assigning resources to tasks
  View → Gantt Chart →Go to Resource names → Right click to go to Information →Enter the resources
  To not have leveling during assigning resources go to resource tab and clear leveling
View the resource Graph
  View → Other views →Resource Graph
Resource leveling and allocation
    Resource →Level → Leveling Options →(To perform leveling without effecting the project duration, select “level only within the available slack”)
  Resource → Level → Level Resource → Level Now

## Slide 11: Creating Baseline, Tracking Progress and Rescheduling Tasks
To compare how project is changing over time Baselines are set
  Project→ Schedule → Set Baseline
To see the variance with respect to Baseline
  View→ Data → Tables →Variance
Tracking a Project as scheduled
  Add one column in task sheet to show % complete
  Project→ Status → Status Date
  Project→ Status → Update Project
Entering actual values for tasks
  View→ Data → Tables →Work
Rescheduling uncompleted Tasks
  Project→ Status → Update Project → Reschedule uncompleted work to start after

## Slide 12: Cash Flow and Project Reports
  To view reports
    Report→ View Reports →Costs →Cash Flow
  To print the report
    File→ Print → Print Entire Project

## Slide 13: Thank You
Questions Please