## Slide 1: ENGINEERING MANAGEMENT (GE 404)
Lecture #6
Time-Scaled Diagram and Resource Leveling
بسم الله الرحمن الرحيم
Notes: This is a title slide.

## Slide 2: Contents
Objectives of the present lecture
Time Scale Network
Advantages and Disadvantages
Management of Resources—Resource Leveling
Resource Leveling (Smoothing) Procedures
Burgess Leveling Procedure
Estimated Method
Problems
Further reading

## Slide 3: Objectives of the Present lecture
To discuss steps involved in drawing the Time-scaled network diagrams
To discuss how to carry out resource leveling using time-scaled diagrams

## Slide 4: Time-Scaled Networks
Time-scaled networks are merely extension of bar charts
Each activity is shown as a one dimensional line rather than as a two dimensional box
The horizontal length is equal to its estimated time duration (beginning at its ES and ending with its EF values)
Vertical solid (or dashed) lines indicate sequential dependence of one activity on another
Float times are shown as horizontal dashed lines

## Slide 5: Free and Total Floats
Free Float or activity Float
Total Float or Path Float
  Free float is the amount of time that an activity’s completion time may be delayed without affecting the earliest start of succeeding activity
Free float is “owned” by an individual activity
Total float is the amount of time that an activity’s completion may be delayed without affecting the earliest start of any activity on the network critical path
Total float is shared by all activities along a slack path
Total path float time for activity (i-j) is the total float associated with a path

## Slide 6: Advantages and Disadvantages
Advantages
Very suitable device for checking daily project needs of different resources, and for the advance detection of conflicting demands among activities for the same resource
Useful for project financial management applications
Disadvantages
Because it is drawn by manual drafting methods, the level of effort needed to modify and update them is very large
Dependencies among activities are not always so obvious as they are on the activity on node network.

## Slide 7: Problem-1
The following activity list represents the job logic and the durations of activities for a market survey project. Draw a time- scaled network for the project, determine project time and calculate the activities float times.
Activity | Description | predecessors | Duration, week
A | Plan survey | — | 1
B | Hire personnel | A | 1
C | Design questionnaire | A | 3
D | Train personnel | B, C | 2
E | Select samples of customers | C | 1
F | Print questionnaire | C | 1
G | Conduct survey | D,E,F | 3
H | Analyze results | G | 2

## Slide 8: Solution
Project completion time = 11 working days
Critical Path: A-C-D-G-H.
Activity | A | B | C | D | E | F | G | H
Total float | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0
Free float | 0 | 2 | 0 | 0 | 1 | 1 | 0 | 0
Notes: Find the critical path by making a rough sketch of activities (with due care of logic) and then see the longest path.

## Slide 9: Management of Resources—Resource Leveling
Resource leveling is a technique to reduce the amount of variability (peak and valley) in the pattern of resource usage (manpower, equipment, or money) over the project duration.
Resource leveling ensures that resource demand does not exceed resource availability.
Main Aspects:
  Sufficient total resources are available
  Project must be completed by a specified due date, in other words, project duration is not allowed to increase

## Slide 10: Contd.
  Improvements can be made to the level of resource requirements by:
  Delaying or bringing forward the start of certain activities
  Extending the duration of certain activities and so reducing the demand for resources over the duration of the activity or by a combination of both of these adjustments
  Note: Time-scale network or bar chart is generally used for resource leveling. The reason for this is that resource leveling must be considered within a time framework and Time-scale network or bar charts are drawn to a time scale while other networks (e.g. AON etc.) are not.

## Slide 11: Resource Leveling (Smoothing) Procedures
Although the sum of daily resource requirements over the project duration is constant, but the sum of the squares of the daily requirements decreases as the peaks and valleys are leveled.
Burgess method utilizes a simple measure of effectiveness given by the Sum of the squares of the resource requirements for each “day” (period). This value reaches a minimum for a schedule that is level and equals
Note: R in the figure is the same as DR in the equation

## Slide 12: Burgess Leveling Procedure (Steps 1-4)
List the project activities in order of precedence. Add to this listing the duration, early start, and float (slack) values for each activity
Starting with the last activity, schedule it period by period to give the lowest sum of squares of resource requirements for each time unit. If more than one schedule gives the same total sum of squares, then schedule the activity as late as possible to get as much slack as possible in all preceding activities.
Holding the last activity fixed, repeat Step 2 on the next to the last activity in the network, taking advantage of any slack that may have been made available to it by the rescheduling in Step 2.
Continue Step 3 until the first activity in the list has been considered; this completes the first rescheduling cycle.

## Slide 13: Burgess Leveling Procedure (Steps 5-8)
Carry out additional rescheduling cycles by repeating Steps 2 through 4 until no further reduction in the total sum of squares of resource requirements is possible, noting that only movement of an activity to the right (schedule later) is permissible under this scheme.
If this resource is particularly critical, repeat Steps 1 through 5 on a different ordering of the activities. which, of course, must still list the activities in order of precedence.
Choose the best schedule of those obtained in Steps 5 and 6.
Make final adjustments to the schedule chosen in Step 7, taking into account factors not considered in the basic scheduling procedure.

## Slide 14: Problem-2
Time-scaled network is given below with the resource demands of each activity on each day. Using Burgess leveling procedure, level the resources.

## Slide 15: Solution
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 
 |  | A |  |  |  | C |  |  |  |  | I |  |  | J |  |  | K |  | 
 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 5 | 5 | 5 | 
 |  |  |  | D |  |  | E |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | 4 | 4 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  | F |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |  | 
 |  |  | B |  |  |  | G |  |  |  |  | H |  |  |  |  |  |  | 
 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 |  |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 9 | 9 | 9 | 6 | 5 | 5 | 5 | 5 | 6 | 4 | 5 | 5 | 5 | 
ΣR | 5 | 10 | 15 | 24 | 33 | 42 | 51 | 60 | 66 | 71 | 76 | 81 | 86 | 92 | 96 | 101 | 106 | 111 | 

## Slide 16: 1st Trial with activity H
Start with Delay activity “H” one period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 
 |  | A |  |  |  | C |  |  |  |  | I |  |  | J |  |  | K |  | 
 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 5 | 5 | 5 | 
 |  |  |  | D |  |  | E |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | 4 | 4 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  | F |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |  | 
 |  |  | B |  |  |  | G |  |  |  |  |  | H |  |  |  |  |  | 
 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 |  | 2 | 2 | 2 | 2 | 2 |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 9 | 9 | 9 | 6 | 3 | 5 | 5 | 5 | 6 | 6 | 5 | 5 | 5 | 
R2 | 25 | 25 | 25 | 81 | 81 | 81 | 81 | 81 | 36 | 9 | 25 | 25 | 25 | 36 | 36 | 25 | 25 | 25 | 
Delay activity “H” one period   R2 = 747

## Slide 17: 2nd Trial with activity H
Start with Delay activity “H” two periods
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 
 |  | A |  |  |  | C |  |  |  |  | I |  |  | J |  |  | K |  | 
 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 5 | 5 | 5 | 
 |  |  |  | D |  |  | E |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | 4 | 4 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  | F |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |  | 
 |  |  | B |  |  |  | G |  |  |  |  |  |  | H |  |  |  |  | 
 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 9 | 9 | 9 | 6 | 3 | 3 | 5 | 5 | 6 | 6 | 7 | 5 | 5 | 
R2 | 25 | 25 | 25 | 81 | 81 | 81 | 81 | 81 | 36 | 9 | 9 | 25 | 25 | 36 | 36 | 49 | 25 | 25 | 
Delay activity “H” 2 periods   R2 = 755

## Slide 18: 3rd Trial with activity H
Start with Delay activity “H” three periods
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 
 |  | A |  |  |  | C |  |  |  |  | I |  |  | J |  |  | K |  | 
 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 5 | 5 | 5 | 
 |  |  |  | D |  |  | E |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | 4 | 4 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  | F |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |  | 
 |  |  | B |  |  |  | G |  |  |  |  |  |  |  | H |  |  |  | 
 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 |  |  |  | 2 | 2 | 2 | 2 | 2 |  | 
R | 5 | 5 | 5 | 9 | 9 | 9 | 9 | 9 | 6 | 3 | 3 | 3 | 5 | 6 | 6 | 7 | 7 | 5 | 
R2 | 25 | 25 | 25 | 81 | 81 | 81 | 81 | 81 | 36 | 9 | 9 | 9 | 25 | 36 | 36 | 49 | 49 | 25 | 
Delay activity “H” 3 periods   R2 = 763

## Slide 19: 4th Trial with activity H
Start with Delay activity “H” four periods
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 
 |  | A |  |  |  | C |  |  |  |  | I |  |  | J |  |  | K |  | 
 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 5 | 5 | 5 | 
 |  |  |  | D |  |  | E |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | 4 | 4 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  | F |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |  | 
 |  |  | B |  |  |  | G |  |  |  |  |  |  |  |  | H |  |  | 
 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 
R | 5 | 5 | 5 | 9 | 9 | 9 | 9 | 9 | 6 | 3 | 3 | 3 | 3 | 6 | 6 | 7 | 7 | 7 | 
R2 | 25 | 25 | 25 | 81 | 81 | 81 | 81 | 81 | 36 | 9 | 9 | 9 | 9 | 36 | 36 | 49 | 49 | 49 | 
Delay activity “H” 4 periods   R2 = 771
Hence,  Lowest  R2 = 747 with Delay activity “H” 1 period

## Slide 20: Conclusion at the end of trials with activity H
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 
 |  | A |  |  |  | C |  |  |  |  | I |  |  | J |  |  | K |  | 
 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 5 | 5 | 5 | 
 |  |  |  | D |  |  | E |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | 4 | 4 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  | F |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |  | 
 |  |  | B |  |  |  | G |  |  |  |  |  | H |  |  |  |  |  | 
 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 |  | 2 | 2 | 2 | 2 | 2 |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 9 | 9 | 9 | 6 | 3 | 5 | 5 | 5 | 6 | 6 | 5 | 5 | 5 | 
R2 | 25 | 25 | 25 | 81 | 81 | 81 | 81 | 81 | 36 | 9 | 25 | 25 | 25 | 36 | 36 | 25 | 25 | 25 | 
The result = Delay activity “H” one period   R2 = 747

## Slide 21: Trial with activity G
Start Delay activity “G” 1 period
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 
 |  | A |  |  |  | C |  |  |  |  | I |  |  | J |  |  | K |  | 
 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 5 | 5 | 5 | 
 |  |  |  | D |  |  | E |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | 4 | 4 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  | F |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |  | 
 |  |  | B |  |  |  |  | G |  |  |  |  | H |  |  |  |  |  | 
 | 2 | 2 | 2 | 2 | 2 |  | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 |  |  |  | 
R | 5 | 5 | 5 | 9 | 9 | 6 | 9 | 9 | 6 | 6 | 5 | 5 | 5 | 6 | 6 | 5 | 5 | 5 | 
R2 | 25 | 25 | 25 | 81 | 81 | 36 | 81 | 81 | 36 | 36 | 25 | 25 | 25 | 36 | 36 | 25 | 25 | 25 | 
Delay activity “H” one period & Delay activity “G” one period   R2 = 729

## Slide 22: Contd.
Continue Delay activities of non critical
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 
 |  | A |  |  |  | C |  |  |  |  | I |  |  | J |  |  | K |  | 
 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 5 | 5 | 5 | 
 |  |  |  |  |  | D |  |  |  |  |  | E |  |  |  |  |  |  | 
 |  |  |  |  |  | 4 | 4 |  |  |  | 2 | 2 | 2 |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | F |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  |  |  |  |  | 
 |  |  | B |  |  |  |  | G |  |  |  |  | H |  |  |  |  |  | 
 | 2 | 2 | 2 | 2 | 2 |  | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 |  |  |  | 
R | 5 | 5 | 5 | 5 | 5 | 7 | 10 | 7 | 7 | 7 | 7 | 7 | 7 | 6 | 6 | 5 | 5 | 5 | 
R2 | 25 | 25 | 25 | 25 | 25 | 49 | 100 | 49 | 49 | 49 | 49 | 49 | 49 | 36 | 36 | 25 | 25 | 25 | 
Delay activity “H” 1 period, Delay activity “G” 1 period, Delay activity “F” 2 periods, Delay activity “E” 5 periods, and Delay activity “D” 2 periods   R2 = 715

## Slide 23: Summary
Sequence of major moves of the first rescheduling cycle:
Delay activity “H” one period  R2 = 747
Delay activity “G” one period  R2 = 729
Delay activity “F” two periods  R2 = 727
Delay activity “E” five periods  R2 = 723
Delay activity “D” two periods  R2 = 715
Thus by delaying activities as given above (simultaneously) leads to the most levelled resources.

## Slide 24: Shortcomings of Burgess leveling procedure
The disadvantage of this approach is that a resource buildup occurs at the end of the project.
The procedure does not position activities in a way so as to obtain an optimum solution, although this happen by chance.
To get the optimum solution, alternate schedules have to be obtained using a different order of activities for shifting.
The number of these alternate schedules will be large even for small projects rendering the approach an impractical one.

## Slide 25: Estimated Method
Step 1: Draw the network in a time scaled diagram using the early start schedule method
Step 2: Perform resource loading for the activities and calculate the total number of resources at each period
Step 3: Reschedule non-critical activities to reduce peaks and to smooth resource usage in the resource loading chart in order to minimize Ri2, where Ri is the number of resource usage in the resource loading chart
Step 4: Continue Step 3 until you reach the schedule of having minimum value of Ri2

## Slide 26
Problem-3
Time-scaled network is given below with the resource demands of each activity on each day. Using Estimated method of leveling procedure, level the resources.

## Slide 27: Trial-1
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 
 |  | A |  |  |  | C |  |  |  |  | I |  |  | J |  |  | K |  | 
 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 5 | 5 | 5 | 
 |  |  |  | D |  |  | E |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | 4 | 4 | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  | F |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |  | 
 |  |  | B |  |  |  |  |  |  |  | G |  |  |  |  | H |  |  | 
 | 2 | 2 | 2 | 2 | 2 |  |  |  |  | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 
R | 5 | 5 | 5 | 9 | 9 | 6 | 6 | 6 | 3 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 
R2 | 25 | 25 | 25 | 81 | 81 | 36 | 36 | 36 | 9 | 36 | 36 | 36 | 36 | 36 | 36 | 49 | 49 | 49 | 
Delay activity “H” 4 periods & Delay activity “G” 4 period  R2 = 717

## Slide 28: Trial-2
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 
 |  | A |  |  |  | C |  |  |  |  | I |  |  | J |  |  | K |  | 
 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 5 | 5 | 5 | 
 |  |  |  |  |  | D |  |  | E |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 4 | 4 | 2 | 2 | 2 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  | F |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  |  |  |  |  | 
 |  |  | B |  |  |  |  |  |  |  | G |  |  |  |  | H |  |  | 
 | 2 | 2 | 2 | 2 | 2 |  |  |  |  | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 
R | 5 | 5 | 5 | 5 | 5 | 7 | 7 | 6 | 6 | 9 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 
R2 | 25 | 25 | 25 | 25 | 25 | 49 | 49 | 36 | 36 | 81 | 36 | 36 | 36 | 36 | 36 | 49 | 49 | 49 | 
Delay activity “H” 4 periods, Delay activity “G” 4 periods, Delay activity “E” 2 periods, Delay activity “F” 2 periods, and Delay activity “D” 2 periods
 R2 = 703

## Slide 29: Other Trials
Time | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 
 |  | A |  |  |  | C |  |  |  |  | I |  |  | J |  |  | K |  | 
 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 5 | 5 | 5 | 
 |  |  |  |  |  | D |  |  | E |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  | 4 | 4 | 2 | 2 | 2 |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  | F |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  | 1 | 1 | 1 |  |  |  |  |  | 
 |  |  | B |  |  |  |  |  |  |  | G |  |  |  |  | H |  |  | 
 | 2 | 2 | 2 | 2 | 2 |  |  |  |  | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 
R | 5 | 5 | 5 | 5 | 5 | 7 | 7 | 5 | 5 | 8 | 7 | 7 | 7 | 6 | 6 | 7 | 7 | 7 | 
R2 | 25 | 50 | 75 | 100 | 125 | 174 | 223 | 248 | 273 | 337 | 386 | 435 | 484 | 520 | 556 | 605 | 654 | 703 | 
Delay activity “H” 4 periods, Delay activity “G” 4 periods, Delay activity “F” 5 periods, Delay activity “E” 2 periods, and Delay activity “D” 2 periods
 R2 = 703
Thus by delaying activities as given above (simultaneously) leads to the most levelled resources.

## Slide 30: Problem-4
Data for small project is listed below:
Activity | Depends on | Duration | Resource Rate | Activity | Depends on | Duration | Resource Rate
A |  | 2 | 4 | F | D | 2 | 2
B |  | 1 | 2 | G | D | 1 | 1
C | A | 1 | 2 | E | D | 1 | 1
D | B, C | 4 | 6 |  |  |  | 
1. Draw Early Start Time-scaled schedule and calculate the corresponding used resource.
2. Perform 2 trials Resource Leveling. Also, specify which one of the two trials Time-scaled schedules is the final schedule and why.

## Slide 31: Solution

## Slide 32: Trial-1

## Slide 33: Trial-2
The 2nd trial schedule is the best Resource Leveling result because it has lowest R2.

## Slide 34: Cumulative Resource Requirement Curve
Cumulative resource requirement curve (S-curve) may be used for:
Planning and Control of progress
Preliminary resource allocation

## Slide 35: Resource leveling and allocation measures

## Slide 36: Significance of Resource Criticality Index
Higher values of resource criticality index are associated with the most critical (i.e., most tightly constrained) resources.
Values of resource criticality index significantly below 1.0 typically are associated with non-constraining resources.
Values around and above 1.0 indicate that project delays (beyond the original critical path duration) will be encountered.

## Slide 37: Problem-5
For a small Engineering project listed below:
a) Draw the Early Start and Late start project schedule using Time- scaled network.
b) Within only two trials, level the project Resource.
c) How many Worker(s)/day you should use in this project?
Activity | Depends on | Time, day | Resource, Worker/day
A | None | 4 | 2
B | A | 6 | 3
C | B | 7 | 3
D | C, G | 3 | 4
E | None | 3 | 3
F | A, E | 4 | 2
G | F | 4 | 2
H | None | 1 | 3
I | H | 5 | 2

## Slide 38: Solution (a) ES Time Scaled Network
 | Earlest Start project schedule using Time- scaled network |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
R | 8 | 7 | 7 | 4 | 7 | 7 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 
∑R | 8 | 15 | 22 | 26 | 33 | 40 | 45 | 50 | 55 | 60 | 65 | 70 | 73 | 76 | 79 | 82 | 85 | 89 | 93 | 97 | 
R2 | 64 | 49 | 49 | 16 | 49 | 49 | 25 | 25 | 25 | 25 | 25 | 25 | 9 | 9 | 9 | 9 | 9 | 16 | 16 | 16 | 
∑R2 | 64 | 113 | 162 | 178 | 227 | 276 | 301 | 326 | 351 | 376 | 401 | 426 | 435 | 444 | 453 | 462 | 471 | 487 | 503 | 519 | 
A
R2
B
R3
C
R3
D
R4
E
R3
F
R2
G
R2
I
R2
H
R3

## Slide 39: Contd.(a) LS Time Scaled Network
 | Latest Start project schedule using Time- scaled network |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
R | 2 | 2 | 2 | 2 | 3 | 3 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 8 | 7 | 7 | 6 | 6 | 6 | 
∑R | 2 | 4 | 6 | 8 | 11 | 14 | 20 | 26 | 32 | 37 | 42 | 47 | 52 | 57 | 65 | 72 | 79 | 85 | 91 | 97 | 
R2 | 4 | 4 | 4 | 4 | 9 | 9 | 36 | 36 | 36 | 25 | 25 | 25 | 25 | 25 | 64 | 49 | 49 | 36 | 36 | 36 | 
∑R2 | 4 | 8 | 12 | 16 | 25 | 34 | 70 | 106 | 142 | 167 | 192 | 217 | 242 | 267 | 331 | 380 | 429 | 465 | 501 | 537 | 
A
R2
B
R3
C
R3
D
R4
E
R3
F
R2
G
R2
I
R2
H
R3
Notes: Draw LS Time-scaled network with the help of ES time-scaled network by exhausting all floats.

## Slide 40: Solution (b) 1st Trial for resource leveling
 | step 1- moving task H to start end of 3rd period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
R | 5 | 5 | 5 | 5 | 7 | 7 | 7 | 7 | 7 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 
∑R | 5 | 10 | 15 | 20 | 27 | 34 | 41 | 48 | 55 | 60 | 65 | 70 | 73 | 76 | 79 | 82 | 85 | 89 | 93 | 97 | 
R2 | 25 | 25 | 25 | 25 | 49 | 49 | 49 | 49 | 49 | 25 | 25 | 25 | 9 | 9 | 9 | 9 | 9 | 16 | 16 | 16 | 
∑R2 | 25 | 50 | 75 | 100 | 149 | 198 | 247 | 296 | 345 | 370 | 395 | 420 | 429 | 438 | 447 | 456 | 465 | 481 | 497 | 513 | 
A
R2
B
R3
C
R3
D
R4
E
R3
F
R2
G
R2
I
R2
H
R3

## Slide 41: Contd.(b) 2nd Trial for Resource Leveling
 | step 2- moving task I to start end of 12th period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
R | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 
∑R | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50 | 55 | 60 | 65 | 70 | 75 | 80 | 85 | 89 | 93 | 97 | 
R2 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 16 | 16 | 16 | 
∑R2 | 25 | 50 | 75 | 100 | 125 | 150 | 175 | 200 | 225 | 250 | 275 | 300 | 325 | 350 | 375 | 400 | 425 | 441 | 457 | 473 | 
A
R2
B
R3
C
R3
D
R4
E
R3
F
R2
G
R2
I
R2
H
R3

## Slide 42: Leveling Result and Solution of part (c)
Resource requirement
The levelling result clearly indicates that 5 worker(s)/day will be enough for this project.

## Slide 43: Further Reading
Jimmie W. Hinze. “Construction Planning and Management,” Fourth Edition, 2012, Pearson.
Read more about the resource leveling from:

## Slide 44: Thank You
Questions Please