## Slide 1: What is Project Management?
A project is an interrelated set of activities that has a definite starting and ending point and that results in a unique product. (service)
Management is generally perceived as concerned with planning, organizing, and control of an ongoing process or activity.
Project management is concerned with control of an important activity for a relatively short period of time after which management effort ends.
Jul 31, 2026
Dr.Bokkasam Sasidhar
Notes: <number>

## Slide 2: Process vs. Project Work
Project
Take place outside the normal, process-oriented world
Unique and separate from routine, process-driven work
Continually evolving
Process
Ongoing, day-to-day activities to produce goods and services
Use existing systems, properties, and capabilities
Typically repetitive
A project is a temporary endeavor undertaken to create a unique product or service.
Notes: <number>

## Slide 3: Additional Definitions
A project is a unique venture with a beginning and an end, conducted by people to meet established goals within parameters of cost, schedule, and quality. Buchanan & Boddy 92
Projects are goal-oriented, involve the coordinated undertaking of interrelated activities, are of finite duration, and are all, to a degree unique. Frame 95

## Slide 4: Project Definitions Summarized
A project can be considered any series of activities and tasks that have:
Specific objectives to be completed within certain specifications,
Defined start and end dates,
Funding limits,
Human and nonhuman resources, and
Multifunctional focus.

## Slide 5: Characteristics of Project
A one-time focus
A specific purpose and a desired result
A start and a finish
A time frame for completion
A limited set of resources
A logical sequence of interdependent activities
A clear user(customer, client) of the result
Jul 31, 2026
Dr.Bokkasam Sasidhar
Notes: <number>

## Slide 6: Elements of Project Planning
Define project objective(s)
Identify activities
Establish precedence relationships
Make time estimates
Determine project completion time
Compare project schedule objectives
Determine resource requirements to meet objective
Jul 31, 2026
Dr.Bokkasam Sasidhar
Notes: <number>

## Slide 7: Project Success Rates
Software & hardware projects fail at a 65% rate,
Over half of all IT projects become runaways,
Only 30% of technology-based projects and programs are a success.
Only 2.5% of global businesses achieve 100% project success and over 50% of global business projects fail,
Average success of business-critical application development projects is 32%, and
Approximately 42% of the 1,200 Iraq reconstruction projects were eventually terminated due to mismanagement or shoddy construction
Notes: <number>

## Slide 8
Project team typically consists of a group of individuals from various areas in an organization and often includes outside consultants.
Members of engineering staff often assigned to project work.
Project team may include workers.
Most important member of project team is the project manager.
Project manager is often under great pressure because of uncertainty inherent in project activities and possibility of failure. Potential rewards, however, can be substantial.
Project manager must be able to coordinate various skills of team members into a single focused effort.
The Project Team
Jul 31, 2026
Dr.Bokkasam Sasidhar
Notes: <number>

## Slide 9: Project Manager Responsibilities
Selecting a team
Developing project objectives and a plan for execution
Performing risk management activities
Cost estimating and budgeting
Scheduling
Managing resources

## Slide 10: Steps in Managing a Project
Define the problem
Develop solution options
Plan the Project : what must be done ?, who will do it?, How will it be done ?
How much will it cost? ,what do we need to do?
Execute the plan
Monitor & Control Progress
Close Project
What was done well?
What should be improved?
Steps in Managing a Project
Jul 31, 2026
Dr.Bokkasam Sasidhar

## Slide 11: Project Life Cycles
Man Hours
Conceptualization
Planning
Execution
Termination
Project Life Cycle Stages
Notes: <number>

## Slide 12
Jul 31, 2026
Dr.Bokkasam Sasidhar
Project Life Cycle

## Slide 13: Project Life Cycle
Jul 31, 2026
Dr.Bokkasam Sasidhar

## Slide 14: Project Life Cycles and Their Effects
Project Life Cycles and Their Effects
Notes: <number>

## Slide 15: Elements of Project Management Work Breakdown Structure (WBS)
WBS breaks down project into major components (modules).
Modules are further broken down into subcomponents, components, activities, and finally, into individual tasks.
Identifies activities, tasks, resource requirements and relationships between modules and activities.
Helps avoid duplication of effort.
Basis for project development, management , schedule resources and modifications.
Approaches for WBS development:
1. Top down process 2. Brainstorm entire project
Jul 31, 2026
Dr.Bokkasam Sasidhar
Notes: <number>

## Slide 16: Work Breakdown Structure
Jul 31, 2026
Dr.Bokkasam Sasidhar

## Slide 17
A Work Breakdown Structure (three levels) for a new business

## Slide 18
WBS for computerized order-processing system project
Elements of Project Management Work Breakdown Structure
Notes: <number>

## Slide 19
Elements of Project Management
Project Scheduling
Project schedule evolves from planning documents, with focus on timely completion.
Critical element in project management – source of most conflicts and problems.
Schedule development steps:
1. Define activities, 2. Sequence activities,
3. Estimate activity times, 4. Develop schedule.
Gantt chart and CPM/PERT techniques can be useful.
Computer software packages available, e.g. QM for Windows, Microsoft Project.
Jul 31, 2026
Dr.Bokkasam Sasidhar

## Slide 20
Elements of Project Management
Gantt Chart
Popular, traditional technique, also known as a bar chart -developed by Henry Gantt (1914).
Direct precursor of CPM/PERT for monitoring work progress.
A visual display of project schedule showing activity start and finish times and where extra time is available.
Suitable for projects with few activities and precedence relationships.
Drawback: precedence relationships are not always discernible which limits chart’s use for smaller projects
Jul 31, 2026
Dr.Bokkasam Sasidhar

## Slide 21
Gantt Chart
Visual scheduling tool
Graphical representation of information
Show dependencies between tasks, personnel, and other resources allocations
Track progress towards completion
Jul 31, 2026
Dr.Bokkasam Sasidhar

## Slide 22
Building a Gantt Chart
List all tasks and milestones from the project along the vertical axis
List time frame along the horizontal axis
Activity 1
Activity 2
Milestone
Time Frame: day 1 day 2 day3
Jul 31, 2026
Dr.Bokkasam Sasidhar

## Slide 23
Building a Gantt Chart
Activities: Create box the length of each activity time duration
  E.g., activity one is scheduled from day1-day3
Activity 1
Activity 2
Time Frame: day 1 day 2 day3
Jul 31, 2026
Dr.Bokkasam Sasidhar

## Slide 24
Building a Gantt Chart
Dependencies: Show dependencies between activities with arrows
  E.g., activity 2 cannot start until activity 1 is complete
Activity 1
Activity 2
Time Frame: day 1 day 2 day3…
Jul 31, 2026
Dr.Bokkasam Sasidhar

## Slide 25: Sequence of Activities of The Project - House Building
Number | Activity | Predecessor | Duration
1 | Design house and obtain financing | -- | 3 months
2 | Lay foundation | 1 | 2 months
3 | Order and receive materials | 1 | 1 month
4 | Build house | 2,3 | 3 months
5 | Select paint | 2, 3 | 1 month
6 | Select carper | 5 | 1 month
7 | Finish work | 4, 6 | 1 month
Jul 31, 2026
Dr.Bokkasam Sasidhar

## Slide 26
Gantt Chart for House Building Project
A Gantt chart
Jul 31, 2026
Dr.Bokkasam Sasidhar

## Slide 27
Jul 31, 2026
Dr.Bokkasam Sasidhar
Gantt Chart for House Building Project using QM for Windows

## Slide 28: Gantt Charts
Establish a time-phased network
Can be used as a tracking tool
Benefits of Gantt charts
Easy to create and comprehend
Identify the schedule baseline network
Allow for updating and control
Identify resource needs

## Slide 29: Gantt Charts – Example
Consider the Gantt chart shown below where the time scale is in minutes and all activities are performed on an early start basis. How much slack is available in the project?
Answer: Nil
Jul 31, 2026
Dr.Bokkasam Sasidhar

## Slide 30: Gantt Charts – Resource Allocation Example
Use the Gantt chart and the activity list to determine when resource 5 is free.
Jul 31, 2026
Dr.Bokkasam Sasidhar
Activity | Resources | Activity | Resources
A | 1 | F | 1
B | 5 | G | 2
C | 4 | H | 5
D | 3 | J | 3
E | 2 | K | 4
A) between 0 and 15
B) between 15 and 30
C) between 30 and 45
D) between 45 and 60
Answer: D

## Slide 31: Gantt Charts – Resource Allocation Example
Use the Gantt chart and the activity list to determine when resource 2 is free.
Jul 31, 2026
Dr.Bokkasam Sasidhar
Activity | Resources | Activity | Resources
A | 1 | F | 1
B | 5 | G | 2
C | 4 | H | 5
D | 3 | J | 3
E | 2 | K | 2
A) between 0 and 15
B) between 15 and 30
C) between 30 and 45
D) between 45 and 60
Answer: A