IS –351 Project Management

Tutorial  # 1

##### Introduction to Project Management

# Objectives:

- Learn what is project management

- Learn how MS Project helps in managing projects

- Learn how to create a new project using MS Project

- Introduction to Project Management

Project management is nothing more than a system for managing tasks, resources, and costs efficiently. A good system can help you improve communication and coordination and reduce the overall amount of time you spend managing projects.

1.1 Definitions

Task

- The actual work that needs to be accomplished to meet your project goals can be broken into tasks.

- For example, painting museum walls and hanging clocks are tasks that, when combined with other tasks, result in the completion of a clockwork exhibit.

###### Resources

- A resource is usually a person, but it can also be a piece of equipment, materials, services, or even a room — whatever is required to complete a task.

- The amount of resources you have can affect the project scope and the time it takes to complete a project.

###### Assignments

- When you assign a resource to work on a task, you have made an assignment.

- Assignments directly affect the amount of time required to complete a task and, indirectly, the total project time.

###### Goals

- The specific results you want your project to accomplish are your project’s goals. They define your project’s purpose.

###### Scope

- The combination of all project goals plus the work required to accomplish those goals represents the scope of your project.

- It is the sum of all the individual, concrete tasks that your team must do.

- In the clockwork exhibit project, for example, scope could include tasks such as painting the galleries in which the clocks will be displayed, hanging 75 clocks, and writing brochures to advertise the exhibit. Under severe deadline pressure, the clockwork project manager might cut the scope by hanging fewer clocks — and painting fewer galleries — than had originally been planned.

###### Assumptions

- Your best guesses as to how various relevant factors are likely to affect the duration and cost of specific tasks, and of the project as a whole, are your project assumptions.

- For example, the clockwork project manager might assume that all the exhibit designers will be available for the month scheduled to complete the exhibit design. But if half the team were to come down with the flu for a week or be assigned to another project, that assumption would be false and either the project scope or schedule would have to be adjusted.

1.2 What Is Project Management?

- Managing projects is a matter of keeping scope, schedule, and resources in balance.

- Generally this means planning, organizing, and tracking a project’s tasks and identifying and scheduling resources to accomplish those tasks.

- Scope is the range of tasks required to accomplish project goals.

- A schedule indicates the time and sequence of each task, as well as the total project duration.

- Resources are the people and/or equipment that perform or facilitate project tasks. Resources usually have costs, such as wages or operating expenses that you may want to track.

- When scope, schedule, and resources are in balance, you have just the right amount of resources to accomplish all your project tasks on or before the project deadline.

- The primary project management tool for achieving the project goals efficiently is a project plan.

- Without a formal plan, you reduce the likelihood of accomplishing project goals, such as staying within budget or on schedule.

- If you can’t easily track who’s doing what, or when tasks should be finished, you jeopardize your chances of meeting those goals.

## How Microsoft Project Helps

Microsoft Project is a powerful tool that helps you organize and track the myriad peculiarities of your project.

2.1 Calculate Most Schedule Details

You enter relatively few pieces of information, and Microsoft Project takes care of the rest. For example, if you specify a task’s length, Microsoft Project calculates the task’s start and finish dates. Automatically, Or, if you define a resource’s workday as 8 hours, Microsoft Project can alert you if there are days when that resource will be working additional hours.

2.2 Balance Critical Scheduling Factors with Ease

On the project level, Microsoft Project helps you maintain a balance among scope, resources, and time: Have more tasks been added to your project but not more time? A quick look at your Microsoft Project schedule shows you if existing resources have enough free time to accomplish the new tasks, without extending the project deadline.

On the task level, Microsoft Project helps you maintain a balance between the hours it takes to complete a task, the assigned resources, and the overall task length. For example, if a task that takes one person 4 days to complete needs to be done in 2 days, Microsoft Project makes it easy to assign a second person.

2.3 Flag Problems — Before They Impact Your Schedule

The ability to look ahead and avoid scheduling problems before they occur can mean the difference between project success and failure. Your project plan helps you identify and correct problems such as overloaded resources, tasks that threaten to bust your budget, and scheduling conflicts that could push out the project deadline.

In these and other ways Microsoft Project helps you manage projects of any degree of complexity efficiently, ensuring that you spend less time on project management details and more on the work that’s of most importance to you.

2.4 Create a Project Plan

During this phase you enter tasks, estimate how many days or hours it will take to complete each task, specify when one task should start relative to another, and assign resources to tasks. Microsoft Project will:

- Schedule each task and calculate the project finish date.

- Calculate the time required to complete each task.

- Balance scope, resources, and time — or show you where they’re out of balance.

2.5 Track a Project Plan

When you track your project, you monitor task progress and, often, compare what has occurred with what you planned. That way, you know if you need to adjust the schedule so that you can keep to the original deadline. Microsoft Project will:

- Display both your original estimates — such as the length of a task — and the actual data.

- Calculate and display the difference between your original estimates and actual data.

- Simplify the process for updating your plan with actual data.

- Calculate the effect of updates on the schedule.

2.6 Close the Project

At the close of a project, you typically resolve outstanding issues, identify what worked well, identify problems and areas for future improvement, and document your findings. Although Microsoft Project doesn’t provide direct support for these activities, it can:

- Save a copy of your original plan to help you identify problem areas.

- Store notes about tasks and resources, which you can refer to when analyzing problems and performance.

- Supply project information you need to document your findings.

- When you use Microsoft Project to manage your project, you stay in control of your schedule during each project phase with a minimum of time and effort.

3. Start a New Project File

Before you can create a project plan in Microsoft Project, you have to start a new project file. A new project file consists of fields and views ready to be filled with information about your project’s tasks, resources, and assignments.

3.1 To start a new project file

- Click New .

- Enter a start or finish date.

  - To enter a start date, type the date on which you want to start your project in the Start date box.

  - To enter a finish date, click Project Finish Date in the Schedule from box, and then type a finish date from which to schedule your project in the Finish date box.

An empty project file appears. By default, the Gantt Chart view is displayed.

3.2 Enter or Change a Project Start or Finish Date

- When you open a new project file in Microsoft Project, you can enter your project’s start or finish date, but not both.

- It’s most common, and recommended, that you enter only your project’s start date and let Microsoft Project calculate the finish date after you have entered and scheduled tasks.

- If your project must absolutely be finished by a certain date, then enter only the project’s finish date.

3.2.1 To change a project start or finish date

- On the Project menu, click Project Information.

- Enter a start or finish date.

  - To enter a start date, type the date on which you want to start your project in the Start date box.

  - To enter a finish date, click Project Finish Date in the Schedule from box, and then type a finish date from which to schedule your project in the Finish date box.

3.3 Enter Project Goals, Scope, and Assumptions

- Before you enter project goals, scope, and assumptions into your project file, you and your team need to think about, discuss, and agree on these important project elements.

- While no project management program can determine goals, scope, and assumptions for you, Microsoft Project makes it easy to incorporate them into a new project plan.

3.3.1 To enter project goals, scope, and assumptions

- On the File menu, click Properties.

- Click the Summary tab.

- In the Comments box, type your project goals, scope, and assumptions.

3.4 Save Your Project

After you make important additions or changes to your project plan, it’s a good idea to save the plan.

3.4.1 To save your project

- Click Save  .

- If this is the first time you’ve saved the project, type the project name in the File name box.