IS –351 Project Management

Tutorial # 2

##### Breaking Your Project into Tasks, Phases, and Milestones

# Objectives:

- Learn what is a task list

- Learn how to enter and delete tasks in MS Project

- Learn how to estimate tasks lengths in MS Project

# 1. The Core of Your Project Plan: The Task List

Without a grocery list, you might not remember all the ingredients you need to buy for tonight’s dinner. Without a task list, you might leave out some of the tasks that need to be performed to achieve your project goals. The task list is the core of your project plan. It consists of all the tasks, phases, and milestones required by your project.

To create an effective task list, use the following rules of thumb:

- Include only tasks that are critical to the completion of your project.

- Add tasks that are significant, yet detailed enough that the time to complete each one is short compared to the overall project length.

- Build in phases and milestones.

- Remember tasks that occur repetitively, such as weekly meetings, status reporting, and anticipated revision work.

In Microsoft Project, you enter and work with tasks mainly in the Gantt Chart view. As you create your task list, you can easily refine it by adding milestones, entering tasks that occur at regular intervals, entering the estimated time each task will take, and deleting unnecessary tasks.

## 2. Enter Tasks

After you decide which tasks you want to include in your project, you can enter those tasks into your project plan. This is the biggest and most important step toward achieving your project goals.

Although you can create your task list in a number of Microsoft Project views, you might find it most convenient to enter your tasks in the Gantt Chart view. In the Gantt Chart view, you not only see your tasks as you enter them, but you also see additional task information that Microsoft Project provides in the view fields (which are represented by columns). Microsoft Project adds this information to the chart portion of the Gantt Chart view.

Even though Microsoft Project starts scheduling tasks as soon as you enter them, the project and task schedules are not accurate until the entire plan is built. For example, you can change task durations after you add each task or after you finish entering all tasks.

To enter a task in the Gantt Chart view

| 1 |  | On the View menu, click Gantt Chart. |
| --- | --- | --- |

| 2 |  | In the Task Name field, type a task name, and then press TAB. Microsoft Project enters an estimated duration of one day for the task followed by a question mark. |
| --- | --- | --- |

| 3 |  | In the Duration field, type the amount of time each task will take in months, weeks, days, hours, or minutes, not counting nonworking time. You can use the following abbreviations: months = mo weeks = w days = d hours = h minutes = m Note To show an estimated duration, type a question mark after the duration. |
| --- | --- | --- |

| 4 |  | Press ENTER. |
| --- | --- | --- |

## 3. Delete Tasks

With Microsoft Project, you can delete unneeded tasks easily. You can, for instance, delete a summary task (and all of its subtasks) or any individual task itself. After you delete a task, Microsoft Project automatically renumbers the remaining tasks.

To delete a task

On the View Bar, click Gantt Chart . You can restore a deleted task right after deleting it by clicking Undo .

- In the Task Name field, select the task you want to delete.

- On the Edit menu, click Delete Task.

## 4. Enter Recurring Tasks

If a task in your project occurs repeatedly during the course of the project — weekly status meetings are a common example — it would be time-consuming to enter each occurrence. With Microsoft Project you need enter each recurring task only once; then all of its occurrences are automatically added to your project plan at the frequency you specify.

You can set up a task to occur daily, weekly, monthly, or yearly. You can also specify the duration of each occurrence, when the task will occur, and how often (or for how long) it should recur.

To enter a recurring task

- On the View Bar, click Gantt Chart .

- In the Task Name field, select the row above which you want to insert the recurring task.

- On the Insert menu, click Recurring Task.

- In the Name box, type the task name.

- In the Duration box, type the duration of a single occurrence of the task.

- Under This occurs, click the interval at which the task will recur. 
The option you click determines whether the Daily, Weekly, Monthly, or Yearly options are displayed. 
If you select Weekly, you must also select a day or days of the week on which the task occurs.

- Under Daily, Weekly, Monthly, or Yearly, specify the task frequency.

Under Length, type the start date in the From box and type the finish date in the To box, or type the number of times the task will occur in the For occurrences box. If you don’t enter a date in the From box, the project start date is used.

## 5. Add Milestones

If your project plan consists purely of tasks, or just tasks and phases, it may not be apparent when you’ve completed a major step. To mark the completion or beginning of significant sections of your project, you can add milestones.

In Microsoft Project, a milestone is indicated by a task with zero duration. So, your first step in adding a milestone is to enter it in the Task Name field. When you enter duration of zero days for the task, Microsoft Project displays a distinctive diamond-shaped milestone symbol at the start of that day on the Gantt Chart.

Add a milestone to the end of a phase or to mark a point in the project when you must deliver something to a supervisor or a client (such as a report, a product, or a service) that’s due before the project ends.

To enter a milestone

- On the View Bar, click Gantt Chart .

- In the Duration field of the task you want to change, type 0days.

- Click or press ENTER.

## 6. Estimate Task Length

Like everything else in life, each task in your project will take a certain amount of time to complete (unless it’s a milestone). That certain amount of time is called the task duration. By including each task’s duration in your project plan, you get some sense of how long the project will take. Besides, Microsoft Project can’t calculate a schedule accurately if it doesn’t have accurate duration estimates from you. So you’re going to need some way to estimate task duration. You can approach this in several ways:

- Base estimates on the experience of others. Find out from the people who are or have been responsible for these tasks how long they think the tasks will take.

- Base estimates on your experience. If you have managed projects that included similar tasks, you might be able to apply your old estimates to the new tasks.

- Base estimates on past records, if any. Perhaps you have copies of past project plans that include estimated or actual durations for tasks similar to the ones in your current project.

In Microsoft Project, a task’s duration does not include any nonworking time, such as weekends and holidays. So, for example, a 4-day task scheduled to begin on a Thursday will occur on Thursday, Friday, Monday, and Tuesday.

If you want to schedule a task over a continuous period of time, including nonworking time, you can specify an elapsed duration. Using elapsed duration, a 4-day task that begins on a Thursday will occur on Thursday, Friday, Saturday, and Sunday. For example, use elapsed duration to indicate the time required for a painted wall to dry. If the wall was painted on Friday and it took 2 days to dry, the elapsed duration would span 3 days, beginning on Friday and ending on Sunday.

## 7. Enter or Change Task Durations

When you enter a task, Microsoft Project gives each task a duration of 1 day by default. It would be an unlikely coincidence if, in fact, all your tasks really did last just 1 day. You’ll probably want to change the durations of most tasks.

You can assign durations to tasks using minutes, hours, days, or weeks. By entering just a duration for each task and letting Microsoft Project calculate the start and finish dates for you, you’ll create the most efficient schedule.

To change a task duration

- On the View Bar, click Gantt Chart .

- In the Duration field for the task duration you want to change, type the duration you want. 
To specify elapsed duration, precede the time unit with the letter "e" (for example, edays for elapsed days).

- Click or press ENTER.

## 8. Enter the Duration Only, and Let Microsoft Project Do the Rest for You

As you enter tasks, Microsoft Project schedules them to start on the project start date. Of course, every task won’t start immediately. Later on, as you enter additional information about tasks, such as their dependencies on other tasks (for example, hang clocks on the wall only after the paint has dried), Microsoft Project automatically sets more realistic start dates.

To give Microsoft Project the flexibility to schedule realistic start dates, you should enter the task duration only — not the start and finish dates for a task. If you enter the start and finish dates for a task, you restrict the task to starting no earlier than the start date. For example, if you specify a fixed start date for hanging clocks on a wall and the date for painting the walls slips, you and the clocks are going to get awfully messy. If you specify the duration only, you enable Microsoft Project to schedule the clock-hanging flexibly, moving the start date forward or back if the wall-painting occurs later or earlier than planned. Restrict a task to start on a certain date only when it’s absolutely necessary.

To move a task

On the View Bar, click Gantt Chart . By clicking the task ID number, you select the entire task row, including all the information for the selected task.

- Click the ID number of the task you want to move.

- Click Cut Task .

- Select the row above which you want to insert the task.

- Click Paste .

## 9. Outline Your Task List

You’ve grouped related tasks and put them in the order you want. But because the task names all line up on the left, there’s no way to tell where one group ends and another begins. Also, a simple, undifferentiated list can’t show which tasks represent major steps or phases.

The way to visually distinguish one group of tasks from another, and to show which tasks belong to a specific project phase, is to outline your task list. With Microsoft Project, you can move a task to a level lower than the task above it by indenting it. Conversely, you can raise a task to a level higher in the outline hierarchy by outdenting it (unless it is already at the highest level). You’ll find it best to stick with either a top- down approach (summary tasks first) or a bottom-up approach (subtasks first) when building your schedule.

When you indent a task with respect to the task above it, the task above becomes a summary task and the indented task becomes its subtask. You can also turn a task into a summary task by outdenting it to a level higher (if it’s not already at the highest level) than the tasks that follow it. Whichever method you use, you should assign at least two subtasks per summary task.

By outlining your task list, you make it easy to reorganize your project schedule. Whenever you move or delete a summary task, all of its subtasks go with it.

To indent or outdent a task

- On the View Bar, click Gantt Chart .

- In the Task Name field, select the task you want to indent or outdent.

- Click Indent to indent the task or click Outdent to outdent the task.

## 10. Expand and Collapse Summary Tasks

When viewing your plan, sometimes you just want to see an overview of your project that includes the major steps or phases. Sometimes you need to see every task, down to the smallest detail. When you outline your project, indenting subtasks under summary tasks, you can view and print your project plan at any level of detail by collapsing and expanding various summary tasks in your project.

By collapsing or expanding an outline, you can hide or display the subtasks of a summary task. For example, you can collapse the outline to show only the top-level tasks, and then print that view to create a summary report for your project. You can also collapse or expand specific summary tasks, highlighting (in bold) or hiding the tasks or group of tasks you want.

To collapse or expand an outline

On the View Bar, click Gantt Chart . To expand the entire outline, click Show All Subtasks .

- In the Task Name field, select the summary task containing the subtasks you want to show or hide, or select the nonsummary tasks you want to hide.

- Click Show Subtasks to show the subtasks or click Hide Subtasks to hide the subtasks.