IS –351 Project Management

Tutorial # 3

##### Project Management

# Objectives:

- Learn how to create task links

- Learn how to create task resource list

- Learn how to create working time calendars

## 1. Create a Task Link

Once you’ve decided which type of link best reflects the dependency between two tasks, you’re ready to link those tasks.

The most commonly used task link in a typical project schedule is Finish-to-start (FS). Because you’ll be applying this link often, Microsoft Project enables you to link tasks in an FS dependency quickly. However, FS links don’t always mirror the dependencies that exist between tasks. You can also create an FS link between summary tasks: the start of one group of tasks depends on the end of another.

To link tasks in an Finish-to-start (FS) dependency

- On the View Bar, click Gantt Chart .

In the Task Name field, select two or more tasks you want to link. Select nonadjacent tasks by holding down CTRL while you select the task.

- Click Link Tasks.

A link line appears on the Gantt Chart, connecting the two tasks.

Avoid Entering Start and Finish Dates - Link Your Tasks

When you enter start and finish dates for tasks, you force those tasks to begin and end no earlier than the dates you have entered. Changes elsewhere in the schedule might not affect the start and finish dates of these tasks. As a result, your schedule can’t accurately reflect the real-life fluidity of your project and its tasks.

Linking tasks saves you time because Microsoft Project will calculate start and finish dates for tasks, as well as the project finish date, so you don’t have to. Task linking also lets you see exactly how a slip in the project schedule changes the start and finish dates of individual tasks and the project’s finish date. If one element of the schedule shifts, the overall task time frame remains flexible. Microsoft Project automatically moves tasks forward or backward in time in a logical way, while maintaining the links between tasks.

Your best strategy is to enter just the duration for each task and leave start and finish date calculations to Microsoft Project. (Specify a start or finish date only for a task that doesn’t depend on another task and therefore shouldn’t be linked.)

## 2. Change or Remove a Task Link

If the link between tasks doesn’t accurately reflect the dependency between those tasks, you can easily change the type of link that connects them. If you later decide that you don’t want a link between particular tasks, you can remove that link.

To change a task link

- On the View Bar, click Gantt Chart .

- Double-click the link line of the tasks you want to change.

- In the Type box, click the task link you want.

To remove a task link

- On the View Bar, click Gantt Chart .

- In the Task Name field, select the tasks you want to unlink.

- Click Unlink Tasks.

The task will be rescheduled based on any other dependencies.

## 3. Overlap or Delay Tasks

Sometimes task links alone might not show accurately when tasks will actually start. For example, in the clockwork project, painting the walls precedes hanging the clocks, and those tasks have a finish-to-start link. The schedule shows that the clocks will be hung immediately after the painter finishes painting, but that’s before the paint has had a chance to dry.

After you enter tasks and assign dependencies to them, analyze your schedule and look for instances where you can apply lead or lag time. By using lead and lag time, you can make your schedule more accurate, and you may be able to shorten it as well.

You can express lead or lag time as units of time or as a percentage of the predecessor task’s duration. For example, the paint on the walls must dry for 1 day before clocks can be hung, so the exhibit manager can specify a 1-day lag between painting the walls and hanging the clocks. Or, if the electrician can begin wiring display cases after half the cases are installed, the "Install and position case lights" task can start when the "Install wood and glass cases" task is 50 percent complete, regardless of the duration of the predecessor task.

To add lead or lag time

- On the View Bar, click Gantt Chart .

In the Task Name field, select the successor task you want, and then click Task Information . To add lead or lag time to a successor task quickly, double-click the link line on the Gantt Chart and type the lead or lag time in the Lag box of the Task Dependency dialog box.

- Select the Predecessors tab.

- In the Lag field, type the lead time or lag time you want, as a duration or as a percentage of the predecessor task’s duration. 
Type lead time as a negative number or as a negative completion percentage. Type lag time as a positive number or as a positive completion percentage. 
Use minute, hour, day, or week for the lead or lag time units. To specify elapsed duration, precede the time unit with the letter "e" (for example, edays for elapsed days). Elapsed days include weekends and other nonworking days.

## 4. Constrain a Task to Start or Finish On or Near a Specific Date

If a task must start or finish on or near a specific date, just linking tasks and adding lead or lag time might not do the trick. This may be the time to set a constraint. The type of constraint you set for a task depends on the task’s scheduling requirements.

To set a constraint

- On the View Bar, click Gantt Chart .

- In the Task Name field, select the task you want, and then click Task Information .

- Click the Advanced tab.

- In the Type box, click a constraint type.

- If you selected a constraint other than As Late As Possible or As Soon As Possible, click a constraint date in the Date box. (Otherwise, Microsoft Project uses the task’s current start or finish date.) 
Microsoft Project adds the constraint and recalculates the schedule.

It’s also a good idea to check the necessity of your constraints occasionally.

To check a constraint

- On the View Bar, click Gantt Chart .

- On the View menu, point to Table, and then click More Tables.

- In the Tables list, click Constraint Dates.

- Click Apply.

Microsoft Project replaces the fields in the Gantt Chart view, listing the task constraints. If necessary, scroll to see the fields.

# 5. Create a Resource List for Your Project

Once you’ve decided which resources to include in your project, you need to add them to your project plan. Using Microsoft Project, you have two methods for adding resources. If you have fewer than 10 or so resources, you can add them one at a time as you assign resources to tasks. If your project includes more than 10 resources, you’re better off creating a resource list before you assign resources to tasks. Adding all resources to your project plan at once by creating a resource list takes less time than adding one resource at a time as you assign resources to tasks.

A resource list includes:

- The name of the resource, which can be a person, a piece of equipment, or a group of interchangeable resources, such as pilots.

- The maximum amount of time per day a resource is available to work.

To create a resource list

On the View Bar, click Resource Sheet . You can also create a resource list as you assign new resources to tasks.

- On the View menu, point to Table, and then click Entry.

- In the Resource Name field, type a resource name in a blank field.

- If you want to designate a resource group, type a name for the group in the Group field. 
To add several resources to the same group, type the same group name in the Group field for each resource.

- If necessary, type the number of resource units available for this resource in the Max. Units field.

- Change the default information in the remaining fields as appropriate.

- Repeat steps 3 through 6 for each resource.

## 6. What You Should Know About Units

Units indicate the percentage of time a resource will spend working on a task. For example, if you assign a person to work full-time on a task, you’d assign that person at 100 percent units. If you want that person to spend only a quarter of his or her available time on the task, you’d assign that person at 25 percent units. When you assign a set of resources to a task, 100 percent units means you’ve assigned one resource from that set to work on the task full-time, 200 percent means you’ve assigned two resources from the set, and so on.

## 7. Create a Working Times Calendar for a Group of Resources

Whenever several resources share basic schedule information, you can create a different base calendar for them. For example, you can have a base calendar for the day-shift workers and one for the night-shift workers.

To modify a project calendar or create a working times calendar for a group of resources

- On the Tools menu, click Change Working Time.

- Click New.

- In the Name box, type a name for the calendar, and then click OK. 
A copy of the Standard calendar appears, with the name you specified.

- On the calendar, select the dates you want to modify.

- Click Use default, Nonworking time, or Working time to modify the selected dates.

- If you clicked Working time in step 5, type the times you want work to start in the From boxes and the times you want work to end in the To boxes.

## 8. Assign a Group of Resources to a Working Times Calendar

After you create a base calendar, you need to assign the calendar to each resource that will be using it.

To assign resources to a working times calendar

- On the View Bar, click Resource Sheet .

- In the Base Calendar field of each resource you want to assign to a calendar, select the same base calendar.

To modify a working times calendar for an individual resource

- On the View Bar, click Resource Sheet .

- In the Resource Name field, select a resource, and then click Resource Information .

- Click the Working Time tab.

- In the Base calendar box, click the base calendar you want to modify for the resource.

- On the calendar, select the dates you want to change.

- Click Use default, Nonworking time, or Working time to modify the selected dates.

- If you clicked Working time in step 6, type the times you want work to start in the From boxes and the times you want work to end in the To boxes.

## 9. Assign One or More Resources to a Task

Keeping track of which resource performs a particular task, how much work a resource has in a certain time period, and how much your resources have cost since the project began can be difficult and time-consuming. But there’s one thing you can do that enables Microsoft Project to take care of these responsibilities for you: assign resources to tasks.

When you assign a resource to a task, you create an assignment. You can assign any resource to any task and change assignments at any time.

You can assign more than one resource to a task and specify whether a resource works full-time or part-time on the task by using resource units. Resource units indicate the percentage of the resource’s time allocated to the task. By default, Microsoft Project assigns 100 percent units to each resource (unless a resource is a part-time resource). If the resource represents a single entity, 100 percent units means the resource is working full-time on the task. If you assign a resource group — for example, a group of three painters — at 100 percent, it means only one of the painters is assigned to the task. If you assign all three painters, it would be 300 percent. If the work assigned to a resource exceeds the daily full-time allotment indicated in the resource’s working times calendar, Microsoft Project displays the name of the overallocated resource in red in resource views.

To assign a resource to a task

On the View Bar, click Gantt Chart . Double-click a resource in the Resource Assign-ment dialog box to display the Resource Information dialog box.

- In the Task Name field, select the task to which you want to assign a resource.

- Click Assign Resources .

- In the Name field, select the resource you want to assign to the task. 
If necessary, type the name of a new resource in a blank Name field.

- Click Assign. 
A check mark to the left of the Name field indicates that the resource is assigned to the selected task.

## 10. Control When a Resource Starts Working on a Task

When you assign resources to a task, Microsoft Project assumes by default that each resource begins working on the task on that task’s start date. But that scenario might not match reality. One resource might begin work on the start date, but another might not be available until several hours or days later.

With Microsoft Project, you can specify exactly when a resource begins working on a task. For example, you can stagger the times that multiple resources begin working on the same task by delaying the starting time of one or more of the resources. This is true even if you have only one resource assigned to a task. When you delay the start of a resource assignment, Microsoft Project recalculates the start date and time for the resource’s work on the task.

To control when a resource works on a task

- On the View Bar, click Gantt Chart .

- On the Window menu, click Split.

- In the Task Name field, select the task for which you want the resource’s work to be delayed.

- Click the Task Form view in the bottom pane.

- On the Format menu, point to Details, and then click Resource Schedule.

- If there is no work for the resource in the Work field, enter the work in the field, and then press ENTER.

- In the Delay field for the resource, enter the duration by which you want to delay the start of the resource’s work. 
For example, type 2h for a delay of 2 hours; type 2d for a delay of 2 days.

- Click OK.

- On the Window menu, click Remove Split.

# 11. Remove a Resource from a Task

Just as a task can change during a project — for example, its duration can increase or decrease — so can a resource. If one of your resources falls ill or becomes too busy to work on a task, you might need to remove that resource. Whenever necessary, it’s easy to remove the assigned resource.

To remove a resource from a task

- On the View Bar, click Gantt Chart .

- In the Task Name field, select a task from which you want to remove a resource.

- Click Assign Resources .

- In the Name field, select the resource you want to remove, and then click Remove.

# 12. Replace a Resource in One Step

You can replace a resource with someone on your resource list in one step. For example, you might find a more qualified person to perform a task you already assigned to someone else. Or, perhaps a piece of equipment you’ve assigned to a task breaks down. Rather than removing the assigned resource and then assigning another resource in a separate action, you can simply replace one resource with another.

To replace a resource with another resource

- On the View Bar, click Gantt Chart .

- In the Task Name field, select a task with a resource you want to replace.

- Click Assign Resources .

- In the Name field, select the resource you want to replace, and then click Replace.

- In the Name field, select one or more resources to assign to the task, and then click OK.