## Slide 1
8 - <number>

## Slide 2
Define and recognize risk
Define the contents of a risk management plan
Conduct a risk identification and prioritization process
Define the correct risk response strategy for the organization
8 - <number>

## Slide 3
Every IT project regardless of size, complexity, location, or organization contains some measure of risk
Aid the project team in assessing the impact a negative event will have on the project and how likely (generally expressed as a percentage or qualitative term) is the event to occur
The PM’s objective: is not the removal of all risk, this simply can’t be done, but to identify and manage risks to the benefit of the project
Risks on a project can be a good thing if managed appropriately
The main objectives of risk management are to increase the probability and impact of positive outcomes and decrease the probability and impact of negative outcomes
8 - <number>

## Slide 4
Crisis management is the opposite of good risk management – organizations find themselves trying to figure out what to do about a problem after it has occurred instead of planning for issues in advance
8 - <number>

## Slide 5
A Function of the {likelihood, and impact}
An event if it occurs will have a negative impact on one or more of: project scope, time, cost, quality, or resources
8 - <number>

## Slide 6
  Risk management planning: deciding how to approach and plan the risk management activities for the project
  Risk identification: determining which risks are likely to affect a project and documenting their characteristics
  Qualitative risk analysis: characterizing and analyzing risks and prioritizing their effects on project objectives
  Quantitative risk analysis: measuring the probability and consequences of risks
  Risk response planning: taking steps to enhance opportunities and reduce threats to meeting project objectives
8 - <number>

## Slide 7
The main deliverable of risk management planning is the risk management plan!
The risk management plan is created early in the planning phase of the project and updated throughout the life of the project
8 - <number>

## Slide 8
The first step is to identify as many risks as possible for the upcoming project with the knowledge that you can never see them all
Risk identification is not a one time process; but should be a continuous process of team members and stakeholders looking for new issues that may affect the success of the project Broad Organizational Categories
  Analogy
  Brainstorming
  Interviews
  Delphi Technique
  SWOT Analysis
8 - <number>

## Slide 9
People (human resources)
Technology (changes)
Quality and performance issues
Customers
Vendors
Management
Funding
Political Issues or Legal Issues
Market Forces
8 - <number>

## Slide 10
Analogy
  Uses information from past similar projects or the experience of team members to look for risks
  Previous projects must be up to date!
  Delphi Technique
  Using this technique the participants are unknown to each other so ideas can be generated without fear of ridicule
Brainstorming
  It is a non-structured or semi-structured method of eliciting ideas from a group with the goal of generating a complete list of ideas
8 - <number>

## Slide 11
Post-it note
  During a short time interval such as five minutes, have each participant write down on post-it notes as many ideas as they can think of putting one idea per post-it
  Participants then hand their notes to the moderators who stick them on a chalk or white board. duplicate ideas are stuck on top of each other to reduce the number of entries. A list of ideas is then quickly generated and the team discusses the merits of each
  Ideas which have close to zero probability of occurring or zero impact to the project are removed from the board
8 - <number>

## Slide 12
The ideas that remain must then be rated for likelihood and impact. A large matrix is drawn on the board similar to the probability and impact matrix (Figure 8-2). The post-it notes can then be moved around inside the matrix until the team agrees on each placement
Finally, generate the start of the risk register (figure 8-1) from the remaining post-it notes
8 - <number>

## Slide 13
The project leader and other key members of the team with interview skills, conduct personal one-on-one discussions with key stakeholders
The crucial aspect to successful interviewing is to make sure the stakeholders feel comfortable sharing ideas with the interviewer
The success of this technique is heavily dependent on the skills of the interviewer
8 - <number>

## Slide 14
8 - <number>

## Slide 15
Copyright © 2010 Pearson Education, Inc. Publishing as Prentice Hall
8 - <number>

## Slide 16
Copyright © 2010 Pearson Education, Inc. Publishing as Prentice Hall
8 - <number>

## Slide 17
Subjective methods for qualifying each risk for impact and probability of occurrence
This usually involves a method which can be done quickly in a short period of time with little resources
Risk qualitative tools and techniques include
  Interviews with Subject Matter Experts
  Probability/Impact matrix
8 - <number>

## Slide 18
The probability and impact matrix aids the project team in prioritizing which risks need more attention based on either their probability of occurring or the size of the impact to the project or both
8 - <number>

## Slide 19
8 - <number>

## Slide 20
Copyright © 2010 Pearson Education, Inc. Publishing as Prentice Hall
8 - <number>

## Slide 21
8 - <number>

## Slide 22
The columns represent the degree of impact to the project’s scope, time, cost, and quality goals
This example using a five level scale: zero to low impact, low to medium, medium, medium to high, and high impact. The scores are determined by subject matter experts and historical data
The next step determine the probability that a risk will materialize again using expert judgment and historical data
8 - <number>

## Slide 23
8 - <number>

## Slide 24
Much like qualitative risk analysis, quantitative risk analysis attempts to estimate the impact a risk may have on a project as well as the probability
The key difference between the two is that quantitative analysis is based on mathematical or statistical techniques to model the behavior of a particular risk
8 - <number>

## Slide 25
Decision trees with expected monetary value analysis
Simulation (Monte Carlo)
8 - <number>

## Slide 26
After identifying and quantifying risk, you must decide how to respond to them
Four main strategies:
  Risk avoidance: eliminating a specific threat or risk, usually by eliminating its causes
  Risk acceptance: accepting the consequences should a risk occur without trying to control it
  Risk transference: shifting the consequence of a risk and responsibility for its management to a third party internal or external to the organization
  Risk mitigation: reducing the impact of a risk event by reducing the probability of its occurrence
8 - <number>

## Slide 27
The final step after the risk response has been chosen; update the risk register with the mitigation strategy: fallback plans, contingency plans, and contingency reserves.
  Fallback plans
  Contingency plans.
  Contingency reserves
Contingency plans use the contingency reserves to meet project objectives
8 - <number>
Notes:   Fallback plans are used if the project can not be completed as originally planned
  Contingency plans are put in place to allow for fluctuations that will allow the project to finish as originally planned.
  Contingency reserves are excess amounts of time, dollars, and resources etc. used if necessary in order for the project to finish as originally planned.
<number>

## Slide 28
Build/choose the risk management plan format
Identify risks
Risk assessment
Complete the risk register
Complete the risk management plan (budget, schedule of activities, any specific tools needed)
8 - <number>