## Slide 1
Project duration can be reduced by assigning more resources to project activities.
However, doing this increases project cost.
Decision is based on analysis of trade-off between time and cost.
Project crashing is a method for shortening project duration by reducing one or more critical activities to a time less than normal activity time.
Project Crashing and
Time-Cost Trade-Off Overview
Jul 29, 2026
Dr.Bokkasam Sasidhar
<number>

## Slide 2: The Project Network House Building Project Data
Number | Activity | Predecessor | Duration
1 | Design house and obtain financing | -- | 12 months
2 | Lay foundation | 1 | 8 months
3 | Order and receive materials | 1 | 4 months
4 | Build house | 2,3 | 12 months
5 | Select paint | 2, 3 | 4 months
6 | Select carper | 5 | 4 months
7 | Finish work | 4, 6 | 4 months
Jul 29, 2026
Dr.Bokkasam Sasidhar
<number>

## Slide 3
Project Crashing and Time-Cost Trade-Off
Example Problem
The project network for building a house

## Slide 4
Normal activity and crash data for the network
Project Crashing and Time-Cost Trade-Off
Example Problem

## Slide 5
Project Crashing and Time-Cost Trade-Off
Example Problem
Time-cost relationship for crashing activity 1
Crash cost & crash time have a linear relationship
Jul 29, 2026
Dr.Bokkasam Sasidhar
<number>

## Slide 6
Network with normal activity times and weekly crashing costs
Project Crashing and Time-Cost Trade-Off
Example Problem

## Slide 7
Revised network with activity 1 crashed
Project Crashing and Time-Cost Trade-Off
Example Problem
As activities are crashed, the critical path may change and several paths may become critical.

## Slide 8
Project Crashing and Time-Cost Trade-Off
QM for Windows Output

## Slide 9
Project Crashing and Time-Cost Trade-Off
QM for Windows

## Slide 10
Project Crashing and Time-Cost Trade-Off
General Relationship of Time and Cost
Project crashing costs and indirect costs have an inverse relationship.
Crashing costs are highest when the project is shortened.
Indirect costs increase as the project duration increases.
The optimal project time is at the minimum point on the total cost curve.
Jul 29, 2026
Dr.Bokkasam Sasidhar
<number>

## Slide 11
Project Crashing and Time-Cost Trade-Off
General Relationship of Time and Cost
The time-cost trade-off
Jul 29, 2026
Dr.Bokkasam Sasidhar
<number>

## Slide 12: Example
Jul 29, 2026
Dr.Bokkasam Sasidhar
<number>
Sharon Lowe, Vice President for Marketing for the Electronic Toys Company, is about to begin a project to design an advertising campaign for a new line of toys. She wants the project completed within 47 days in time to launch the advertising campaign at the beginning of the Christmas season.
Sharon has identified the six activities (labeled A, B, …, F) needed to execute this project. Considering the order in which these activities need to occur, she also has constructed the following project network.

## Slide 13: Example (Contd.)
Jul 29, 2026
Dr.Bokkasam Sasidhar
<number>

## Slide 14: Example (Contd.)
Jul 29, 2026
Dr.Bokkasam Sasidhar
<number>
Activity | Time (days) |  | Cost |  | Maximum Reduction in Time | Crash Cost per day saved
 | Normal | Crash | Normal | Crash |  | 
A | 12 | 9 | $210,000 | $270,000 | 3 | $20,000
B | 23 | 18 | $410,000 | $460,000 | 5 | $10,000
C | 15 | 12 | $290,000 | $320,000 | 3 | $10,000
D | 27 | 21 | $440,000 | $500,000 | 6 | $10,000
E | 18 | 14 | $350,000 | $410,000 | 4 | $15,000
F | 6 | 4 | $160,000 | $210,000 | 2 | $25,000
To meet the deadline of 47 days, Sharon has decided to crash the project, using the CPM method of time-cost trade-offs to determine how to do this in the most economical way. She has gathered the data needed to apply this method, as given below.

## Slide 15: Example - Solution
Jul 29, 2026
Dr.Bokkasam Sasidhar
<number>
The upper path is A-C-E-F with a path length of 51 days.
Of the activities on the path, activity C has the smallest crash cost per day saved ($10,000) and activity E is next ($15,000). Activity C can only be reduced by 3 days, so activity E also will need to be crashed somewhat. Therefore, we find that the most economical way of reducing the length of this path to 47 days is to shorten activity C by 3 days and activity E by 1 day with an additional total cost of $45,000.
Activity to crash | Crash Cost | Length of Path A-C-E-F
 |  | 51
C | $10,000 | 50
C | $10,000 | 49
C | $10,000 | 48
E | $15,000 | 47

## Slide 16: Example - Solution
Jul 29, 2026
Dr.Bokkasam Sasidhar
<number>
The lower path is B-D with a path length of 50 days.
From the time-cost trade-off data, both activities B and D have a crash cost per day saved of $10,000, and both can be reduced by more than 3 days. Therefore, using marginal cost analysis, we find that the most economical way of reducing the length of this path to 47 days is to shorten either activity (it doesn’t matter which one) by 3 days with an additional total cost of $30,000.
Activity to crash | Crash Cost | Length of Path B-D
 |  | 50
B or D | $10,000 | 49
B or D | $10,000 | 48
B or D | $10,000 | 47

## Slide 17: Example - Solution
Jul 29, 2026
Dr.Bokkasam Sasidhar
<number>
Combining both the results, the total crashing cost for the optimal way of meeting the deadline of 47 days is $30,000 + $45,000 = $75,000.