## Slide 1: 5. Project PLAN & cost estimation
Session # 5
https://fac.ksu.edu.sa/aquadri

## Slide 2: Checking plan duration, cost and work
Why keep a track of plan??
After you create a task list and assign resources to tasks, your plan contains a large number of details.
Usually, these details are not visible in the default view that is displayed.
The key indicators of a plan are:
    Who is assigned to do what work in the plan?
    How long will it take to complete the project?
    How much will it cost?

## Slide 3: Hands on
Project status reporting features including views and reports.
Enable the Timeline view: On the View tab, in the Split View group, select the Timeline check box.
This allows you to see a complete time line of the project in line with the Gantt Chart.
Next, have a look at the project costs:
        On the View tab, in the Data group, click Tables, and then click Cost.
        The Cost table appears, replacing the Entry table.
        The Cost table includes various cost values for each subtask
        Note the project summary task’s total cost value and map it with the cost in the project information.

## Slide 4: Work assignment values via report
On the Report tab, in the View Reports group, click Resources and then click Resource Overview.
In this report, you can see two charts and one table that contain resource-assignment details.
    Resource Stats
    The chart contains only remaining work values.
    Because, no base line has been stored nor any actual work has been reported.

## Slide 5: Cost management – earned value estimation
Activity:
Construct a room with 4 sides (scope)
Estimation duration – each side 1 day
Estimate cost - each side- $ 1000
Default relation between activities – DFS
Find Actuals PV, EV, AC, BAC, CV, CPI, SV, SPI
Find Forecasters (EAC, ETC, VAC, TCPI)

## Slide 6: analysis
Day 1- 100 % Done @ $1000
Day 2- 100 % Done @ $1200
Day 3- 50% Done @ $600 (We are here today)
Day 4- Not yet done

## Slide 7
Planned Value (PV):
According to the plan we were to complete 3 sides in 3 days and spend $ 3000
Therefore PV = 3000
Earned Value (EV):
Work accomplished so far and cost incurred so far as per the original plan
Therefore EV = D1, 1000 + D2, 1000 + D3 500 = 2500
Actual Cost:
Actual Cost, is the cost incurred against the planned cost
AC = D1, 1000 + D2, 1200 + D3, 600 = 2800
Budget At Completion (BAC):
Budget at completion as planned
As planned D1, 1000 + D2, 1000 + D3, 1000 + D4, 1000 = $ 4000

## Slide 8: Lets work it out!
Cost Variance (CV):
Gives us the variance incase the project is going overbudget or underbudget
CV = EV – AC = ??
Cost Performance Index (CPI):
CPI = EV/AC = ??
Schedule Variance (SV):
SV = EV-PV = ??
Schedule Performance Index (SPI):
SPI = EV/PV = ??
To Complete Performance Index (TCPI):
TCPI = BAC-EV/BAC-AC

## Slide 9: Forecasting
Estimate At Completion (EAC):
EAC = BAC/CPI = ??
Estimate To Complete:
The helps in computing if the remaining money in budget would be sufficient for the remaining work
Remaining work = D3, 50% & D4, 100 %
ETC= EAC-AC = ??
Variance At Complete
VAC = BAC-EAC=??

## Slide 10
Cost Variance (CV):
Gives us the variance incase the project is going overbudget or underbudget
CV = EV – AC = 2500 – 2800 = (300)
This means as on today we are over budget by $300
Cost Performance Index (CPI):
CPI = EV/AC = 2500/2800 = 0.89
The means, as on today we are benefitting worth $0.89 for every $1 spent, a CPI of less than 1 is always bad for the project
Schedule Variance (SV):
SV = EV-PV = 2500-3000 = (500)
Indicates how much ahead or behind the schedule a project is running
Schedule Performance Index (SPI):
SPI = EV/PV = 2500/3000 = 0.83 (again less than 1 is bad)
SPI is the speed of the performance

## Slide 11
Forecasters:
Estimate At Completion (EAC):
EAC = BAC/CPI = 4000/0.89 = 4494
This helps in identifying if the allocated budget would be enough.
Estimate To Complete:
The helps in computing if the remaining money in budget would be sufficient for the remaining work
Remaining work = D3, 50% & D4, 100 %
ETC= EAC-AC = 4494-2800=1694
Variance At Complete
VAC = BAC-EAC= 4000-4494= (494)
To Complete Performance Index (TCPI):
TCPI = BAC-EV/BAC-AC = 4000-2500/4000-2800= 1.2
TCPI implies that for every dollar spent we need to get the work done worth $1.2