## Slide 1: 5. Cost resources & PLAN DURATION
Session # 5

## Slide 2: Introduction
Cost resources are used to represent a financial cost associated with a task in a project.
Cost resources might include categories o expenses you want to budget and track or accounting or financial reporting purposes
Cost resources do not incur assignment units.
The costs that tasks can incur can include:
    Work resource costs, such as a person’s standard pay rate times the amount of work they perform on the task.
    Fixed amount that is entered while being assigned to a task.

## Slide 3: Hands on
Enter a task in the task list ‘Author reading and signing at the book fair’.
This task requires air travel by the author, and you allocated $800 in anticipation of this expense.
Assigning the work resource to this task:
    In the Resource Name column in the Assign Resources dialog box, click Zack, and then click Assign.
    Notice that there is no cost assigned in the cost field.
    In the Assign Resources dialog box, select the Travel cost resource, type 800, and then click Assign.
    Click on close

## Slide 4: Checking plan duration, cost and work
Why keep a track of plan??
After you create a task list and assign resources to tasks, your plan contains a large number of details.
Usually, these details are not visible in the default view that is displayed.
The key indicators of a plan are:
    Who is assigned to do what work in the plan?
    How long will it take to complete the project?
    How much will it cost?

## Slide 5: Hands on
Project status reporting features including views and reports.
Enable the Timeline view: On the View tab, in the Split View group, select the Timeline check box.
This allows you to see a complete time line of the project in line with the Gantt Chart.
Next, have a look at the project costs:
        On the View tab, in the Data group, click Tables, and then click Cost.
        The Cost table appears, replacing the Entry table.
        The Cost table includes various cost values for each subtask
        Note the project summary task’s total cost value and map it with the cost in the project information.

## Slide 6: Work assignment values via report
On the Report tab, in the View Reports group, click Resources and then click Resource Overview.
In this report, you can see two charts and one table that contain resource-assignment details.
    Resource Stats
    The chart contains only remaining work values.
    Because, no base line has been stored nor any actual work has been reported.

## Slide 7: Cost management – earned value estimation
Activity:
Construct a room with 4 sides (scope)
Estimation duration – each side 1 day
Estimate cost - each side- $ 1000
Default relation between activities – DFS
Compute Actuals PV, EV, AC, BAC, CV, CPI, SV, SPI
Compute Forecasters (EAC, ETC, VAC, TCPI)

## Slide 8: Activity – Ishikawa Analysis
- Using the Ishikawa Analysis technique create the WBS, cost, time and percentage and
completion percentage of the tasks for the project.
Using the fish bone diagram you identify the delays caused, reasons and cost variances and create a hypothetical chart of the activity, cost and variance
- Based on the hypothesis the Actuals and Forecasters will be computed.

## Slide 9
Actuals
Planned Value (PV):
According to the plan we were to complete 3 sides in 3 days
Earned Value (EV):
Work accomplished so far and cost incurred so far as per the original plan
Actual Cost:
Actual Cost, is the cost incurred against the planned cost
Budget At Completion (BAC):
Budget at completion as planned

## Slide 10
Actuals Contd.
Cost Variance (CV):
Gives us the variance incase the project is going over budget or under budget
CV = EV – AC
Cost Performance Index (CPI):
CPI = EV/AC
Schedule Variance (SV):
SV = EV-PV
Indicates how much ahead or behind the schedule a project is running
Schedule Performance Index (SPI):
SPI = EV/PV
SPI is the speed of the performance should be more that 1 Always

## Slide 11
Forecasters:
Estimate At Completion (EAC):
EAC = BAC/CPI
This helps in identifying if the allocated budget would be enough.
Estimate To Complete:
The helps in computing if the remaining money in budget would be sufficient for the remaining work
Remaining work = D3, 50% & D4, 100 %
ETC= EAC-AC
Variance At Complete
VAC = BAC-EAC
To Complete Performance Index (TCPI):
TCPI = BAC-EV/BAC-AC
TCPI implies that for every dollar spent we need to get the work done worth the result of calculation