## Slide 1: 5. Tracking the project
Session # 5
https://fac.ksu.edu.sa/aquadri

## Slide 2: Why baseline a project
Capture the original estimates (task and resources) of the project.
Track and Report Progress
Measure Variance
Setting proper expectations
The key indicators of a plan are:
    Who is assigned to do what work in the plan?
    How long will it take to complete the project?
    How much will it cost?

## Slide 3: Hands on
Project status reporting features including views and reports.
Enable the Timeline view: On the View tab, in the Split View group, select the Timeline check box.
This allows you to see a complete time line of the project in line with the Gantt Chart.

## Slide 4: Save a baseline
Baseline is used to record the fully developed estimated plan.
With ”Progressive Elaboration” and “Rolling wave Planning” the tasks, resources and costs in project may change.
With MS Project, you can save upto 13 baselines in a single plan.
Multiple baselines help you with managing different levels of plan with external and internal parties.
Project Tab  Schedule Group  Set Baseline

## Slide 5: View baseline in gantt chart
Click View Tab  Task Views Group  Gantt Chart
Click Format Tab  Bars and Styles Group  Baseline (select the one you want to see)

## Slide 6: Update a previously saved baseline
After making necessary changes to tasks, resources and cost
Click Project Tab  Schedule Group  Set Baseline
(Select the previously Saved Baseline to update it)

## Slide 7: Track plan by specific Date
When the tasks are completed not necessarily as per exact estimates but close to deadlines.
Click Project Tab  Status Group  Update Project
Click on the Radio Button “Update work as complete through” and then set a percentage. Select Current Date.
Click Ok

## Slide 8: Track plan as % complete
Click on any task  Task Tab  Schedule group  use 0%, 25 %, 50%, 75% or 100%
Click View tab  Data Group  Tables  Tracking
(For the tasks you wish to update, click the corresponding %Comp column and enter the required %)

## Slide 9: Track plan by actual values
You can enter the following actual values for your project:
Actual Start and Finish Dates
Tasks Actual duration
To Set Tasks Actual Duration
Click View Tab  Data Group  Tables  Work
You will see the % W.Comp (% Work complete) column
Select any task you wish to update, click on ’Actual Field’ and update the duration of this task.

## Slide 10: Lab exercise
Part 1:
From the following description create the ‘Planning’ and ‘Execution’ phases with:
You have been hired as a project manager by Tetra Banks Inc., Your project you are tasked with is to assemble your team with the required resources to landscape the city and identify favorable spots to install and configure the ATM’s.
You will be required to identify the different teams, hold meetings, set up a detailed plan and proceed with execution.
Part 2:
-Draft the complete task list and set the baseline.
-Track your tasks with % completion
-Let some tasks slip on duration
-Identify the variance