## Slide 1: 6. Tracking progress

## Slide 2: objectives
Save current schedule values in a plan as a baseline.
Record progress on tasks through a specific date.
Record tasks’ percentage of completion.
Enter actual work and duration values for tasks.

## Slide 3: introduction
‘Tracking’ refers to:
- who did what work ?
- when the work was done ?
- what was the cost?
These details are also called ‘Actuals’

## Slide 4: Why track a project?
Tracking actuals is essential to properly managing a project.
By properly tracking a project, we can answer the following questions:
    Are tasks starting and finishing as planned or not, what will be the impact on the project’s finish date
    Are resources spending more or less time than planned to complete tasks?
    Are higher-than-anticipated task costs driving up the overall cost of the project?
    When planning similar projects in the future, will you be able to determine how good your (or the team’s) estimating skills were in prior projects?

## Slide 5: How can I track my project?
Project supports several ways to track progress.
Tracking method depends strongly on the level of detail or required control by the PM, Stake holder or Project Sponsor.
The different levels of tracking are:
    Record project work as scheduled. This level works best if everything in the project occurs exactly as planned.
    Record each task’s percentage of completion, either at precise values or at preset increments such as 25, 50, 75, or 100 percent.
    Record the actual start date, actual finish date, actual work, and actual and remaining duration for each task or assignment.
    Track assignment-level work by time period. This is the most detailed level of tracking.
    Here, you record actual work values per day, week, or other interval.

## Slide 6: Baseline
‘Baseline’ refers to the recorded state of the plan (Dates of tasks, resources allotted, etc.,)
As project progresses the actual dates may change, thus to keep a track of project in comparison with the original plan we need to save the ‘Baseline’.
When you save a baseline, MS-Project snapshots the existing values and keeps it save for future comparisons with actuals.
When should I save a baseline?
      When you have a full developed plan.
      Before entering any actuals.
TIP: Project can save up to 11 baselines for a plan

## Slide 7: Hands on
Saving Base line
On the Project tab, in the Schedule group, click Set Baseline, and then click Set Baseline and click on Ok.
*Project saves the baseline but no changes are reflected in the Gantt chart view.
To reflect and track the tasks switch to Task sheet to see the variance.
On the Task tab, in the View group click the down arrow below Gantt Chart, and then click Task Sheet.
On the View tab, in the Data group, click Tables.
Click Variance.
* Notice the variance.

## Slide 8: Recording the actuals – hands on
On the Project tab, in the Status group, click Update Project.
Make sure the Update work as complete through option is selected.
In the adjacent date box, type or select 1/04/17.
Click OK.
Notice the change in the Gantt chart task bars

## Slide 9: Entering task completion by %
Select the task # 3 design and order marketing material.
On the Task tab, in the Schedule group, click 100% Complete.
Recording milestone completion and subsequent task of next phase:
Select the milestone tasks “Planning complete!” and while holding the Ctrl key select the task “Kickoff book launch”
On the Task tab, in the Schedule group, click 100% Complete.
Recording semi completion of task:
Insert a new task “Prepare P&L Statement” with a duration of 2 days in the phase 2.
On the Task tab, in the Schedule group, click 50% Complete.

## Slide 10: Entering actual ‘values’ for tasks
Entering actual work values and actual start dates for tasks
Enter the following tasks in the phase 2:
-Plan author itinerary (1d)
-Channel sales prep (1d)
On the View tab, in the Data group, click Tables and then click Work
In the ‘Actual’ Field for ‘Prepare P&L’ task, type 24 and press enter.
Select the task ‘Plan author itinerary’, On the Task tab, in the Schedule group, click the down arrow to the right of the Mark on Track button, and then click Update Tasks.
In the Start field in the Actual group on the left side of the dialog box, type or select 1/20/15.
In the ‘Actual dur’ field, type or select 7d and click OK

## Slide 11: Reference notes
When you enter various actual values, Project uses the following rules to update the plan:
When you enter a task’s actual start date, Project moves the scheduled start date to match the actual start date.
When you enter a task’s actual finish date, Project moves the scheduled finish date to match the actual finish date and sets the task to 100% complete.
When you enter a task’s actual work value, Project recalculates the task’s remaining work value, if any.
When you enter a task’s actual duration, if it is less than the scheduled duration, Project subtracts the actual duration from the scheduled duration to determine the remaining duration.
When you enter a task’s actual duration, if it is equal to the scheduled duration, Project sets the task to 100% complete.
When you enter a task’s actual duration, if it is longer than the scheduled duration, Project adjusts the scheduled duration to match the actual duration and sets the task to 100% complete.