## Slide 1: GE404 Engineering Management
Topic1. INTRODUCTION

## Slide 2: GE404 Course Topics Covered
Introduction
  Introduction for project management objectives.
    Project Participants and Project Life Cycle.
Contractual and organizational approaches
Projects Planning
  Processes, and Bar (Gantt) Chart
Network Model
  Scheduling using activity-on-node, precedence methods and time Scaled.
Resource leveling and allocation.
Project time-cost trade-off.
Financial Management: Cashflow Forecasting
Project time and cost control
Analysis of Scheduling Delay

## Slide 3: GE404 Course Learning Objectives
Using bar chart technique to formulate a complete plan for a project.
Apply activity-on-node network, and precedence diagram to schedule a project.
Level and allocate project resources.
Shorten project duration.
Monitor an engineering project for purpose of time and cost control.
Use computer software for preparing project schedules
Understand principles of project organization and contractual relationships including definition of professional responsibilities of project participants.
Students completing this course successfully will be able to:

## Slide 4: GE404 Textbook(s) and/or Other Required Material
Project Management with CPM, PERT, and Precedence Diagramming, 3rd Edition, by Moder J., Phillips, C., and Davis, E.
Construction Planning and Scheduling (4th Edition) by Jimmie W. Hinze, February 28, 2011
Course lectures are also found on the following website:
http://faculty.ksu.edu.sa/algahtani & LMS (Blackboard)

## Slide 5: GE404 Grade Distribution
Mid-term Exams 40 %
Assignments and Quizzes 10 %
Final Examination 50 %

## Slide 6
“A Project is :
  a temporary endeavor undertaken to create a unique product or service or result. (PMI)
  a one-shot, time-limited, goal-directed, major undertaking requiring the commitment of varied skills and resources. (PMI)
  A Combination of human and non-human resources pooled together to achieve a specific purpose and deliverables.
What is a Project?

## Slide 7
Temporary (start, end, project team)
Unique (Product, Service or Result)
Completed (objectives, acceptance& Satisfaction)
Progressive Elaboration
Project variables and parameters (nature, size, budget, resources, complexity)
Project Categories (small, medium, large)
      Source (PMI,2004)
Project Characteristics

## Slide 8
Construction projects of various types as:
  Building projects (Residential as non residential), and Construction projects (dams, tunnels, and bridges, power plants and refineries)
Engineering Projects:
Product Development, Manufacturing, \construction, Design Engineering, Industrial Engineering, technology, production, or any other field that employs personnel who perform an engineering function.
Research and development projects such as the Stealth fighter plan.
Software Development projects such as the university registration computer program.
Project Examples

## Slide 9: Examples of Projects

## Slide 10: Examples of Projects

## Slide 11: Examples of Projects

## Slide 12
  Management is a process concerned with the attainment of objectives.
  Levels of Management
What is Management?
Top
Middle
Low
Project Management
Figure below shows the involvement % of the different levels of management for:
  (Planning vs. controlling)
  (conceptual vs. technical)
Planning
Control
Conceptual
Technical
Top
Management
Middle
Management
Low
Management

## Slide 13
Planning
  What are we aiming for and why?
Organizing
  What’s involved and why?
Motivation
  What motivates people to do their best work?
Directing
  Who decides what and when?
Control
  Who judges results and by what standards?
Management Functions

## Slide 14
What are we aiming for and why?
  Develop project objectives, goals, and strategies.
  Develop project work breakdown structure.
  Develop precedence diagrams to establish logical relationship of project activities and milestones.
  Develop time-based schedule for the project based on the time precedence diagram.
  Plan for the resource support of the project.
Planning

## Slide 15
What is involved and why?
  Establish organizational structure for the team.
  Identify and assign project roles to members of the project team.
  Define project management policies, procedures, and techniques.
  Prepare project management charter and other delegation instruments.
  Establish standards for authority, responsibility and accountability of the project team.
Organizing

## Slide 16
What motivates people to do their best work?
  Determine project team member needs.
  Assess factors that motivate people to do their best work.
  Provide appropriate counseling and mentoring as required.
  Establish rewards program for project team members.
  Conduct initial study of impact of motivation on productivity.
Motivation

## Slide 17
Who decides what and when?
  Establish “limits” of authority for decision making for the allocation of project resources.
  Develop leadership style.
  Enhance interpersonal skills.
  Prepare plan for increasing participative management techniques in managing the project team.
  Develop consensus decision making techniques for the project team.
Directing

## Slide 18
Who judges results and by what standards?
  Establish cost, schedule, and technique performance standards for project.
  Prepare plans for means to evaluate project progress.
  Establish a project management information system for the project.
  Prepare project review strategy.
  Evaluate project progress.
Control

## Slide 19
Project Management is defined as the application of knowledge, skills, tools, and techniques (as optimization) to project activities to meet project requirements (scheduling and resourcing). (PMI, 2004)
What is Project Management?
Project Management involves planning, organizing, staffing, directing, and controlling to achieve an objective with constraints on
  Time
  Cost
  Performance of the end product

## Slide 20
Project Management main Function Activities
  Planning
  Objectives
  Resources
  Work break-down schedule
  Organization
Scheduling
  Project activities
  Start & end times
  Network
  Controlling
  Monitor, compare, revise, action

## Slide 21
Project Management main Function Activities
Before Start of project During
project Timeline project
Budgets
Delayed activities report
Slack activities report
Time/cost estimates
Budgets
Engineering diagrams
Cash flow charts
Material availability details
CPM/PERT
Gantt charts
Milestone charts
Cash flow schedules
Figure 3.1 (from Heizer/Render –Operation Management

## Slide 22
Project sponsor
Project Owner
Project manager
Customer/user
Functional managers
Performing organization
Project team members
Project management team
Internal and external contractors, suppliers and vendors
Government agencies and media
Project Stakeholders

## Slide 23
The main resources are (3M)
Manpower (People)
Money
Materials And Machines.
Project Common Resources

## Slide 24
The objective Key factors affecting and varying the project are:
Scope
Cost
Time, and
Quality (affected by balancing the above three factors)
Project Objective Key Factors
Cost
Time
Scope
Quality
Good Will
Safety

## Slide 25
Within Schedule
Within Budget
Meeting Spec requirements
With minimal or agreed upon scope changes
Without disturbing workflow of organization
Acceptance by customer and or user
Customer Satisfaction
Without negatively affecting corporate culture
Assessing Project Success