## Slide 1
Project Organization

## Slide 2
Contractual and Organizational Approaches
The main objective of Project organization is to establish the relationship among:
  the work to be done
  the people doing the work
  the work place(s)

## Slide 3
Defining The Organization
within the firm
  involves internal organization of personnel.
With other firms
  number of organizations involved
  relationship between the organizations
  when each organization be involved in the project.

## Slide 4
Defining The Organization
Functional Organization
  Personnel organized by FUNCTION, i.e. electronics, software, operations, etc.

## Slide 5
Defining The Organization
Project Organization
  Personnel organized by Projects, i.e. Ka Band receiver, Spectrometer, etc.

## Slide 6
A Sample Project Organization
Test
Engineer
Mechanical
Engineer
Project 1
Project
Manager
Technician
Technician
Project 2
Project
Manager
Electrical
Engineer
Computer Engineer
Marketing
Finance
Human
Resources
Design
Quality
Mgt
Production
President
Figure 3.2 (from Heizer/Render; Operation Management)

## Slide 7
Project Organization Works Best When
Work can be defined with a specific goal and deadline
The job is unique or somewhat unfamiliar to the existing organization
The work contains complex interrelated tasks requiring specialized skills
The project is temporary but critical to the organization
The project cuts across organizational lines

## Slide 8
Project Organization Characteristics
Often temporary structure
Uses specialists from entire company
Headed by project manager
  Coordinates activities
  Monitors schedule and costs
Permanent structure called ‘matrix organization’

## Slide 9
Matrix Organization
Marketing Operations Engineering Finance
Project 1
Project 2
Project 3
Project 4

## Slide 10
Matrix Organization
Each staff member is a member of 2 distinct organizations
  Functional – Electronics, SDD, etc.
  Project – PTCS, Ka Band Receiver, etc.
Different types of Matrix organizations
  Strong Matrix
  Weak Matrix
  Balanced Matrix

## Slide 11
Defining The Organization
Matrix Organization
  Personnel organized in BOTH ways

## Slide 12
Defining The Organization
Matrix Organization
  Personnel organized in BOTH ways

## Slide 13
Defining The Organization
Matrix Organization
  Personnel organized in BOTH ways

## Slide 14
Defining The Organization
Balanced Matrix VS Strong Matrix Organization

## Slide 15
Project Participants
The main participants of a project are:
the Owner:
  construction manager
the Contractor:
  general and subcontractors,
  material and equipment supplier
the designer:
  consultant and architecture engineering A/E

## Slide 16
Organizational Types
Four principal structures of contractual relationship between the project participants:
  Traditional
  Owner-Builder
  Turnkey
  Professional Construction Manager

## Slide 17
Organizational Types

## Slide 18
Organizational Types
1. Traditional
Advantages:
  Widely accepted and historically supported.
  Using lump-sum the overall cost can be determined before awarding the contract.
  Minimal involvement of the owner during construction.
  Design-construct time can be reduced using phased construction.
Disadvantages:
  Design may not benefit from construction expertise.
  Overall design-construct time is usually the longest.
  The owner and the designer are usually in an adversary position with general contractor (maximum vs. minimum quality).
  Change orders will often end in disputes and may drive-up costs.

## Slide 19
Organizational Types

## Slide 20
Organizational Types
2. The Owner-Builder
Advantages:
  Justified when the volume of work is relatively large and relatively constant over a period of time.
  Justified where the project management can be separated from operational management.
  The owner-builder can employ all techniques of the design-constructor, the professional construction manager, and the traditional approach.

## Slide 21
Organizational Types

## Slide 22
Organizational Types
3. Turnkey
Advantages:
  Only one contract for the owner. Design, construction, and know-how are furnished by a single organization.
  Minimal owner coordination -dealing with a single organization.
  Appropriate for unknowledgeable owner.
  Design-construct time can be reduced through using phased construction.
  Construction expertise can be utilized during design phased construction.
  Change orders are easy to handle.
Disadvantages:
  Usually cost cannot be determined before construction.
  If the project cost is fixed price, the overall quality and performance may be affected to ensure profit.
  The owner may not be informed if there is a design or construction problems that may affect the schedule or the cost.

## Slide 23
Organizational Types

## Slide 24
Organizational Types
4. Professional Construction Manager
Advantages:
  Special construction skills may be utilized at all stages of the project with no conflicts of interest between the owner and the designer.
  Independent evaluation of costs, schedules, and overall construction performance, including similar evaluation for changes or modifications helps assure decisions in the best interest of the owner.
  Full-time coordination between design and the construction contractors is available.
  Minimum design-construction time can be achieved through use of phased construction.
  The professional construction manager approach allows price competition from local contractors akin to the traditional lump-sum or unit-price methods.
  Significant opportunities are provided for value engineering in the design, bidding, and award phases.