## Slide 1: Time Planning and Control Activity on Node Network (AON)

## Slide 2
Processes of Time Planning and Control
Processes of Time Planning
Visualize and define the activities.
Sequence the activities (Job Logic).
Estimate the activity duration.
Schedule the project or phase.
Allocate and balance resources.
Processes of Time Control
Compare target, planned and actual dates and update as necessary.
Control the time schedule with respect to changes

## Slide 3
Network Based Project Management
Network Techniques Development:
  CPM by DuPont for chemical plants (1957)
  PERT by Booz, Allen & Hamilton with the U.S. Navy, for Polaris missile (1958)
They consider precedence relationships and interdependencies
Each uses a different estimate of activity times
Developing the Network by:
  Arrow diagramming (AOA)
  Node diagramming (AON)
  Precedence diagramming (APD) –
  Time scaled Network (TSN)

## Slide 4
Each time-consuming activity is portrayed by a rectangular figure.
The dependencies between activities are indicated by dependency lines (arrows) going from one activity to another.
Each activity duration in terms of working days is shown in the upper, central part of the activity box.
The principal advantage of the activity on node network is that it eliminates the need for dummies.
Activity on Node Notation
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 5
Latest
Starting
Date
Latest
Finishing
Date
Total Float
Duration
Earliest
Starting
Date
Earliest
Finishing
Date
EF | D | ES
FF | Activity ID | 
LF | TF | LS
The left side of the activity box (node) is the start side, while the right side is the finish (end) side.
Activity Box
Predecessor
Successor
Free Float
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 6
Each activity in the network must be preceded either by the start of the project or by the completion of a previous activity.
Each path through the network must be continuous with no gaps, discontinuities, or dangling activities.
All activities must have at least one activity following, except the activity that terminates the project.
Each activity should have a unique numerical designation (activity code). Activity code is shown in the upper, central part of the activity box, with the numbering proceeding generally from project start to finish.
Activity on Node Network
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 7
A horizontal diagram format is the standard format.
The general developing of a network is from start to finish, from project beginning on the left to project completion on the right.
The sequential relationship of one activity to another is shown by the dependency lines between them.
The length of the lines between activities has no significance.
Arrowheads are not always shown on the dependency lines because of the obvious left to right flow of time.
Dependency lines that go backward from one activity to another (looping) should not be used.
Crossovers occur when one dependency line must cross over another to satisfy job logic.
Network Format
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 8
The activity list shown below represents the activities, the job logic and the activities’ durations of a small project. Draw an activity on node network to represent the project.
Activity | Depends on | Duration (days)
A B C E F D S R | D R D R, S B, C None A, C A, C | 4 5 8 7 3 4 2 9
Example
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 9
Example
Activity | Depends on | Duration (days)
A B C E F D S R | D R D R, S B, C None A, C A, C | 4 5 8 7 3 4 2 9
D
4
A
4
C
8
E
7
B
5
F
3
END
0
S
2
R
9
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 10
The purpose of network computations is to determine:
  The overall project completion time; and
  The time brackets within which each activity must be accomplished (Activity Times ).
In activity on node network, all of the numbers associated with an activity are incorporated in the one node symbol for the activity, whereas the arrow symbols contain each activity’s data in the predecessor and successor nodes, as well as on the arrow itself or in a table.
ES | Duration | EF
Activity ID |  | FF
LS | TF | LF
Network Computations
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 11: EARLY ACTIVITY TIMES
  The "Early Start" (ES) or "Earliest Start" of an activity is the earliest time that the activity can possibly start allowing for the time required to complete the preceding activities.
  The "Early Finish" (EF) or "Earliest Finish" of an activity is the earliest possible time that it can be completed and is determined by adding that activity's duration to its early start time.
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 12
Direction: Proceed from project start to project finish, from left to right.
Name: This process is called the "forward pass".
Assumption: every activity will start as early as possible. That is to say, each activity will start just as soon as the last of its predecessors is finished.
The ES value of each activity is determined first.
The EF time is obtained by adding the activity duration to the ES time.
EF = ES + D
In case of merge activities the earliest possible start time is equal to the latest (or largest) of the EF values of the immediately preceding activities.
COMPUTATIONS OF EARLY ACTIVITY TIMES
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 13
Example
Calculate the early activity times (ES and EF) and determine project time.
D
4
A
4
C
8
E
7
B
5
F
3
END
0
S
2
R
9
0
4
4
4
8
12
12
12
14
21
21
21
28
26
26
29
29
29
EF = ES + D
Largest EF
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 14
  The “Late Finish" (LF) or "Latest Finish" of an activity is the very latest that it can finish and allow the entire project to be completed by a designated time or date.
  The “Late Start” (LS) or "Latest Start" of an activity is the latest possible time that it can be started if the project target completion date is to be met and is obtained by subtracting the activity's duration from its latest finish time.
LATE ACTIVITY TIMES
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 15
Direction: Proceed from project end to project start, from right to left.
Name: This process is called the “backward pass".
Assumption: Each activity finishes as late as possible without delaying project completion.
The LF value of each activity is obtained first and is entered into the lower right portion of the activity box.
The LS is obtained by subtracting the activity duration from the LF value.
LS = LF - D
In case of burst activities LF value is equal to the earliest (or smallest) of the LS times of the activities following.
COMPUTATIONS OF LATE ACTIVITY TIMES
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 16: Example
Calculate the late activity times (LS and LF).
D
4
A
4
C
8
E
7
B
5
F
3
END
0
S
2
R
9
0
4
4
4
8
12
12
12
14
21
21
21
28
26
26
29
29
29
LS = LF - D
0
8
4
4
12
12
20
12
22
21
22
21
29
26
26
29
29
29
Smallest LS
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 17
FLOAT Time
Float or leeway is a measure of the time available for a given activity above and beyond its estimated duration.
Two classifications of which are in general usage: Total Float and Free Float.
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 18
The total float of an activity is obtained by subtracting its ES time from its LS time. Subtracting the EF from the LF gives the same result.
Total float (TF) = LS - ES = LF - EF
An activity with zero total float has no spare time and is, therefore, one of the operations that controls project completion time.
Activities with zero total float are called "critical activities“.
TOTAL FLOAT
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 19: Example
Calculate Total Float for an activity.
Total float (TF) = LS - ES = LF - EF
D
4
A
4
C
8
E
7
B
5
F
3
END
0
S
2
R
9
0
4
4
4
8
12
12
12
14
21
21
21
28
26
26
29
29
29
0
8
4
4
12
12
20
12
22
21
22
21
29
26
26
29
29
29
0
0
0
0
0
0
1
8
4
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 20
Critical activity is quickly identified as one whose two start times at the left of the activity box are equal. Also equal are the two finish times at the right of the activity box.
The critical activities must form a continuous path from project beginning to project end, this chain of critical activities is called the "critical path".
The critical path is the longest path in the network.
CRITICAL PATH
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 21
The critical path is normally indicated on the diagram in some distinctive way such as with colors, heavy lines, or double lines.
Any delay in the finish date of a critical activity, for whatever reason, automatically prolongs project completion by the same amount.
CRITICAL PATH
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 22
CRITICAL PATH
D
4
A
4
C
8
E
7
B
5
F
3
END
0
S
2
R
9
0
4
4
4
8
12
12
12
14
21
21
21
28
26
26
29
29
29
0
8
4
4
12
12
20
12
22
21
22
21
29
26
26
29
29
29
0
0
0
0
0
0
1
8
4
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 23
The free float of an activity is the amount of time by which the completion of that activity can be deferred without delaying the early start of the following activities.
The free float of an activity is found by subtracting its earliest finish time from the earliest start time of the activities directly following.
FF = The smallest of the ES value of those activities immediately following - EF of the activity.
    = the smallest of the earliest start time of the successor activities minus the earliest finish time of the activity in question.
    FFi = Min. (ESj) - EFi
FREE FLOAT
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 24
Network Analysis (Computation)
  Critical path is the path with the least total float = The longest path through the network.
Critical Path
Subcritical Paths
  Subcritical paths have varying degree of path float and hence depart from criticality by varying amounts.
  Subcritical paths can be found in the following way:
    Sort the activities in the network by their path float, placing those activities with a common path float in the same group.
    Order the activities within a group by early start time.
    Order the groups according to the magnitude of their path float, small values first.

## Slide 25
Draw AON diagram to represent the following project. Calculate occurrence times of events, activity times, and activity floats. Also determine the critical path and the degree of criticality of other float paths.
Activity | Preceding Activity | Time (days)
A | None | 5
B | A | 7
C | A | 4
D | A | 8
E | B | 6
F | D | 8
G | E, C, F | 3
H | G | 4
I | G | 6
Example

## Slide 26
Example
Activity on node network
0
5
5
0
0
5
A
13
8
21
13
0
21
F
5
8
13
5
0
13
D
5
4
9
17
12
21
C
5
7
12
8
3
15
B
12
6
18
15
3
21
E
21
3
24
21
0
24
G
24
4
28
26
2
30
H
24
6
30
24
0
30
I
ES
t
EF
LS
TF
LF
Activity
30
0
30
30
0
30
END

## Slide 27
Activity | ES | EF | LF | LS | TF | FF
A | 0 | 5 | 5 | 0 | 0 | 0
B | 5 | 12 | 15 | 8 | 3 | 0
C | 5 | 9 | 21 | 17 | 12 | 12
D | 5 | 13 | 13 | 5 | 0 | 0
E | 12 | 18 | 21 | 15 | 3 | 3
F | 13 | 21 | 21 | 13 | 0 | 0
G | 21 | 24 | 24 | 21 | 0 | 0
H | 24 | 28 | 30 | 26 | 2 | 2
I | 24 | 30 | 30 | 24 | 0 | 0
Activity times and activity floats
Example

## Slide 28
Activity | ES | EF | LF | LS | TF | Criticality
A | 0 | 5 | 5 | 0 | 0 | Critical Path
D | 5 | 13 | 13 | 5 | 0 | 
F | 13 | 21 | 21 | 13 | 0 | 
G | 21 | 24 | 24 | 21 | 0 | 
I | 24 | 30 | 30 | 24 | 0 | 
H | 24 | 28 | 30 | 26 | 2 | a “near critical” path
B | 5 | 12 | 15 | 8 | 3 | Third most critical path
E | 12 | 18 | 21 | 15 | 3 | 
C | 5 | 9 | 21 | 17 | 12 | Path having most float
Critical path and subcritical paths
Example

## Slide 29
Activity times (ES, EF, LS, LF) obtained from previous calculations are expressed in terms of expired working days.
For purposes of project directing, monitoring and control, it is necessary to convert these times to calendar dates on which each activity is expected to start and finish.
This is done with the aid of a calendar on which the working days are numbered consecutively, starting with number 1 on the anticipated start date and skipping weekends and holidays.
CALENDAR-DATE SCHEDULE
EF | D |  | ES
FF | Activity ID |  | 
LF | TF | LS | 

## Slide 30
Advantages and disadvantages of network diagram
Advantages
  Show precedence well
  Reveal interdependencies not shown in other techniques
  Ability to calculate critical path
  Ability to perform “what if” exercises
Disadvantages
  Default model assumes resources are unlimited
    You need to incorporate this yourself (Resource Dependencies) when determining the “real” Critical Path
  Difficult to follow on large projects

## Slide 31
Example 2: Milwaukee Paper Manufacturing's
Table 3.2 (Frome Heizer/Render; Operation Management)
Activity | Description | Immediate Predecessors | Time (weeks)
A | Build internal components | — | 2
B | Modify roof and floor | — | 3
C | Construct collection stack | A | 2
D | Pour concrete and install frame | A, B | 4
E | Build high-temperature burner | C | 4
F | Install pollution control system | C | 3
G | Install air pollution device | D, E | 5
H | Inspect and test | F, G | 2

## Slide 32
Example 2: Milwaukee Paper Manufacturing's
Start
0
Activity | Description | Immediate Predecessors | Time (weeks)
A | Build internal components | — | 2
B | Modify roof and floor | — | 3
C | Construct collection stack | A | 2
D | Pour concrete and install frame | A, B | 4
E | Build high-temperature burner | C | 4
F | Install pollution control system | C | 3
G | Install air pollution device | D, E | 5
H | Inspect and test | F, G | 2
A
2
B
3
C
2
F
3
D
4
E
4
G
5
H
2

## Slide 33
Example 2: Milwaukee Paper Manufacturing's
Activity | Description | Immediate Predecessors | Time (weeks)
A | Build internal components | — | 2
B | Modify roof and floor | — | 3
C | Construct collection stack | A | 2
D | Pour concrete and install frame | A, B | 4
E | Build high-temperature burner | C | 4
F | Install pollution control system | C | 3
G | Install air pollution device | D, E | 5
H | Inspect and test | F, G | 2
Start
0
A
2
B
3
C
2
F
3
D
4
E
4
G
5
H
2
ES
0
0
EF = ES + Activity time
0
2
2
4
4
7
4
8
0
3
3
7
13
13
15
MAX(EF of Preceding activities 7,8)
8
ES/EF calculation

## Slide 34
Example 2: Milwaukee Paper Manufacturing's
Activity | Description | Immediate Predecessors | Time (weeks)
A | Build internal components | — | 2
B | Modify roof and floor | — | 3
C | Construct collection stack | A | 2
D | Pour concrete and install frame | A, B | 4
E | Build high-temperature burner | C | 4
F | Install pollution control system | C | 3
G | Install air pollution device | D, E | 5
H | Inspect and test | F, G | 2
Start
0
A
2
B
3
C
2
F
3
D
4
E
4
G
5
H
2
0
0
0
2
2
4
4
7
4
8
0
3
3
7
13
13
15
8
LS = LF - Activity time
LS/LF calculation
0
0
0
2
1
4
2
4
8
4
8
8
13
10
13
13
LF = Min(LS of activities 4,10)
4
LF = EF of Project
15

## Slide 35
Example 2: Milwaukee Paper Manufacturing's
Activity | Description | Immediate Predecessors | Time (weeks)
A | Build internal components | — | 2
B | Modify roof and floor | — | 3
C | Construct collection stack | A | 2
D | Pour concrete and install frame | A, B | 4
E | Build high-temperature burner | C | 4
F | Install pollution control system | C | 3
G | Install air pollution device | D, E | 5
H | Inspect and test | F, G | 2
Total Float calculation
Start
0
A
2
B
3
C
2
F
3
D
4
E
4
G
5
H
2
0
0
0
2
2
4
4
7
4
8
0
3
3
7
13
13
15
8
0
0
0
2
1
4
2
4
8
4
8
8
13
10
13
13
4
LF = EF of Project
15
Slack = LS – ES or
Slack = LF – EF
0
0
0
0
0
0
1
1
6

## Slide 36
Example 2: Milwaukee Paper Manufacturing's
Earliest Earliest Latest Latest On Start Finish Start Finish Slack Critical Activity ES EF LS LF LS – ES Path
A 0 2 0 2 0 Yes
B 0 3 1 4 1 No
C 2 4 2 4 0 Yes
D 3 7 4 8 1 No
E 4 8 4 8 0 Yes
F 4 7 10 13 6 No
G 8 13 8 13 0 Yes
H 13 15 13 15 0 Yes
Computing Slack Time (Float Time)

## Slide 37
Example 2: Milwaukee Paper Manufacturing's
Critical Path for Milwaukee Paper: A, C, E, G, H
Start
0
A
2
B
3
C
2
F
3
D
4
E
4
G
5
H
2
0
0
0
2
2
4
4
7
4
8
0
3
3
7
13
13
15
8
0
0
0
2
1
4
2
4
8
4
8
8
13
10
13
13
4
15
0
0
0
0
0
0
1
1
6
Activity | Duration | ES | EF | LS | LF | TF | FF | CP
A | 2 | 0 | 2 | 0 | 2 | 0 | 0 | Y
B | 3 | 0 | 3 | 1 | 4 | 1 | 0 | N
C | 2 | 2 | 4 | 2 | 4 | 0 | 0 | Y
D | 4 | 3 | 7 | 4 | 8 | 1 | 1 | N
E | 4 | 4 | 8 | 4 | 8 | 0 | 0 | Y
F | 3 | 4 | 7 | 10 | 13 | 6 | 6 | N
G | 5 | 8 | 13 | 8 | 13 | 0 | 0 | Y
H | 2 | 13 | 15 | 13 | 15 | 0 | 0 | Y

## Slide 38
Example 2: Milwaukee Paper Manufacturing's
ES –EF GANTT CHART SCHEDULE
 | ACTIVITY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
A | Build internal components |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
C | Construct collection stack |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
E | Build high-temperature burner |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
G | Install air pollution device |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
H | Inspect and test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
B | Modify roof and floor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
D | Pour concrete and install frame |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
F | Install pollution control system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
LS –LF GANTT CHART SCHEDULE
 | ACTIVITY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
A | Build internal components |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
C | Construct collection stack |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
E | Build high-temperature burner |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
G | Install air pollution device |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
H | Inspect and test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
B | Modify roof and floor |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
D | Pour concrete and install frame |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
F | Install pollution control system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |