## Slide 1
Project Cost Control

## Slide 2
To identify those work types having excessive costs and to give an indication of how serious those overruns are.
To forecast the final total job cost.
To indicate the trend for each cost code, that is, whether the unit cost involved has been increasing or decreasing (evaluation of the effectiveness of cost reduction efforts).
To update the database of the company that will be used to estimate future works.
Objectives of Project Cost Control System

## Slide 3
The cost estimate prepared for the project during the bidding process is the basis for cost control.
Cost control for an engineering project is limited to the cost of labor, equipment, materials and site overheads.
Control of cost and time should be linked together.
Project Time Control
Project Cost Control System

## Slide 4
Three Key Indicators in Performance Measurement
Budgeted Cost of Work Scheduled (BCWS) is the budgeted amount of cost of the work scheduled to be accomplished in a given time period (including support and allocated overhead). (This is can be referred to as “planned value of work to be accomplished [PV]”.)
Budgeted Cost of Work Performed (BCWP) is the budgeted amount of cost for the work completed in a given time period, including support effort and allocated overhead. (This is can be referred to as “earned value of work accomplished [EV]”.)
How to calculate BCWP
Budgeted cost for work performed (BCWP) = Earned value of an activity = Percent completed for the activity * the activity budget
Percent completed for an activity = [(Projected duration – Remaining duration) / Projected duration] * 100
Actual Cost of Work Performed (ACWP) OR [AC] is the amount reported as actually expended in completing the particular work accomplished within a given time period.

## Slide 5
BCWP
ACWP
= 0
> 0
< 0
Under budget
Work performed cost > Actual cost
Within budget
Work performed cost = Actual cost
Over budget
Work performed cost < Actual cost
Cost Performance
BCWP
ACWP
= 0
> 0
< 0
Under run
Performed cost > Earned
on run
Performed cost = Earned
Over run
Performed cost < Earned
Cost Performance
The “Cost Overrun” curve is a plot of the calculated percent over- or Underrun at any given time.
BCWP
ACWP
= 1
> 1
< 1
Under budget
Work performed cost > Actual cost
Within budget
Work performed cost = Actual cost
Over budget
Work performed cost < Actual cost
Cost Performance
Performance Equations
Symbol | Definition | التعريف
(BCWS) [PV]” | Budgeted Cost of Work Scheduled “planned value of work to be accomplished | تكلفة موازنة للأعمال المجدولة وفقا للخطة
(BCWP) [EV] | Budgeted Cost of Work Performed “earned value of work accomplished | تكلفة موازنة لما تم من أعمال
(ACWP) [AC] | Actual Cost of Work Performed | التكلفة الفعلية لما تم من أعمال وتم دفعها
Cost Performance Index | CPI = BCWP/ACWP
Cost Variance | CV = BCWP-ACWP
% Cost Overrun/ Underrun | )
% Cost Overrun/ Underrun | 

## Slide 6
BCWP
BCWS
= 1
> 1
< 1
Ahead schedule
Work performed > Work scheduled
On schedule
Work performed = Work scheduled
Behind scheduke
Work performed < Work scheduled
Schedule (Time) Performance
BCWP
BCWS
= 0
> 0
< 0
Ahead schedule
Work performed > Work scheduled
On schedule
Work performed = Work scheduled
Behind scheduke
Work performed < Work scheduled
Schedule (Time) Performance
Performance Equations
Symbol | Definition | التعريف
(BCWS) [PV]” | Budgeted Cost of Work Scheduled “planned value of work to be accomplished | تكلفة موازنة للأعمال المجدولة وفقا للخطة
(BCWP) [EV] | Budgeted Cost of Work Performed “earned value of work accomplished | تكلفة موازنة لما تم من أعمال
(ACWP) [AC] | Actual Cost of Work Performed | التكلفة الفعلية لما تم من أعمال وتم دفعها
Schedule/Performance Variance | SV = BCWP-BCWS
Schedule Performance Index | SPI = BCWP/BCWS

## Slide 7
Symbol | Definition | التعريف
(BCWS) [PV]” | Budgeted Cost of Work Scheduled “planned value of work to be accomplished | تكلفة موازنة للأعمال المجدولة وفقا للخطة
(BCWP) [EV] | Budgeted Cost of Work Performed “earned value of work accomplished | تكلفة موازنة لما تم من أعمال
(ACWP) [AC] | Actual Cost of Work Performed | التكلفة الفعلية لما تم من أعمال وتم دفعها
Estimated Cost At Completion | * BAC, OR
Estimated Cost At Completion | 
Estimate to Completion | ETC = EAC - ACWP
Budget Cost At Completion | BAC = BCWSend
Variance from original budget | VB = EAC - BAC
Cost Forecasting Equations

## Slide 8
BCWS [PV], BCWP [EV], and ACWP[AC] – S-CURVES
BCWP [EV]
BCWS [PV]
ACWP [AC]

## Slide 9
BCWS, BCWP, and ACWP
Under budget (costs below budget) & Ahead of schedule (fast)
Over budget (Over costs) & Ahead of schedule (fast)
Under budget (costs below budget) & Behind schedule (Slow)
Over budget (Over cost) & Behind schedule (Slow)

## Slide 10
Performance report from integrated time/cost control system
BCWS, BCWP, and ACWP

## Slide 11
Example
The following time-scale diagram represents a small engineering project. The budgeted cost of each activity is shown in the table below. At the end of the 10th week, the field progress report gives you the following information:
Activity “A” was completed on schedule.
Activity “B” started as planned but it is expected to take four weeks more.
Activity “C” started as planned but finished one week later.
% age of completion of activity “D” is 60%.
ACWP at the end of week 10 = SR 90400
Calculate the CV, SV, BAC, EAC, ETC, and comment on the progress of the work.
Time (week) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
A (5 weeks) |  |  |  |  | B (8 weeks) |  |  |  |  |  |  |  | E (7 weeks) |  |  |  |  |  |  | F (3 weeks) |  | 
C (5weeks) |  |  |  |  | D (6 weeks) |  |  |  |  |  |  |  | G (4 weeks) |  |  |  |  |  |  |  |  | 
Activity | A | B | C | D | E | F | G
Budgeted cost (SR) | 50000 | 12000 | 16000 | 24000 | 12000 | 21000 | 20000

## Slide 12
% age of completion of activity “A” = 100%
Projected duration of activity “B” = 8 + 4 = 12 weeks
% age of completion of activity “B” = 5/12 = 41.666666%
% age of completion of activity “C” = 100%
BCWS10 = A + C + 5/8*B + 5/6*D = 50000 + 16000 + 5/8*12000 + 5/6*24000 = SR 93500 [remark: 5/8 & 5/6 represent ratio off completion of activities B&D with respect to scheduled duration]
BCWP10 = A + C + 0.4167*12000 + 0.60*24000 = SR 85400 [remark: 0.4167 & 0.6 represent ratio of completion of activities B&D with respect to actual completion duration]
CV = BCWP – ACWP = 85400 – 90400 = SR -5000 (Over Budget)
SV = BCWP – BCWS = 85400 – 93500 = SR -8100 (Behind Schedule)
BAC = 50000 + 12000 + 16000 + 24000 + 12000 + 21000 + 20000 = SR 155000
EAC = [ACWP/BCWP]*BAC = [90400/85400]*155000 = SR 164075
ETC = EAC – ACWP = 164075 – 90400 = SR 73675
Example

## Slide 13
Project Example1
Figure (1) shows a planned schedule and cost of the main product design project activities. Figure (2) gives the planned scheduled for the engineering task activities which should be done within 7 month. A control report should be reported at 3rd month.

## Slide 14
Project Example1
Figure (2) shows that engineering task is done by 9 activities and the status of these activities at the end of 3rd month is reported as follows:
Activity 1- system design: this activity is completed and it actual cost of work performed (ACWP) = $144
Activity 2- Subcontract specs: this activity is started and the scheduled completion is 90.4% while actual completion is 62.1% due delay with paid actual cost of work performed (ACWP) = $84
Activity 3- Material tests: this activity is completed and it actual cost of work performed (ACWP) = $22.5
Activity 4- Specs review: this activity is started and the scheduled completion is 68.75% while actual completion is 46.875% due delay with paid actual cost of work performed (ACWP) = $15.5
Activity 5- Drafting: this activity is started and the scheduled completion is 80.83% while actual completion is 49.167% due delay with paid actual cost of work performed (ACWP) = $59
Activity 6- Fabrication/assembly support: this activity is completed and it actual cost of work performed (ACWP) = $36
Activity 7- Fabrication/assembly process: this activity is started and the scheduled completion is 79.923% while actual completion is 48.462% due delay with paid actual cost of work performed (ACWP) = $67
Activity 8- Test support: this activity is started and the scheduled completion is 21% while actual completion is 21% due delay with paid actual cost of work performed (ACWP) = $21
Activity 9- Engineering release and review: this activity is not started yet

## Slide 15
ENGINEERING SUBTASKS STATUS AT END OF MONTH 3
(thousands of dollars)
Task | Status | BCWS | BCWP | ACWP
System design | Completed | $131.0 | $131.0 | $144.0
Subcontract specs | Started | 132.0 | 82.0 | 84.0
Material tests | Completed | 22.0 | 22.0 | 22.5
Specs review | Started | 22.0 | 15.0 | 15.5
Drafting | Started | 97.0 | 59.0 | 59.0
Fabrication/assembly support | Completed | 29.0 | 29.0 | 36.0
Fabrication/assembly process | Started | 100.0 | 63.0 | 67.0
Test support | Started | 21.0 | 21.0 | 21.0
Engineering release and review | Not Started |  |  | 
Total |  | $554.0 | $422.0 | $449.0
Project Example1
Example of calculation:
BCWS2 = 0.904*146 = 131
BCWP2 = 0.562*146 = 82
The status report is as shown in the table:

## Slide 16
Status summary of engineering subtasks in progress and estimate to complete.
Task | BCWS | BCWP | ACWP | Status
Subcontract specs | $132 | $82 | $84 | Behind schedule and over cost
Specs review | 22 | 15 | 15.5 | Behind schedule and over cost
Drafting | 97 | 59 | 59 | Behind schedule but within cost
Fabrication/assembly process | 100 | 63 | 67 | Behind schedule and over cost
Test support | 21 | 21 | 21 | On schedule and within cost
Estimated at completion: =$812 K |  |  |  | 
Summary: Engineering work is behind schedule and a cost overrun is occurring |  |  |  | 
Project Example1

## Slide 17
Project Example 2
For the following network, compute the early start cumulative costs for the project, and draw the result.
Activity | Depend on | Duration Week | ES Time | LS Time | Cost per week, SR
A |  | 2 | 0 | 0 | 400
B |  | 4 | 0 | 3 | 200
C | A | 5 | 2 | 2 | 300
D | A | 6 | 2 | 5 | 400
E | B, C | 4 | 7 | 7 | 350
F | B, C | 2 | 7 | 7 | 200
G | E | 3 | 11 | 11 | 300
H | D, F | 3 | 9 | 11 | 200

## Slide 18
Cost based on Time Scaled Network (ES)

## Slide 19
Cost based on Time Scaled Network (LS)

## Slide 20
Cumulative Project Cost

## Slide 21
Project Example 3 :
You are required to submit a progress report to your boss about the performance of an activity of a project. The activity’s information as follow: number of units is (800); unit cost is SR 12 ; and planned productivity is 100 unit/day. Performances were measure at the end of day (3) and day (6) as follows:
Period | Cost at this period | Number of units finished
day 0 to day 3 | SR 3,600 | 250
day 4 to day 6 | SR 3,700 | 320
Calculate the following information for each of the two periods (i.e. day 0 to day 3 and day 4 to day 6) and to date (i.e. day 0 to day 3 and day 0 to day 6).
Draw a graphical report for ACWP, BCWP, and BCWS. Discuss the results.
1. This Period |  |  |  |  |  |  | 
Period | BCWP | ACWP | BCWS | Variance |  | STATUS | 
 |  |  |  | Cost | Sch. | Schedule | Cost
0 - 3 | SR 3000 | SR 3600 | SR 3600 | -600 | -600 | Behind | Over Bud.
4 - 6 | SR 3840 | SR 3700 | SR 3600 | 140 | 240 | Ahead | under Bud.
2. To Date |  |  |  |  |  |  |  |  | 
Period | BCWP | ACWP | BCWS | Variance |  | STATUS |  | Estimate at | Day ahead
 |  |  |  | Cost | Sch. | Sch. | Cost | completion | or behind
0 - 3 | SR 3000 | SR 3600 | SR 3600 | -600 | -600 | Behind | Over Bud. | SR 11,520 | 0.5
0 - 6 | SR 6840 | SR 7300 | SR 7200 | -460 | -360 | Behind | Over Bud. | SR 10,446 | 0.3

## Slide 22
b) At this rate, the contractor needs actions to reduce the cost and accelerate the time.
Project Example 3 :

## Slide 23
Project Example 4 :
The following eight activities constitute an overall bar chart project that has twenty-week. Now 10 weeks finished on the project with and the project manager has the following Data:
The weekly planned percentage of completion (inside each activity bar),
The actual percentage of completion up to week 10 (in below activity bar and table),
The Budget cost of each activity (in below table),
Actual Expenses up to week 10 of each activity (in below table),
The Critical Path is A-B-C-D (bolted bar), and Total Float of each activity (dash lines)
ACT | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20
A | 7% | 14% | 20% | 27% | 32% |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | 100 % |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
B |  |  |  |  |  | 5% | 10% | 15% | 19% | 23% | 28% |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  | 60 % |  |  |  |  |  |  |  |  | 
C |  |  |  |  |  |  |  |  |  |  |  | 4% | 7% | 11% | 14% | 18% | 21% | 25% |  | 
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 % |  | 
D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 40% | 60%
 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 %
E |  |  |  |  |  | 40% | 60% |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  | 100 % |  |  |  |  |  |  |  |  |  |  |  |  | 
F |  |  |  |  |  |  |  | 7% | 14% | 20% | 27% | 32% |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  |  | 50 % |  |  |  |  |  |  |  | 
G |  |  |  |  |  | 40% | 60% |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  | 100 % |  |  |  |  |  |  |  |  |  |  |  |  | 
H |  |  |  |  |  |  |  | 10% | 20% | 30% | 40% |  |  |  |  |  |  |  |  | 
 |  |  |  |  |  |  |  |  |  |  | 70 % |  |  |  |  |  |  |  |  | 

## Slide 24
For this point in time (10 weeks after the start date):
Calculate the values of the Budgeted Cost of Work Performed and Budgeted Cost of Work Scheduled for each activity? (8%)
For each activity in progress, calculate the Cost and Schedule Performed Indices and state its budget and schedule status. (3%)
Draw the weekly cumulative BCWS of activity B, determine its delay/Ahead week, and whether it will delay/accelerate the project or not and why. (5%)
Determine the project cost variance and state if the project is over or under budget. (2%)
Based on the performance of past 10 weeks, forecast the project completion cost at the end of the project, and its variance from original project budget. (2%)
Project Example 4 :

## Slide 25
Act. | % of Completion | Budget Cost (SR) | Actual Expenses (SR) | BCWS (SR) | BCWP (SR) | CPI | SPI | Cost Status | Schedule Status
A | 100% | 8000 | 9000 | 8000 | 8000 | 1.13 | 1 |  | 
B | 60% | 10000 | 6000 | 7200 | 6000 | 1 | 1.2 | On Budget | Behind
C | 0% | 11000 | 0 | 0 | 0 |  |  |  | 
D | 0% | 3000 | 0 | 0 | 0 |  |  |  | 
E | 100% | 4000 | 3500 | 4000 | 4000 | 0.88 | 1 |  | 
F | 50% | 7000 | 4000 | 2870 | 3500 | 1.143 | 0.82 | Over Bud. | Ahead
G | 100% | 5000 | 4000 | 5000 | 5000 | 0.8 | 1 |  | 
H | 70% | 6000 | 3900 | 3600 | 4200 | 0.93 | 0.86 | Under Bud. | Ahead
Total |  | 54,000 | 30,400 | 30,670 | 30,700 |  |  |  | 
Project Example 4 : Solution
Parts a) and b),

## Slide 26
0
1000
2000
3000
4000
5000
6000
7000
8000
9000
10000
11000
0
1
2
3
4
5
6
7
Week
SR
½
Week
Project Example 4 : Solution
Parts c)

## Slide 27
This activity will delay the project because it is critical activity.
d) Project cost Variance = BCWPproject  ACWPproject = 30,700  30,400
= SR 300 (Under Budget)
e) Budgeted Cost At Completion (BAC) =  Budget Cost = SR 54,000
Estimated Cost At Completion (EAC) = [ACWP/BCWP]*BAC = SR 53,472.3
OR
Estimated Cost At Completion (EAC) = ACWP + [(BAC – BCWP) / CPI] = SR 53,472.3
Variance from original project budget = EAC  BAC = SR -527.7 (Under Budget)
Project Example 4 : Solution
Parts d) and e),