GE 404 Engineering Management

King Saud University

Tutorial 1: Gantt Bar Chart					     College of Engineering

Department of Civil Engineering

ــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــ

Question No. 1:

- The library at KSU has just received authorization to spend up to SR 40,000 on new journal subscriptions and book purchases. Accordingly, the librarian has developed the following small project.
Draw Gantt bar chart for the library at KSU and use this representation to determine the expected number of weeks it will take before the new materials are in the library.

- Draw Gantt bar chart for this project based on the calendar days instead of the working days : (Use activity duration in days instead of weeks  )

Starts on = start date 02/12/2012.

Holidays= Friday.

Task:

For the following project, Draw Gantt bar chart if the project starts on 3/10/2012 and workdays are six days a week (Sat – Thu).

| Act. | Depends on | Time | Act. | Depends on | Time |
| --- | --- | --- | --- | --- | --- |
| A | None | 2 | D | B, C | 2 |
| B | A | 3 | E | C | 1 |
| C | None | 3 | F | E, B | 4 |