GE 404 Engineering Management

King Saud University

Tutorial 2: Activity on Node (AON)				     College of Engineering

Department of Civil Engineering

ــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــــ

Question No. 1:

For the following small engineering project,

| Act. | Depends on | Time | Act. | Depends on | Time | Act. | Depends on | Time |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | - | 20 | D | B | 12 | G | D | 16 |
| B | A | 8 | E | C | 16 | H | D, E, F | 8 |
| C | A | 6 | F | C | 18 | I | F | 10 |
| J | G, H, I | 10 |  |  |  |  |  |  |

- Draw the AON diagram.

- The activity durations are in working days. It is required to compute the activity times (ES, EF, LS, and LF), free floats (FF) and total floats (TF) and then indicate the critical activities.

Task:

For the following small engineering project,

| Act. | Depends on | Time | Act. | Depends on | Time |
| --- | --- | --- | --- | --- | --- |
| A | - | 12 | D | A | 18 |
| B | A | 16 | E | B , C | 8 |
| C | A | 8 | F | D , E | 10 |

- Draw the AON diagram.

- The activity durations are in working days. It is required to compute the activity times (ES, EF, LS, and LF), free floats (FF) and total floats (TF) and then indicate the critical activities.