## Slide 1: Studio 4. Project Planning and Literature Review
FALL 2019
Class Lecture: Dr. Raja Rizwan Hussain
Subject: GE105
Introduction to Engineering Design College of Engineering
King Saud University

## Slide 2: Project Planning
Contents:
Literature Review
Group Activity

## Slide 3: Project Planning

## Slide 4
Assigning tasks to the wrong individuals
Poor Planning of Tasks
Failure to Implement the tasks
You do not manage time
You manage your commitments
Poor Estimation of the difficulty or risks or resources
Bad Management
Studies report that nearly half of all projects initiated are not completed because of:
The Main Reason For Failure: You Don’t Start Soon Enough

## Slide 5: Project Parameters
Project Parameters
Quality
Specifications
Budget*
Cost*
Time
Schedule
Target
YOUR TIME
Due Date
Notes: Parameters: معايير
Specifications: مواصفات
Triple Constraint Theory (read about it here: https://programsuccess.wordpress.com/2011/05/02/scope-time-and-cost-managing-the-triple-constraint/)
Projects are constrained by three variables:
  specification
  time
  resources
These are not mutually exclusive
Errors or overruns in one are likely to have knock-on effects on the others
* What is the difference between Cost and Budget? (Budget: is what you are allowed to spend, Cost: the price of the final product)

## Slide 6: Phases of Project Planning
Define the project’s scope* (including literature review given at the end of these slides)
Develop the project’s plan
Implement the plan
Control the process
Complete the project
What is a project plan?
Can be as simple as a list of sequences for a small project
Can be more complex with charts, tables, costings etc. for a larger project
4
Notes: * i.e. what you must do to achieve target (just a list)

## Slide 7: Develop the Project’s Plan
Break Down Project
Tasks (WBS)
Time Estimation &
Dependencies
Assign Tasks
Develop Gantt Chart
Review & adjust
Task 1 – 20hrs
Task 2 – 10hrs – FS 1
Task 3 – 15hrs – SS 1
Task 4 – 25hrs – FF 2
Task | Hrs | Who
Act. 1 | 10 | Ali
Act. 2 | 7 | Ahmed
Act. 3 | 13 | Omar
Notes: Planning is an iterative process. Some projects won’t require a proposal
* WBS: work breakdown structure

## Slide 8: Work Breakdown Structure (WBS)
A hierarchical representation of activities
It starts with the major project tasks to be accomplished
It breaks the project tasks into actionable* pieces of work, segmenting elements into appropriate sublevels
Number of levels depends on project complexity
Notes: * Usually this means that such actions are designed to be performed by a single person within a ‘reasonable’ amount of time (e.g. week – ten days)

## Slide 9: Task Dependencies
Dependencies are the relationships between activities
“Finish to Start (FS)” example
Task B cannot begin until Task A is complete
Examples of other dependency types:
Start-Start (SS): have to start at the same time
Finish-Finish (FF): have to end at the same time
Unconstrained: the task can start at any time
A
B
Notes: The most common type of linkage is Finish to Start

## Slide 10: Network Charts
Task 1 – 20hrs
Task 2 – 10hrs – FS 1
Task 3 – 15hrs – FS 1
Task 4 – 25hrs – FS 2
Task 1
Task 2
Task 3
Task 4
Task 5
Task 6
Task 7

## Slide 11: Responsibility Matrix
Task | Hours Needed* | Who
Activity 1 | 10 | Ali
Activity 2 | 7 | Ahmed
Activity 3 | 13 | Abdullah
Creates accountability by assigning each task to the person with the right skill
Notes: * Q: how can you assess how much time a task needs? Usually, this comes with experience, and from reading other projects

## Slide 12
Generated from Network Chart
In a single page, it graphically shows :
    Timeline for each task
    Dependencies of tasks
    Progress towards project completion
May include initials of the responsible for each task
  “Milestone" events marked with a special symbol
Gantt Chart Basics
Notes: * Note, student must be familiar with -and show- all 4 planning stages: WBS, Network Chart, Responsibility Matrix, Gantt Chart

## Slide 13
Task | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7
Literature Review |  |  |  |  |  |  | 
Requirement Analysis |  |  |  |  |  |  | 
Human Factors |  |  |  |  |  |  | 
Problem Formulation |  |  |  |  |  |  | 
Progress Report |  |  |  |  |  |  | 
Concept generation |  |  |  |  |  |  | 
Creative Design |  |  |  |  |  |  | 
Design evaluation |  |  |  |  |  |  | 
Final Report |  |  |  |  |  |  | 
Gantt Chart Example*
Notes: * Note, you can –possibly– change task color to match person (and include a key to the colors to match the person)
Watch the following video on how to create a basic Gantt chart in excel 2016: https://youtu.be/xgxXpLnx-R4 also: https://youtu.be/-oD50HSBBBI

## Slide 14: Project Planning Summary
Create WBS to identify activities
Estimate time durations
Note dependencies between tasks
Assign the right person to the right task
Schedule activities using a Gantt chart
Put plan into action
Document, document, document !

## Slide 15: Literature Review

## Slide 16: Purpose of a literature review
Find out what others did and avoid duplication of efforts
Learn from achievements/failures of other engineers
Better identify and estimate the risk in achieving the tasks
Highlight gaps and under-researched areas
Find ideas about approaches and methods which had not occurred to you
Learn how you might classify and present your own data*
Notes: * Indeed, after a literature search and review the focus of the research may change or be slanted somewhat differently.

## Slide 17: Literature Review model
Example: you may be researching the academic performance of Saudi students in higher education
Higher education
Academic performance*
Saudi students
Notes: * This is the kind of figure (Venn diagram) that is useful to bear in mind if you are carrying out an online search. You can enter as many subject keywords as you think are relevant for each component of your topic. The search engine will combine the subject terms for you when you perform your search.

## Slide 18: Where do you search?
Internet
  Use keyword searches in Google Scholar: http://scholar.google.com/
Digital Libraries*
  Need to use accurate keywords to identify relevant articles
Libraries
  Look through the list of journals and browse the books on the shelves to find relevant ones
Notes: * One of the best digital libraries accessible to all KSU students is: http://www.sciencedirect.com/

## Slide 19: Basic Steps
Identify a coherent set of keywords
Concise and exhaustive
Example:
(Saudi students OR Saudi education OR Saudi learning) AND (academic performance OR academic achievement ) AND (higher education OR colleges OR universities)
Search your sources for relevant publications (Identify search time-span*)
Notes: * i.e. indicate in your Gantt chart how much time it took you to search for all your references/sources

## Slide 20
Compile and sort the collected material
Extract a list of references
Refer to references whenever contents are used
Include this list of references in your final document
Write your literature review*
Always acknowledge the source of information
Do NOT copy word-for-word from a reference
Adhere to ethical norms and avoid plagiarism; This issue will be looked at very seriously throughout the course
Notes: * Watch the following video on how to perform a successful literature review: https://youtu.be/2IUZWZX4OGI

## Slide 21: Group Activity

## Slide 22: Project Planning Class Activity
Create a work breakdown structure for your project and an initial Gantt Chart
Watch the following great video for ideas: https://youtu.be/ADK58IRPKh8 *
Decide on the appropriate keywords for your projects’ literature review
Notes: * Also check out How to make a Basic Gantt Chart in Microsoft Excel: