## Slide 1
Time-Cost Trade-Off (Time Reduction = Time Compression)
(Time Shortening)

## Slide 2: Reasons to Reduce Project Durations:
Shortening the duration is called project crashing
To avoid late penalties (or avoid damaging the company’s relationship)
To realize incentive pay (monetary incentives for timely or early competition of a project
To beat the competition to the market to fit within the contractually required time (influences Bid Price)
To free resources for use on other projects (complete a project early & move on to another project)
To reduce the indirect costs associated with running the project
To complete a project when weather conditions make it less expensive (Avoid temporary heating, avoid completing site work during raining season)
Many things make crashing a way of life on some projects (i.e. last minutes changes in client specification, without permission to extend the project deadline by an appropriate increment)

## Slide 3
Methods to reduce durations
Overtime: Have the existing crew work overtime. This increase the labor costs due to increase pay rate and decrease productivity.
Hiring and/or Subcontracting:
  Bring in additional workers to enlarge crew size. This increases labor costs due to overcrowding and poor learning curve.
  Add subcontracted labor to the activity. This almost always increases the cost of an activity unless the subcontracted labor is far more efficient.
Use of advanced technology: Use better/more advanced equipment. This will usually increase costs due to rental and transport fees. If labor costs (per unit) are reduced, this could reduce costs.

## Slide 4
How project cost is estimated?
Practices to Estimate the Project Cost
Some company assigns Overhead office as % of direct cost.
Most companies don’t consider profit as a cost of the job.
Cost analysis are completed by using:
  [Direct costs + Indirect costs + Company overhead] vs. Budgeted (estimated costs)
Similar to each activity, the project as a whole has an ideal (least expensive) duration.

## Slide 5
How project cost is estimated?

## Slide 6
How project is crashed?
Specify 2 activity times and 2 costs
1st time/cost combination (D, CD)- called Normal [Normal – usual ‘average’ time, resources]
2nd time/cost combination (d, Cd)- called Crash [Expedite by applying additional resources]

## Slide 7
General 2 Steps in Project Crashing
In order to speed up any project schedule with a minimum cost, you need to follow these two general steps:
  Select the Critical Path Activities.
  Within the critical path activities, select the lowest reduction cost rate “Cost Slope” to reduce it.
In following slides more details on these 2 General Steps

## Slide 8
Steps in Project Crashing
Compute the crash cost per time period. If crash costs are linear over time:
Using current activity times, find the critical path and identify the critical activities
Basic Steps

## Slide 9
Steps in Project Crashing
If there is only one critical path, then select the activity on this critical path that (a) can still be crashed, and (b) has the smallest crash cost per period.
If there is more than one critical path, then select one activity from each critical path such that (a) each selected activity can still be crashed, and (b) the total crash cost of all selected activities is the smallest.
Note that the same activity may be common to more than one critical path.
Update all activity times. If the desired due date has been reached, stop. If not, return to Step 2.

## Slide 10
Example1: Crashing The Project
Critical Path for Milwaukee Paper (A, C, E, G, H)
Start
0
A
2
B
3
C
2
F
3
D
4
E
4
G
5
H
2
0
0
0
2
2
4
4
7
4
8
0
3
3
7
13
13
15
8
0
0
0
2
1
4
2
4
8
4
8
8
13
10
13
13
4
15
0
0
0
0
0
0
1
1
6

## Slide 11
Example1: Crashing The Project
Table 3.16 (Frome Heizer/Render; Operation Management)
CALCULATION OF CRAH COST/PERIOD
Crash and Normal Times and Costs for Activity B
| | |
1 2 3 Time (Weeks)
$34,000 —
$33,000 —
$32,000 —
$31,000 —
$30,000 —
—
Activity Cost
Crash
Normal
Crash Time, d
Normal Time, D
Crash Cost, Cd
Normal Cost, CD
Crash Cost/Wk =
Crash Cost – Normal Cost
Normal Time – Crash Time
=
$34,000 – $30,000
3 – 1
= = $2,000/Wk
$4,000
2 Wks

## Slide 12
Example1: Crashing The Project
Time (Wks) Cost ($)
Crash Cost Critical Activity Normal Crash Normal Crash Per Wk ($) Path?
A 2 1 22,000 22,750 750 Yes
B 3 1 30,000 34,000 2,000 No
C 2 1 26,000 27,000 1,000 Yes
D 4 2 48,000 49,000 1,000 No
E 4 2 56,000 58,000 1,000 Yes
F 3 2 30,000 30,500 500 No
G 5 2 80,000 84,500 1,500 Yes
H 2 1 16,000 19,000 3,000 Yes
Table 3.5 (Frome Heizer/Render; Operation Management)

## Slide 13
Example2: Crashing Project
Activity | Precedence | Normal |  | Crash | 
 |  | Time, day | Cost, $ | Time, day | Cost, $
A | - | 4 | 210 | 3 | 280
B | - | 8 | 400 | 6 | 560
C | A | 6 | 500 | 4 | 600
D | A | 9 | 540 | 7 | 600
E | B,C | 4 | 500 | 1 | 1100
F | C | 5 | 150 | 4 | 240
G | E | 3 | 150 | 3 | 150
H | D,F | 7 | 600 | 6 | 750
 |  | Σ | 3050 |  | 4280
For the small project shown in the table, it is required to reduce the project duration.
Reduce by 2 periods.
Reduce by 5 periods.

## Slide 14
Example2: Crashing Project
1- develop network
A
4
C
6
B
8
E
4
G
3
F
5
H
7
START
FINISH
D
9
Activity | Precedence | Normal |  | Crash | 
 |  | Time, day | Cost, $ | Time, day | Cost, $
A | - | 4 | 210 | 3 | 280
B | - | 8 | 400 | 6 | 560
C | A | 6 | 500 | 4 | 600
D | A | 9 | 540 | 7 | 600
E | B,C | 4 | 500 | 1 | 1100
F | C | 5 | 150 | 4 | 240
G | E | 3 | 150 | 3 | 150
H | D,F | 7 | 600 | 6 | 750
 |  | Σ | 3050 |  | 4280

## Slide 15
Example2: Crashing Project
A
0
4
4
0
0
4
C
4
6
10
4
0
10
B
0
8
8
7
7
15
E
10
4
14
15
5
19
G
14
3
17
19
5
22
F
10
5
15
10
0
15
H
15
7
22
15
0
22
0
0
0
0
0
0
START
22
0
22
22
0
22
FINISH
D
4
9
13
6
2
15
Activity | A | B | C | D | E | F | G | H
Total float | 0 | 7 | 0 | 2 | 5 | 0 | 5 | 0
Free float | 0 | 2 | 0 | 2 | 0 | 0 | 5 | 0
Project completion time = 22 working days
Critical Path: A, C, F, H.
2- calculate times, find critical path

## Slide 16
Example2: Crashing Project
Activity | Precedence | Normal |  | Crash | 
 |  | Time, day | Cost, $ | Time, day | Cost, $
A | - | 4 | 210 | 3 | 280
B | - | 8 | 400 | 6 | 560
C | A | 6 | 500 | 4 | 600
D | A | 9 | 540 | 7 | 600
E | B,C | 4 | 500 | 1 | 1100
F | C | 5 | 150 | 4 | 240
G | E | 3 | 150 | 3 | 150
H | D,F | 7 | 600 | 6 | 750
 |  | Σ | 3050 |  | 4280
Cost Slope, $/day
70
80
50
30
200
90
**
150
Remarks
1- [G can not expedite]
2- lowest slope and can be expedited on critical path is activity (C) WITH 2 periods
3- calculate cost slope

## Slide 17
Example2: Crashing Project
A
0
4
4
0
0
4
C
4
4
8
4
0
8
B
0
8
8
5
5
13
E
8
4
12
13
5
17
G
12
3
15
17
5
20
F
8
5
13
8
0
13
H
13
7
20
13
0
20
0
0
0
0
0
0
START
20
0
20
20
0
20
FINISH
D
4
9
13
4
0
13
Activity | A | B | C | D | E | F | G | H
Total float | 0 | 5 | 0 | 0 | 5 | 0 | 5 | 0
Free float | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0
Project completion time = 20 working days
Critical Path: A, C, F, H. & A, D, H
Reduce 2 periods of activity (C) with increase of cost (2*50) =100
Activity | Precedence | Normal |  | Crash |  | Cost Slope,
 |  | Time, day | Cost, $ | Time, day | Cost, $ | $/day
A | - | 4 | 210 | 3 | 280 | 70
B | - | 8 | 400 | 6 | 560 | 80
C | A | 6 | 500 | 4 | 600 | 50
D | A | 9 | 540 | 7 | 600 | 30
E | B,C | 4 | 500 | 1 | 1100 | 200
F | C | 5 | 150 | 4 | 240 | 90
G | E | 3 | 150 | 3 | 150 | **
H | D,F | 7 | 600 | 6 | 750 | 150
 |  | Σ | 3050 |  | 4280 | 
ES
LS
EF
TF
LF
Activity
Crash limit (d @ cost)

## Slide 18
Example2: Crashing Project
A
0
3
3
0
0
3
C
3
4
7
3
0
7
B
0
8
8
8
4
12
E
7
4
11
12
5
16
G
11
3
14
16
5
19
F
7
5
12
7
0
12
H
12
7
19
12
0
19
0
0
0
0
0
0
START
19
0
19
19
0
19
FINISH
D
3
9
12
3
0
12
Activity | A | B | C | D | E | F | G | H
Total float | 0 | 4 | 0 | 0 | 5 | 0 | 5 | 0
Free float | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0
Project completion time = 19 working days
Critical Path: A, C, F, H. & A, D, H
Reduce 1 period of activity (A) with increase of cost =70
Activity | Precedence | Normal |  | Crash |  | Cost Slope,
 |  | Time, day | Cost, $ | Time, day | Cost, $ | $/day
A | - | 4 | 210 | 3 | 280 | 70
B | - | 8 | 400 | 6 | 560 | 80
C | A | 6 | 500 | 4 | 600 | 50
D | A | 9 | 540 | 7 | 600 | 30
E | B,C | 4 | 500 | 1 | 1100 | 200
F | C | 5 | 150 | 4 | 240 | 90
G | E | 3 | 150 | 3 | 150 | **
H | D,F | 7 | 600 | 6 | 750 | 150
 |  | Σ | 3050 |  | 4280 | 

## Slide 19
Example2: Crashing Project
Activity | A | B | C | D | E | F | G | H
Total float | 0 | 3 | 0 | 0 | 4 | 0 | 4 | 0
Free float | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
Project completion time = 19 working days
Critical Path: A, C, F, H. & A, D, H
Reduce farther 1 period of 2 activities (D,F) with increase of cost (30+90) =120
Activity | Precedence | Normal |  | Crash |  | Cost Slope,
 |  | Time, day | Cost, $ | Time, day | Cost, $ | $/day
A | - | 4 | 210 | 3 | 280 | 70
B | - | 8 | 400 | 6 | 560 | 80
C | A | 6 | 500 | 4 | 600 | 50
D | A | 9 | 540 | 7 | 600 | 30
E | B,C | 4 | 500 | 1 | 1100 | 200
F | C | 5 | 150 | 4 | 240 | 90
G | E | 3 | 150 | 3 | 150 | **
H | D,F | 7 | 600 | 6 | 750 | 150
 |  | Σ | 3050 |  | 4280 | 
A
0
3
3
0
0
3
C
3
4
7
3
0
7
B
0
8
8
3
3
11
E
7
4
11
11
4
15
G
11
3
14
15
4
18
F
7
4
11
7
0
11
H
11
7
18
11
0
18
0
0
0
0
0
0
START
18
0
18
18
0
18
FINISH
D
3
8
11
3
0
11

## Slide 20
Example2: Crashing Project
Activity | A | B | C | D | E | F | G | H
Total float | 0 | 2 | 0 | 0 | 3 | 0 | 3 | 0
Free float | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
Project completion time = 19 working days
Critical Path: A, C, F, H. & A, D, H
Reduce farther 1 period of activity (H) with increase of cost =150
Activity | Precedence | Normal |  | Crash |  | Cost Slope,
 |  | Time, day | Cost, $ | Time, day | Cost, $ | $/day
A | - | 4 | 210 | 3 | 280 | 70
B | - | 8 | 400 | 6 | 560 | 80
C | A | 6 | 500 | 4 | 600 | 50
D | A | 9 | 540 | 7 | 600 | 30
E | B,C | 4 | 500 | 1 | 1100 | 200
F | C | 5 | 150 | 4 | 240 | 90
G | E | 3 | 150 | 3 | 150 | **
H | D,F | 7 | 600 | 6 | 750 | 150
 |  | Σ | 3050 |  | 4280 | 
A
0
3
3
0
0
3
C
3
4
7
3
0
7
B
0
8
8
2
2
10
E
7
4
11
10
3
14
G
11
3
14
14
3
17
F
7
4
11
7
0
11
H
11
6
17
11
0
17
0
0
0
0
0
0
START
17
0
17
17
0
17
FINISH
D
3
8
11
3
0
11

## Slide 21
Example2: Crashing Project
Reduction from 22 to 17 increase to 3490
Activity | Precedence | Normal |  | Crash |  | Cost Slope,
 |  | Time, day | Cost, $ | Time, day | Cost, $ | $/day
A | - | 4 | 210 | 3 | 280 | 70
B | - | 8 | 400 | 6 | 560 | 80
C | A | 6 | 500 | 4 | 600 | 50
D | A | 9 | 540 | 7 | 600 | 30
E | B,C | 4 | 500 | 1 | 1100 | 200
F | C | 5 | 150 | 4 | 240 | 90
G | E | 3 | 150 | 3 | 150 | **
H | D,F | 7 | 600 | 6 | 750 | 150
 |  | Σ | 3050 |  | 4280 | 
Chart: Project Duration
| 22 | 20 | 19 | 18 | 17
 | 3050 | 3150 | 3220 | 3340 | 3490
Cycle | Activity | Time | cost | Total cost | Duration
0 | - |  |  | 3050 | 22
1 | C | 2 | 100 | 3150 | 20
2 | A | 1 | 70 | 3220 | 19
3 | D,F | 1 | 30+90 | 3340 | 18
4 | H | 1 | 150 | 3490 | 17

## Slide 22
Accelerating the Critical and Noncritical path
Activity | Precedence | Normal |  | Crash |  | Cost Slope,
 |  | Time, day | Cost, $ | Time, day | Cost, $ | $/day
A | - | 4 | 210 | 3 | 280 | 70
B | - | 8 | 400 | 6 | 560 | 80
C | A | 6 | 500 | 4 | 600 | 50
D | A | 9 | 540 | 7 | 600 | 30
E | B,C | 4 | 500 | 1 | 1100 | 200
F | C | 5 | 150 | 4 | 240 | 90
G | E | 3 | 150 | 3 | 150 | **
H | D,F | 7 | 600 | 6 | 750 | 150
 |  | Σ | 3050 |  | 4280 | 
Example2: Crashing Project

## Slide 23
Determine Normal project duration, and cost.
How project is crashed?
Network Compression Algorithm
Identify Normal duration Critical Path.
For large network, using CRITICALITY THEOREM to eliminate the noncritical paths that do not need to be crashed.
  Eliminate Activities with having “TF > the required project reduction time”.
Compute the cost slop

## Slide 24
Network Compression Algorithm
Shortening the CRITICAL ACTIVITIES beginning with the activity having the lowest cost-slope
Organize the data as in the following table:
Determine the compression limit (Nil)
How project is crashed?

## Slide 25
Network Compression Algorithm
Update the project network
When a new Critical Path is formed:
  Shorten the combination of activity which Falls on Both Critical Paths, OR
  Shorten one activity from each of the critical paths. Use the combined cost of shortening both activities when determining if it is cost-effective to shorten the project.
At each shortening cycle, compute the new project duration and project cost
Continue until no further shortening is possible
How project is crashed?

## Slide 26
Network Compression Algorithm
Use the total project cost-time curve to find the optimum time.
Tabulate and Plot the Indirect project Cost on the same time-cost graph
Add direct and indirect cost to find the project cost at each duration.
How project is crashed?

## Slide 27
38470
Example 3

## Slide 28
Example 3
Cycle # | Activity to Shorten | Can Be Shortened | Nil | Weeks Shortened | Cost per Week | Cost for Cycle | Total Cost | Project Duration
0 |  |  |  |  |  |  | 36,500 | 59
1 | G | 5 | 2 | 2 | 60 | 120 | 36,620 | 57
2@100
0
12
12
0
0
12
A
1@300
27
5
32
29
2
34
F
3@200
12
15
27
12
0
27
C
2@150
12
8
20
14
2
22
B
0
20
23
43
24
4
47
D
1@50
20
5
25
22
2
27
E
5@60
27
20
47
27
0
47
G
2@75
47
12
59
47
0
59
I
2@40
32
13
45
34
2
47
H
ES
D
EF
LS
TF
LF
Activity
Crash limit
4
2
We have one critical path, A-C-G- I.
Either crash A at cost SR 100/week or crash C at cost SR 200/week or
crash G at cost SR 60/week or
crash I at cost SR 75/week.

## Slide 29
2@100
0
12
12
0
0
12
A
1@300
27
5
32
27
0
32
F
3@200
12
15
27
12
0
27
C
2@150
12
8
20
14
2
22
B
0
20
23
43
22
2
45
D
1@50
20
5
25
22
2
27
E
3@60
27
18
45
27
0
47
G
2@75
45
12
57
45
0
55
I
2@40
32
13
45
32
0
45
H
ES
D
EF
LS
TF
LF
Activity
Crash limit
Cycle # | Activity to Shorten | Can Be Shortened | Nil | Weeks Shortened | Cost per Week | Cost for Cycle | Total Cost | Project Duration
0 |  |  |  |  |  |  | 36,500 | 59
1 | G | 5 | 2 | 2 | 60 | 120 | 36,620 | 57
2 | I | 2 |  | 2 | 75 | 150 | 36,770 | 55
Now we have two critical paths:
A-C-F-H-I and A-C-G- I.
Either crash A at cost SR 100/week or crash C at cost SR 200/week or
crash I at cost SR 75/week or
crash F and G at cost SR 360/week or
crash H and G at cost SR 100/week.
2
Example 3

## Slide 30
2@100
0
12
12
0
0
12
A
1@300
27
5
32
27
0
32
F
3@200
12
15
27
12
0
27
C
2@150
12
8
20
14
2
22
B
0
20
23
43
22
2
45
D
1@50
20
5
25
22
2
27
E
3@60
27
18
45
27
0
45
G
0
45
10
55
45
0
55
I
2@40
32
13
45
32
0
45
H
ES
D
EF
LS
TF
LF
Activity
Crash limit
Cycle # | Activity to Shorten | Can Be Shortened | Nil | Weeks Shortened | Cost per Week | Cost for Cycle | Total Cost | Project Duration
0 |  |  |  |  |  |  | 36,500 | 59
1 | G | 5 | 2 | 2 | 60 | 120 | 36,620 | 57
2 | I | 2 |  | 2 | 75 | 150 | 36,770 | 55
3 | A | 2 |  | 2 | 100 | 200 | 36,970 | 53
Now we have two critical paths:
A-C-F-H-I and A-C-G- I.
Either crash A at cost SR 100/week or crash C at cost SR 200/week or
crash F and G at cost SR 360/week or
crash H and G at cost SR 100/week.
2
Example 3

## Slide 31
0
0
10
10
0
0
10
A
1@300
25
5
30
25
0
30
F
3@200
10
15
25
10
0
25
C
2@150
10
8
18
12
2
20
B
0
18
23
41
20
2
43
D
1@50
18
5
23
20
2
25
E
3@60
25
18
43
25
0
43
G
0
43
10
53
43
0
53
I
2@40
30
13
43
30
0
43
H
ES
D
EF
LS
TF
LF
Activity
Crash limit
2
Cycle # | Activity to Shorten | Can Be Shortened | Nil | Weeks Shortened | Cost per Week | Cost for Cycle | Total Cost | Project Duration
0 |  |  |  |  |  |  | 36,500 | 59
1 | G | 5 | 2 | 2 | 60 | 120 | 36,620 | 57
2 | I | 2 |  | 2 | 75 | 150 | 36,770 | 55
3 | A | 2 |  | 2 | 100 | 200 | 36,970 | 53
4 | H, G | 2 | 2 | 2 | 60+40 | 200 | 37,170 | 51
Now we have two critical paths:
A-C-F-H-I and A-C-G- I.
Either crash C at cost SR 200/week or
crash F and G at cost SR 360/week or
crash H and G at cost SR 100/week.
Example 3

## Slide 32
0
0
10
10
0
0
10
A
1@300
25
5
30
25
0
30
F
3@200
10
15
25
10
0
25
C
2@150
10
8
18
10
0
18
B
0
18
23
41
18
0
41
D
1@50
18
5
23
20
2
25
E
1@60
25
16
41
25
0
41
G
0
41
10
51
41
0
51
I
0
30
11
41
30
0
41
H
ES
D
EF
LS
TF
LF
Activity
Crash limit
0
Cycle # | Activity to Shorten | Can Be Shortened | Nil | Weeks Shortened | Cost per Week | Cost for Cycle | Total Cost | Project Duration
0 |  |  |  |  |  |  | 36,500 | 59
1 | G | 5 | 2 | 2 | 60 | 120 | 36,620 | 57
2 | I | 2 |  | 2 | 75 | 150 | 36,770 | 55
3 | A | 2 |  | 2 | 100 | 200 | 36,970 | 53
4 | G, H | 2 | 2 | 2 | 60+40 | 200 | 37,170 | 51
5 | B, C | 2 |  | 2 | 150+200 | 700 | 37,870 | 49
Now we have three critical paths;
A-C-F-H-I, A-C-G- I, and A-B-D-I.
Either crash C and B at cost SR 350/week or
crash F, G and B at cost SR 510/week.
Example 3

## Slide 33
Example 3 – Final Results
0
0
10
10
0
0
10
A
1@300
23
5
28
23
0
28
F
1@200
10
13
23
10
0
23
C
0
10
6
16
10
0
16
B
0
16
23
39
16
0
39
D
1@50
16
5
21
18
2
23
E
1@60
23
16
39
23
0
39
G
0
39
10
49
39
0
49
I
0
28
11
39
28
0
39
H
ES
D
EF
LS
TF
LF
Activity
Crash limit
Cycle # | Project Duration | Direct Cost | Indirect Cost | Total Cost
0 | 59 | 36500 | 7375 | 43875
1 | 57 | 36620 | 7125 | 43745
2 | 55 | 36770 | 6875 | 43645
3 | 53 | 36970 | 6625 | 43595
4 | 51 | 37170 | 6375 | 43545
5 | 49 | 37870 | 6125 | 43995

## Slide 34: Project Optimal Duration
Example 3 – Final Results

## Slide 35
CASE WORK
Activity | Depends | Normal |  | Crash | 
 | on | Time | Cost | Time | Cost
A |  | 6 days | SR700 | 4 days | SR800
B |  | 4 days | 400 | 4 days | 400
C |  | 5 days | 650 | 4 days | 700
D | A | 8 days | 625 | 5 days | 700
E | B | 10 days | 200 | 7 days | 350
F | B | 7 days | 500 | 5 days | 700
G | C | 3 days | 600 | 3 days | 600
H | D, E | 6 days | 300 | 5 days | 400
I | F, G | 7 days | 350 | 4 days | 425
Data on small maintenance project is given as below: On completion, the project will give a return of SR110/day. Using time-cost trade-off method, how much would you like to compress the project for maximizing the return (ignore the Indirect cost effect)? Show all calculations.